## Slide 1
Campus Management Application
At
World Skill Center
WEEKLY PROJECT STATUS REPORT
02-June-2023

## Slide 2: PROJECT SUMMARY
OVERALL PROJECT STATUS (R)ed, (A)mber, (G)reen | DELAY
PROJECT NAME | Campus Management Application At World Skill Center(WSC) |  | 
SOUL POC | sharmistha.panda@soulunileaders.com | WSC POC | 
PROJECT START DATE | 03-02-2023 | PROJECT END DATE | 03-02-2024
Red | Likely delay in overall project schedule | Amber | Some Activities are delayed | Green | On track

## Slide 3: TASKS PLANNED/ACCOMPLISHED THIS WEEK
TASKS |  |  | 
Description | Owner | Status | Remarks
Training Gap Analysis and SRS documents Sign off | WSC | PARTIAL | 25/05: SOUL team reminded for sign off (email) 29/05: Digital sign-off received A meeting will be scheduled by WSC stakeholders for physical sign off
Placement Gap Analysis and SRS documents Sign off | WSC | PARTIAL | 25/05: SOUL team reminded for sign off (email) 29/05: Digital sign-off received A meeting will be scheduled for physical sign off
Academy - Gap Analysis and SRS documents Sign off | WSC | PARTIAL | 29/05: SOUL team reminded for sign off (email) 29/05: Digital sign-off received A meeting will be scheduled for physical sign off
School Of Engineering (SOE) - Gap Analysis and SRS documents Sign off | WSC | PARTIAL | 26/05: SOUL team reminded for sign off (email) 31/05: Digital sign-off received for ToT documents A meeting will be scheduled for physical sign off

## Slide 4: TASKS PLANNED/ACCOMPLISHED THIS WEEK
TASKS |  |  | 
Description | Owner | Status | Remarks
Admission Gap Analysis and SRS documents Sign off | WSC | PARTIAL | 25/05: SOUL team reminded for sign off (email) 31/05: Digital sign-off received A meeting will be scheduled by WSC stakeholders for physical sign off
Procurement and Inventory Management Gap analysis and SRS documents Sign off | WSC | PARTIAL | 25/05: SOUL team reminded for sign off (email) 02/06: Digital sign-off received A meeting will be scheduled by WSC stakeholders for physical sign off
HRMS Gap analysis and SRS documents Sign off | WSC | PARTIAL | 25/05: SOUL team reminded for sign off (email) 02/06: Digital sign-off received A meeting will be scheduled by WSC stakeholders for physical sign off

## Slide 5: TASKS PLANNED/ACCOMPLISHED THIS WEEK
TASKS |  |  | 
Description | Owner | Status | Remarks
School Of Services (SOS) - Gap Analysis and SRS documents Sign off | WSC | PARTIAL | 18/05: SOUL team reminded for sign off (email) 18/05: Digital sign-off received A meeting will be scheduled for physical sign off
Examination - Gap Analysis and SRS documents Sign off | WSC | PARTIAL | 29/05: SOUL shared the documents 31/05: Digital sign-off received A meeting will be scheduled for physical sign off
Infrastructure - Gap Analysis and SRS documents Sign off Project Monitoring Tool Infrastructure Management and Maintenance | WSC | DELAYED | 29/05: SOUL team reminded for sign off (email) 01/06: SOUL team reminded for sign off over phone Update: No response received
Finance & Accounting Gap Analysis and SRS documents Sign off | WSC | DELAYED | 29/05: SOUL team shared updated documents Update: No response received

## Slide 6: TASKS PLANNED/ACCOMPLISHED THIS WEEK
TASKS |  |  | 
Description | Owner | Status | Remarks
Integration - Payment Gateway | SOUL - WSC | ON GOING | Meeting initiated on 12 May 2023 Update 16/05: Meeting with POS team Update : Follow up email sent by SOUL to provide the POS device 02/06: Follow up email sent by SOUL team
SOUL will share the updated version of Gap analysis and SRS documents with Finance & Accounting SME for sign off | SOUL | DONE | SOUL shared the documents on May 29th 2023

## Slide 7: OVERALL PROJECT PROGRESS TIMELINE

## Slide 8: ISSUES
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
A delay in discussing and capturing requirements | High | The revised project plan was discussed on 06-Apr, during weekly Project review meeting update : schedule has been reviwed with WSC stakeholders | WSC | OPEN | WSC stakeholders to acknowledge the delay | 
SOUL highlighted the addition to scope (change request) for the features that were discovered during the requirements study but were not specified in the request for proposal document | High | WSC stakeholders to acknowledge the change request | SOUL - WSC | OPEN | SOUL will discuss the change request details with WSC stakeholder during upcoming weekly project review meeting | Change request lists are attached to this report

## Slide 9: ISSUES
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
Procurement & Inventory Gap analysis and SRS documents sign off | High | WSC stakeholder to ensure that documents are signed off on time | WSC | OPEN | WSC Stakeholders to coordinate with SME's for timely sign off | SOUL has received digital sign off. Physical sign off to be scheduled
HRMS Gap analysis and SRS documents sign off | High | WSC stakeholder to ensure that documents are signed off on time | WSC | OPEN | WSC Stakeholders to coordinate with SME's for timely sign off | SOUL has received digital sign off. Physical sign off to be scheduled

## Slide 10: ISSUES
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
Admission (Students support) Gap analysis and SRS documents sign off | High | WSC stakeholder to ensure that documents are signed off on time | WSC | OPEN | WSC Stakeholders to coordinate with SME's for timely sign off | SOUL has received digital sign off. Physical sign off to be scheduled
SOE Gap analysis and SRS documents sign off | High | WSC stakeholder to ensure that documents are signed off on time | WSC | OPEN | WSC Stakeholders to coordinate with SME's for timely sign off | SOUL has received digital sign off for ToT. Yet to receive for Academics Physical sign off to be scheduled

## Slide 11: ISSUES
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
Academy Gap analysis and SRS documents sign off | High | WSC stakeholder to ensure that documents are signed off on time | WSC | OPEN | WSC Stakeholders to coordinate with SME's for timely sign off | SOUL has received digital sign off for ToT. Physical sign off to be scheduled
SOS Gap analysis and SRS documents sign off | High | WSC stakeholder to ensure that documents are signed off on time | WSC | OPEN | WSC Stakeholders to coordinate with SME's for timely sign off | SOUL has received digital sign off for ToT. Physical sign off to be scheduled
SOS Gap analysis and SRS documents sign off | High | WSC stakeholder to ensure that documents are signed off on time | WSC | OPEN | WSC Stakeholders to coordinate with SME's for timely sign off | SOUL has received digital sign off for ToT. Physical sign off to be scheduled

## Slide 12: ISSUES
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
Training Gap analysis and SRS documents sign off by WSC SME's | High | WSC stakeholder to ensure that documents are signed off on time | WSC | OPEN | WSC Stakeholders to coordinate with SME's for timely sign off | SOUL has received digital sign off. Physical sign off to be scheduled
Placement Gap analysis and SRS documents sign off by WSC SME's | High | WSC stakeholder to ensure that documents are signed off on time | WSC | OPEN | WSC Stakeholders to coordinate with SME's for timely sign off | SOUL has received digital sign off. Physical sign off to be scheduled
Finance & Accounting Gap analysis and SRS documents sign off by WSC SME's | High | WSC stakeholder to ensure that documents are signed off on time | WSC | OPEN | WSC Stakeholders to coordinate with SME's for timely sign off | SOUL yet to receive digital sign off

## Slide 13: ISSUES
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
Availability of OCAC server | High | WSC stakeholder to ensure availability of the requested server version | WSC | OPEN | WSC stakeholder to communicate preferred choices to SOUL | 31/05: SOUL, WSC and OSDC had a meeting to discuss the server issue. Update: Since OSDC is unable to provide the required server version, SOUL team has suggested alternate options to WSC

## Slide 14: CHANGE REQUESTS
Description | Module
Entrance Examination Process | Students Management
TrainingOfTrainers(TOT) | Students Management
Recruitment Process | Human Resources Management System
Employee Re-Engagement | Human Resources Management System
Budget | Finance & Accounting
Payroll | Finance & Accounting
Testing effort for application installation in desktop version | OCAC Server

## Slide 15: UPCOMING WORK
WHAT’S NEXT |  |  | 
Description | Owner | Status | Remarks
Physical sign off | WSC | OPEN | To be scheduled by WSC
Monthly Steering Committee meeting | SOUL - WSC | OPEN | Not Started
Required information / template from Admission - Documents verification checklist | SOUL - WSC | OPEN | SOUL team will send an email to WSC director for assistance
Start of design phase | SOUL | OPEN | 

## Slide 16
THANK YOU