## Slide 1
Campus Management Application
At
World Skill Center
WEEKLY PROJECT STATUS REPORT
04-Aug-2023

## Slide 2: PROJECT SUMMARY
OVERALL PROJECT STATUS (R)ed, (A)mber, (G)reen | DELAY
PROJECT NAME | Campus Management Application At World Skill Center(WSC) |  | 
SOUL POC | sharmistha.panda@soulunileaders.com | WSC POC | 
PROJECT START DATE | 03-02-2023 | PROJECT END DATE | 03-02-2024
Red | Likely delay in overall project schedule | Amber | Some Activities are delayed | Green | On track

## Slide 3: TASKS PLANNED/ACCOMPLISHED THIS WEEK
TASKS |  |  | 
Description | Owner | Status | Remarks
Integration - Payment Gateway | SOUL - WSC | ON GOING | 28-Jul-23: SOUL team is integrating the code to test server for HDFC team to verify / audit the payment flow Update: Internal test and the server set up is in progress
Design phase | SOUL | ON GOING | 28-Jul-23: Training & Placement, Infrastructure and Procurement design documents have been shared with WSC IT team Update: Finance and Accounting document shall be shared in the upcoming week
Role permission template | SOUL | ON GOING | 28-Jul-23: WSC has shared HRMS roles permission. SLCM role permission is pending Update: SLCM role permission shall be shared by WSC in the upcoming week

## Slide 4: TASKS PLANNED/ACCOMPLISHED THIS WEEK
TASKS |  |  | 
Description | Owner | Status | Remarks
Master data template for SLCM and HRMS | SOUL | ON GOING | 28-Jul-23: WSC has shared HRMS master data, SLCM is on-going and to be shared Update: Meeting was held to clarify queries raised by WSC. The master data shall be shared by WSC in the upcoming week
Templates for development | WSC | ON GOING | WSC will be sharing the corporate calendar template

## Slide 5: OVERALL PROJECT PROGRESS TIMELINE

## Slide 6: ISSUES
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
A delay in discussing and capturing requirements | High | The revised project plan was discussed on 06-Apr, during weekly Project review meeting update : schedule has been reviwed with WSC stakeholders | WSC | OPEN | WSC stakeholders to acknowledge the delay | 
SOUL highlighted the addition to scope (change request) for the features that were discovered during the requirements study but were not specified in the request for proposal document | High | WSC stakeholders to acknowledge the change request | WSC | OPEN | The change requests will be acknowledged by WSC | Update: SOUL team sent an email to WSC to acknowledge the change reqests and the additional effort required for development. The change requests have been listed in Slide 8

## Slide 7: ISSUES
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
Availability of OCAC server | High | WSC stakeholder to ensure availability of the requested server version | WSC | OPEN | SOUL team has installed the application and database on the same server in the desktop version WSC to acknowledge the additional effort required (CR) to test the desktop version of the application | 

## Slide 8: CHANGE REQUESTS
Description | Module
Entrance Examination Process | Students Management
TrainingOfTrainers(TOT) | Students Management
Recruitment Process | Human Resources Management System
Employee Re-Engagement | Human Resources Management System
Testing effort for application installation in desktop version | OCAC Server
As discussed on 9th June 2023, the change requests Budget and Payroll have been removed from the the list

## Slide 9: UPCOMING WORK
WHAT’S NEXT |  |  | 
Description | Owner | Status | Remarks
Monthly Steering Committee meeting | WSC | OPEN | WSC will coordinate with higher management / relevant stakeholders on their availability for the Steering Committee Meeting
Continuation of the design phase - Design documentation | SOUL | OPEN | Finance and Accounting will be shared

## Slide 10
THANK YOU