## Slide 1
Campus Management Application
At
World Skill Center
WEEKLY PROJECT STATUS REPORT
12-May-2023

## Slide 2: PROJECT SUMMARY
OVERALL PROJECT STATUS (R)ed, (A)mber, (G)reen | DELAY
PROJECT NAME | Campus Management Application At World Skill Center(WSC) |  | 
SOUL POC | sharmistha.panda@soulunileaders.com | WSC POC | 
PROJECT START DATE | 03-02-2023 | PROJECT END DATE | 03-02-2024
Red | Likely delay in overall project schedule | Amber | Some Activities are delayed | Green | On track

## Slide 3: TASKS PLANNED/ACCOMPLISHED THIS WEEK
TASKS |  |  | 
Description | Owner | Status | Remarks
Gap analysis and SRS walkthrough of Training of Trainers and Academics with SOE WSC SME’s | SOUL and WSC | DONE | Completed SRS walkthrough on 09 May and 10 May 2023
Gap analysis and SRS walkthrough of Infrastructure and Project management module with WSC SME’s | SOUL and WSC | ON GOING | Completed SRS walkthrough of Project plan monitoring and Infrastructure management and maintenance on 11th / 12th May with respective WSC SME’s
Gap analysis and SRS documents shared with Procurement and Inventory Management WSC SME (Mr. Chandan Kumar) for sign off | WSC | DELAYED | Documents shared on 27th Apr 2023. WSC SME to sign the documents and share it with SOUL by 3rd May 2023 Update: No response received from WSC SME
Gap analysis and SRS documents shared with HRMS WSC SME’s for sign off | WSC | DELAYED | 02-May-23: SOUL shared the Gap analysis and SRS documents.WSC SME’s to sign off by 5th May 2023 Update: No response received from WSC SME

## Slide 4: TASKS PLANNED/ACCOMPLISHED THIS WEEK
TASKS |  |  | 
Description | Owner | Status | Remarks
Gap analysis and SRS documents shared with Admission WSC SME’s for sign off | WSC | DELAYED | 3-May-23: SOUL shared the Gap analysis and SRS documents.WSC SME’s to sign off by 5th May 2023 Update: No response received from WSC SME
Gap analysis and requirements study for PayRoll | SOUL and WSC | DONE | Completed on 9th May 2023
SRS walkthrough of Trainig module with WSC SME | SOUL and WSC | DONE | Completed on 10th May 2023
SRS documents shared with Training WSC SME’s for sign off | WSC | OPEN | Documents shared by SOUL on 12th May 2023
SRS walkthrough of Tot and Life Skills with WSC Academy SME’s | SOUL and WSC | ON GOING | Completed SRS walkthrough on 10 May 2023 WSC SME will share their business process flow with SOUL for further discussion
Gap analysis and SRS walkthrough of Finance and Accounting module with WSC SME’s | SOUL and WSC | NOT STARTED | 12-May-23: Communication sent to WSC SME's for their availability to review the SRS (walkthrough)

## Slide 5: TASKS PLANNED/ACCOMPLISHED THIS WEEK
TASKS |  |  | 
Description | Owner | Status | Remarks
Integration - Payment Gateway | SOUL - WSC | ON GOING | Meeting initiated on 12 May 2023

## Slide 6: OVERALL PROJECT PROGRESS TIMELINE

## Slide 7: ISSUES
ISSUES |  |  |  |  |  | 
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
A delay in discussing and capturing requirements | High | The revised project plan was discussed on 06-Apr, during weekly Project review meeting update : schedule has been reviwed with WSC stakeholders | WSC | OPEN | WSC stakeholders to acknowledge the delay | 
Unavailibity of WSC SME’s for requirments gathering of Students Management module and Procurement and Inventory | High | WSC leadership team to ensure availability of the SME’s or concerned team | WSC | CLOSED | Discussed on 6th Apr, during weekly Project review meeting. WSC stakeholder’s will raise it to the concerned authority | Discussed the point on 27th Apr during weekly project review meeting

## Slide 8: ISSUES
ISSUES |  |  |  |  |  | 
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
Faculty workload, Appraisal template to be discussed with WSC Principal | High | Meeting will be organised by WSC stakeholder | WSC | OPEN | WSC stakeholders to arrange a meeting with the WSC Principal or senior management to discuss all open (pending) issues | 20-Apr-23: SOUL team communicated to WSC stakeholder Update(5/5): SOUL team discussed with WSC stakeholder on 4th May
The accounting requirements meeting was delayed since WSC SME was late | High | WSC stakeholder to ensure SME’s availability for the scheduled meetings | WSC | CLOSED | WSC Stakeholders to coordinate with the SME's for their timely availability | SOUL team raised the issue during weekly project review meeting on 4th May 2023
Procurement & Inventory Gap analysis and SRS documents sign off by WSC SME's | High | WSC stakeholder to ensuree that documents are signed off on time | WSC | OPEN | WSC Stakeholders to coordinate with SME's for timely sign off | Numerous follow up done by SOUL team 12/05 - WSC stakeholder coordinated with the SME to send the approval

## Slide 9: ISSUES
ISSUES |  |  |  |  |  | 
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
Unavailability of WSC SME’s SOE for SRS walkthrough | High | WSC stakeholder to ensure availability of SME’s | WSC | CLOSED | WSC Stakeholders to coordinate with SME's for SRS walkthrough participation | Numerous follow up done by SOUL team 12/05 - WSC stakeholder coordinated with the SME for walkthrough
Required information / template from Admission / Examination / Procurement WSC SME’s | High | Dependency on WSC stakeholders to ensure information is shared with SOUL team | WSC | OPEN | WSC stakeholders will coordinate with all the SME’s to participate in weekly review meeting in order to to discuss and resolve open issues | Update(12/05): SOUL team coordinated with examination SME and received the required templates WSC stakeholder coordinated with students support SME’s for discussion of students grievance and students feedback

## Slide 10: ISSUES
ISSUES |  |  |  |  |  | 
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
HRMS Gap analysis and SRS documents sign off by WSC SME's | High | WSC stakeholder to ensure that documents are signed off on time | WSC | OPEN | WSC Stakeholders to coordinate with SME's for timely sign off | Numerous follow up done by SOUL team
Availability of OCAC server | High | WSC stakeholder to ensure availability of the requested server version | WSC | OPEN | SOUL technical team / higher mgmt and WSC higher mgmt to discuss the issue | SOUL has been provided with desktop version

## Slide 11: RISKS & ISSUES
RISKS |  |  |  | 
Description | Risk Impact | Mitigation | Risk Owner | Status

## Slide 12: UPCOMING WORK
WHAT’S NEXT |  |  | 
Description | Owner | Status | Remarks
SRS walkthrough with finance and accounting WSC SME’s | SOUL - WSC | Open | SOUL has proposed the dates to WSC SME’s
Monthly Steering Committee meeting | SOUL - WSC | Open | Not Started
Gap analysis and SRS documents sign off by Training WSC SME | SOUL - WSC | Open | Not Started
SRS documents walkthrough with Examination | SOUL - WSC | Open | Meeting scheduled on 15th May
Integration - Payment Gateway | SOUL - WSC | Open | Another meeting scheduled on 16th May 2023
Placement module requirements study with WSC SME’s | SOUL - WSC | Open | Meeting scheduled on 15th May
Gap analysis and SRS documents sign off by WSC SOS | SOUL - WSC | Open | Not Started

## Slide 13
THANK YOU