## Slide 1
Campus Management Application
At
World Skill Center
WEEKLY PROJECT STATUS REPORT
15-June-2023

## Slide 2: PROJECT SUMMARY
OVERALL PROJECT STATUS (R)ed, (A)mber, (G)reen | DELAY
PROJECT NAME | Campus Management Application At World Skill Center(WSC) |  | 
SOUL POC | sharmistha.panda@soulunileaders.com | WSC POC | 
PROJECT START DATE | 03-02-2023 | PROJECT END DATE | 03-02-2024
Red | Likely delay in overall project schedule | Amber | Some Activities are delayed | Green | On track

## Slide 3: TASKS PLANNED/ACCOMPLISHED THIS WEEK
TASKS |  |  | 
Description | Owner | Status | Remarks
SRS Physical Sign Off | WSC | ON GOING | Sign Off done on 12th June for the following: Academy, SOS, SOE and Admission HRMS Training & Placement Infrastructure Management and Maintenance Finance and Accounting
Integration - Payment Gateway | SOUL - WSC | ON GOING | SOUL team is awaiting for test url from WSC
Start of Design phase | SOUL | ON GOING | SOUL team has started working on the design phase. Design phase plan will be shared in next week’s Project review meeting

## Slide 4: OVERALL PROJECT PROGRESS TIMELINE

## Slide 5: ISSUES
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
A delay in discussing and capturing requirements | High | The revised project plan was discussed on 06-Apr, during weekly Project review meeting update : schedule has been reviwed with WSC stakeholders | WSC | OPEN | WSC stakeholders to acknowledge the delay | 
SOUL highlighted the addition to scope (change request) for the features that were discovered during the requirements study but were not specified in the request for proposal document | High | WSC stakeholders to acknowledge the change request | WSC | OPEN | The change requests will be acknowledged by WSC | SOUL team discussed the change requests on June 9th 2023. Update: SOUL team sent an email to WSC to acknowledge the change reqests and the additional effort required for development

## Slide 6: ISSUES
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
Procurement & Inventory Gap analysis and SRS documents sign off | High | WSC stakeholder to ensure that documents are signed off on time | WSC | OPEN | WSC Stakeholders to coordinate with SME's for timely sign off | SOUL has received digital sign off for ToT. Physical sign off to be done
HRMS Gap analysis and SRS documents sign off | High | WSC stakeholder to ensure that documents are signed off on time | WSC | DONE | WSC Stakeholders to coordinate with SME's for timely sign off | Physical sign off done on June 12th

## Slide 7: ISSUES
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
Admission (Students support) Gap analysis and SRS documents sign off | High | WSC stakeholder to ensure that documents are signed off on time | WSC | DONE | WSC Stakeholders to coordinate with SME's for timely sign off | Physical sign off done on June 12th
SOE Gap analysis and SRS documents sign off | High | WSC stakeholder to ensure that documents are signed off on time | WSC | OPEN | WSC Stakeholders to coordinate with SME's for timely sign off | Physical sign off done on June 12th

## Slide 8: ISSUES
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
Academy Gap analysis and SRS documents sign off | High | WSC stakeholder to ensure that documents are signed off on time | WSC | DONE | WSC Stakeholders to coordinate with SME's for timely sign off | Physical sign off done on June 12th
SOS Gap analysis and SRS documents sign off | High | WSC stakeholder to ensure that documents are signed off on time | WSC | DONE | WSC Stakeholders to coordinate with SME's for timely sign off | Physical sign off done on June 12th
Examination Gap analysis and SRS documents sign off | High | WSC stakeholder to ensure that documents are signed off on time | WSC | OPEN | WSC Stakeholders to coordinate with SME's for timely sign off | SOUL has received digital sign off for ToT. Physical sign off to be done

## Slide 9: ISSUES
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
Training Gap analysis and SRS documents sign off by WSC SME's | High | WSC stakeholder to ensure that documents are signed off on time | WSC | DONE | WSC Stakeholders to coordinate with SME's for timely sign off | Physical sign off done on June 12th
Placement Gap analysis and SRS documents sign off by WSC SME's | High | WSC stakeholder to ensure that documents are signed off on time | WSC | DONE | WSC Stakeholders to coordinate with SME's for timely sign off | Physical sign off done on June 12th
Finance & Accounting Gap analysis and SRS documents sign off by WSC SME's | High | WSC stakeholder to ensure that documents are signed off on time | WSC | DONE | WSC Stakeholders to coordinate with SME's for timely sign off | Physical sign off done on June 12th

## Slide 10: ISSUES
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
Availability of OCAC server | High | WSC stakeholder to ensure availability of the requested server version | WSC | OPEN | SOUL team will install the application and database on the same server and test the desktop version of the application | WSC to acknowledge the additional effort required (CR) to test the desktop version of the application

## Slide 11: CHANGE REQUESTS
Description | Module
Entrance Examination Process | Students Management
TrainingOfTrainers(TOT) | Students Management
Recruitment Process | Human Resources Management System
Employee Re-Engagement | Human Resources Management System
Budget | Finance & Accounting
Payroll | Finance & Accounting
Testing effort for application installation in desktop version | OCAC Server

## Slide 12: UPCOMING WORK
WHAT’S NEXT |  |  | 
Description | Owner | Status | Remarks
Monthly Steering Committee meeting | WSC | OPEN | To be scheduled by WSC
Design phase plan | SOUL | OPEN | The plan will be shared by SOUL team during upcoming project review meeting

## Slide 13
THANK YOU