## Slide 1
Campus Management Application
At
World Skill Center
WEEKLY PROJECT STATUS REPORT
19-May-2023

## Slide 2: PROJECT SUMMARY
OVERALL PROJECT STATUS (R)ed, (A)mber, (G)reen | DELAY
PROJECT NAME | Campus Management Application At World Skill Center(WSC) |  | 
SOUL POC | sharmistha.panda@soulunileaders.com | WSC POC | 
PROJECT START DATE | 03-02-2023 | PROJECT END DATE | 03-02-2024
Red | Likely delay in overall project schedule | Amber | Some Activities are delayed | Green | On track

## Slide 3: TASKS PLANNED/ACCOMPLISHED THIS WEEK
TASKS |  |  | 
Description | Owner | Status | Remarks
Placement module requirements study with WSC SME’s | SOUL - WSC | DONE | Meeting conducted on 15th May
Gap analysis and SRS walkthrough of Infrastructure and Project management module with WSC SME’s | SOUL and WSC | DONE | Completed SRS walkthrough of Project plan monitoring and Infrastructure management and maintenance on 11th / 12th May with respective WSC SME’s
Gap analysis and SRS documents shared with Procurement and Inventory Management WSC SME (Mr. Chandan Kumar) for sign off | WSC | DELAYED | Documents shared on 27th Apr 2023. WSC SME to sign the documents and share it with SOUL by 3rd May 2023 Update: No response received from WSC SME
Gap analysis and SRS documents shared with HRMS WSC SME’s for sign off | WSC | DELAYED | 02-May-23: SOUL shared the Gap analysis and SRS documents.WSC SME’s to sign off by 5th May 2023 Update: No response received from WSC SME

## Slide 4: TASKS PLANNED/ACCOMPLISHED THIS WEEK
TASKS |  |  | 
Description | Owner | Status | Remarks
Gap analysis and SRS documents shared with Admission WSC SME’s for sign off | WSC | DELAYED | 3-May-23: SOUL shared the Gap analysis and SRS documents.WSC SME’s to sign off by 5th May 2023 Update: No response received from WSC SME
Gap analysis and SRS documents of Training with WSC SME’s for sign off | WSC | DELAYED | Documents shared by SOUL on 12th May 2023 Update: No response received from WSC SME
SRS walkthrough of Tot and Life Skills with WSC Academy SME’s | SOUL and WSC | DELAYED | Completed SRS walkthrough on 10 May 2023 WSC SME will share their business process flow with SOUL for further discussion Update: Meeting to be scheduled with WSC SME for another session of walkthrough
Gap analysis and SRS walkthrough of Finance and Accounting module with WSC SME’s | SOUL and WSC | NOT STARTED | 12-May-23: Communication sent to WSC SME's for their availability to review the SRS (walkthrough) Update: Meeting for walkthrough to be scheduled on 22 May 2023

## Slide 5: TASKS PLANNED/ACCOMPLISHED THIS WEEK
TASKS |  |  | 
Description | Owner | Status | Remarks
Integration - Payment Gateway | SOUL - WSC | ON GOING | Meeting initiated on 12 May 2023 Update 16/05: Meeting with POS team Update : Follow up email sent by SOUL to provide the POS device
SRS documents walkthrough with Examination | SOUL - WSC | ON GOING | Walkthrough done on 15th & 16th May 2023 Update 18/05 : SOUL will share the updated SRS and another discussion to be scheduled with exam coordinators
Gap analysis and SRS documents sign off by WSC SOS | SOUL - WSC | DONE | Sign Off / Acknowledgement received by WSC SME on 18 May 2023
SOUL highlighted the addition to scope (change request) for the features that were discovered during the requirements study but were not specified in the request for proposal document | SOUL - WSC | ON GOING | The point was discussed during project review meeting with WSC stakeholder

## Slide 6: TASKS PLANNED/ACCOMPLISHED THIS WEEK
TASKS |  |  | 
Description | Owner | Status | Remarks
Placement SRS documents shared with WSC SME for sign off | WSC | ON GOING | Documents shared on 19 May 2023

## Slide 7: OVERALL PROJECT PROGRESS TIMELINE

## Slide 8: ISSUES
ISSUES |  |  |  |  |  | 
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
A delay in discussing and capturing requirements | High | The revised project plan was discussed on 06-Apr, during weekly Project review meeting update : schedule has been reviwed with WSC stakeholders | WSC | OPEN | WSC stakeholders to acknowledge the delay | 
Faculty workload, Appraisal template to be discussed with WSC Principal | High | Meeting will be organised by WSC stakeholder | WSC | OPEN | WSC stakeholders to arrange a meeting with the WSC Principal or senior management to discuss all open (pending) issues | 20-Apr-23: SOUL team communicated to WSC stakeholder Update(05/May): SOUL team discussed with WSC stakeholder on 4th May

## Slide 9: ISSUES
ISSUES |  |  |  |  |  | 
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
Procurement & Inventory Gap analysis and SRS documents sign off by WSC SME's | High | WSC stakeholder to ensuree that documents are signed off on time | WSC | OPEN | WSC Stakeholders to coordinate with SME's for timely sign off | Numerous follow up done by SOUL team 12/05 - WSC stakeholder coordinated with the SME to send the approval Update 18/05: SRS sign off shall be discussed during WSC stakeholders meeting
Required information / template from Admission / Examination / Procurement WSC SME’s | High | Dependency on WSC stakeholders to ensure information is shared with SOUL team | WSC | OPEN | WSC stakeholders will coordinate with all the SME’s to participate in weekly review meeting in order to to discuss and resolve open issues | Update(12/05): SOUL team coordinated with examination SME and received the required templates WSC stakeholder coordinated with students support SME’s for discussion of students grievance and students feedback

## Slide 10: ISSUES
ISSUES |  |  |  |  |  | 
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
HRMS Gap analysis and SRS documents sign off by WSC SME's | High | WSC stakeholder to ensure that documents are signed off on time | WSC | OPEN | WSC Stakeholders to coordinate with SME's for timely sign off | Numerous follow up done by SOUL team Update 18/05: SRS sign off shall be discussed during WSC stakeholders meeting
Admission (Students support) Gap analysis and SRS documents sign off by WSC SME's | High | WSC stakeholder to ensure that documents are signed off on time | WSC | OPEN | WSC Stakeholders to coordinate with SME's for timely sign off | Numerous follow up done by SOUL team Update 12/05 : WSC stakeholder coordinated with SME to sign off the documents Update 18/05: SRS sign off shall be discussed during WSC stakeholders meeting

## Slide 11: ISSUES
ISSUES |  |  |  |  |  | 
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
Gap analysis and SRS documents sign off by WSC SOE | High | WSC stakeholder to ensure that documents are signed off on time | WSC | OPEN | WSC Stakeholders to coordinate with SME's for timely sign off | Numerous follow up done by SOUL team Update 18/05: SRS sign off shall be discussed during WSC stakeholders meeting
Training Gap analysis and SRS documents sign off by WSC SME's | High | WSC stakeholder to ensure that documents are signed off on time | WSC | OPEN | WSC Stakeholders to coordinate with SME's for timely sign off | Numerous follow up done by SOUL team Update 18/05: SRS sign off shall be discussed during WSC stakeholders meeting
Availability of OCAC server | High | WSC stakeholder to ensure availability of the requested server version | WSC | OPEN | SOUL technical team / higher mgmt and WSC higher mgmt to discuss the issue | SOUL has been provided with desktop version Update 18/05: OCAC poc stated server version with CentOS shall be provided. SOUL will check with technical team for feasibility

## Slide 12: RISKS & ISSUES
RISKS |  |  |  | 
Description | Risk Impact | Mitigation | Risk Owner | Status

## Slide 13: UPCOMING WORK
WHAT’S NEXT |  |  | 
Description | Owner | Status | Remarks
SRS walkthrough with finance and accounting WSC SME’s | SOUL - WSC | Open | Meeting proposed for 22nd May 2023
Monthly Steering Committee meeting | SOUL - WSC | Open | Not Started
SRS documents of Placement to be shared with WSC SME for sign off | SOUL - WSC | Open | Not Started
Meeting with WSC SME’s and Stakeholders | WSC | Open | To be scheduled

## Slide 14
THANK YOU