## Slide 1
Campus Management Application
At
World Skill Center
WEEKLY PROJECT STATUS REPORT
23-June-2023

## Slide 2: PROJECT SUMMARY
OVERALL PROJECT STATUS (R)ed, (A)mber, (G)reen | DELAY
PROJECT NAME | Campus Management Application At World Skill Center(WSC) |  | 
SOUL POC | sharmistha.panda@soulunileaders.com | WSC POC | 
PROJECT START DATE | 03-02-2023 | PROJECT END DATE | 03-02-2024
Red | Likely delay in overall project schedule | Amber | Some Activities are delayed | Green | On track

## Slide 3: TASKS PLANNED/ACCOMPLISHED THIS WEEK
TASKS |  |  | 
Description | Owner | Status | Remarks
SRS Physical Sign Off | WSC | ON GOING | Sign Off done on 12th June for the following: Academy, SOS, SOE and Admission HRMS Training & Placement Infrastructure Management and Maintenance Finance and Accounting update: to be done for Infrastructure project plan & monitoring and Procurement
Integration - Payment Gateway | SOUL - WSC | ON GOING | SOUL team is awaiting for Integration test kit from HDFC bank. update: WSC will share the domain name

## Slide 4: TASKS PLANNED/ACCOMPLISHED THIS WEEK
TASKS |  |  | 
Description | Owner | Status | Remarks
Start of Design phase | SOUL | ON GOING | SOUL team has started working on the design phase. The design phase plan was shared with WSC during weekly review meeting on 22nd June 2023. Revised design phase plan will be shared by SOUL with WSC following internal discussion

## Slide 5: OVERALL PROJECT PROGRESS TIMELINE

## Slide 6: ISSUES
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
A delay in discussing and capturing requirements | High | The revised project plan was discussed on 06-Apr, during weekly Project review meeting update : schedule has been reviwed with WSC stakeholders | WSC | OPEN | WSC stakeholders to acknowledge the delay | 
SOUL highlighted the addition to scope (change request) for the features that were discovered during the requirements study but were not specified in the request for proposal document | High | WSC stakeholders to acknowledge the change request | WSC | OPEN | The change requests will be acknowledged by WSC | SOUL team discussed the change requests on June 9th 2023. Update: SOUL team sent an email to WSC to acknowledge the change reqests and the additional effort required for development

## Slide 7: ISSUES
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
Procurement & Inventory Gap analysis and SRS documents sign off | High | WSC stakeholder to ensure that documents are signed off on time | WSC | OPEN | WSC Stakeholders to coordinate with SME's for timely sign off | SOUL has received digital sign off for ToT. Physical sign off to be done
Examination Gap analysis and SRS documents sign off | High | WSC stakeholder to ensure that documents are signed off on time | WSC | CLOSED | WSC Stakeholders to coordinate with SME's for timely sign off | SOUL has received digital sign off for ToT. Physical sign off done
Infrastructure Gap analysis and SRS documents sign off | High | WSC stakeholder to ensure that documents are signed off on time | WSC | OPEN | WSC Stakeholders to coordinate with SME's for timely sign off | SOUL has received digital sign off Physical sign off to be done

## Slide 8: ISSUES
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
Availability of OCAC server | High | WSC stakeholder to ensure availability of the requested server version | WSC | OPEN | SOUL team has installed the application and database on the same server in the desktop version WSC to acknowledge the additional effort required (CR) to test the desktop version of the application | 

## Slide 9: CHANGE REQUESTS
Description | Module
Entrance Examination Process | Students Management
TrainingOfTrainers(TOT) | Students Management
Recruitment Process | Human Resources Management System
Employee Re-Engagement | Human Resources Management System
Testing effort for application installation in desktop version | OCAC Server
As discussed on 9th June 2023, the change requests Budget and Payroll have been removed from the the list

## Slide 10: UPCOMING WORK
WHAT’S NEXT |  |  | 
Description | Owner | Status | Remarks
Monthly Steering Committee meeting | WSC | OPEN | To be scheduled by WSC
Design phase plan | SOUL | OPEN | The revised plan will be shared by SOUL team during upcoming project review meeting
Role permission template | SOUL | OPEN | SOUL will share the role permission template with WSC

## Slide 11
THANK YOU