## Slide 1
Campus Management Application
At
World Skill Center
WEEKLY PROJECT STATUS REPORT
24-Mar-2023

## Slide 2: PROJECT SUMMARY
OVERALL PROJECT STATUS (R)ed, (A)mber, (G)reen | DELAY
PROJECT NAME | Campus Management Application At World Skill Center(WSC) |  | 
SOUL POC | sharmistha.panda@soulunileaders.com | WSC POC | 
PROJECT START DATE | 03-02-2023 | PROJECT END DATE | 03-02-2024
Red | Likely delay in overall project schedule | Amber | Some Activities are delayed | Green | On track

## Slide 3: TASKS PLANNED/ACCOMPLISHED THIS WEEK
TASKS |  | 
Description | Owner | Status
Start of gap analysis and requirements study for Students Management Module | SOUL and WSC | Started (20th Mar 2023)

## Slide 4: OVERALL PROJECT PROGRESS TIMELINE

## Slide 5: RISKS & ISSUES
ISSUES |  |  |  | 
Description | Issue Priority | Proposed Solution | Issue Owner | Status
A delay in discussing and capturing requirements | High | The project completion date should be reviwed and revised | WSC | Open
RISKS |  |  |  | 
Description | Risk Impact | Mitigation | Risk Owner | Status

## Slide 6: UPCOMING WORK
WHAT’S NEXT |  | 
Description | Owner | Status
Gap analysis and requirement study of Students Management Module | SOUL-WSC | In-Progress

## Slide 7
THANK YOU