## Slide 1
Campus Management Application
At
World Skill Center
WEEKLY PROJECT STATUS REPORT
26-May-2023

## Slide 2: PROJECT SUMMARY
OVERALL PROJECT STATUS (R)ed, (A)mber, (G)reen | DELAY
PROJECT NAME | Campus Management Application At World Skill Center(WSC) |  | 
SOUL POC | sharmistha.panda@soulunileaders.com | WSC POC | 
PROJECT START DATE | 03-02-2023 | PROJECT END DATE | 03-02-2024
Red | Likely delay in overall project schedule | Amber | Some Activities are delayed | Green | On track

## Slide 3: TASKS PLANNED/ACCOMPLISHED THIS WEEK
TASKS |  |  | 
Description | Owner | Status | Remarks
Gap analysis and SRS documents shared with Procurement and Inventory Management WSC SME (Mr. Chandan Kumar) for sign off | WSC | DELAYED | Documents shared on 27th Apr 2023. WSC SME to sign the documents and share it with SOUL by 3rd May 2023 Update (19/05): No response received from WSC SME Update (25.05): SOUL team has requested for digital sign off
Gap analysis and SRS documents shared with HRMS WSC SME’s for sign off | WSC | DELAYED | 02-May-23: SOUL shared the Gap analysis and SRS documents.WSC SME’s to sign off by 5th May 2023 Update (19/05): No response received from WSC SME Update (25.05): SOUL team has requested for digital sign off

## Slide 4: TASKS PLANNED/ACCOMPLISHED THIS WEEK
TASKS |  |  | 
Description | Owner | Status | Remarks
Gap analysis and SRS documents shared with Admission WSC SME’s for sign off | WSC | DELAYED | 3-May-23: SOUL shared the Gap analysis and SRS documents.WSC SME’s to sign off by 5th May 2023 Update (19/05): No response received from WSC SME Update (23/05) : A meeting will be scheduled by WSC stakeholders for physical sign off by all SME’s on May 29 2023.However, SOUL team has requested for digital sign off
Gap analysis and SRS documents of Training with WSC SME’s for sign off | WSC | DELAYED | Documents shared by SOUL on 12th May 2023 Update (19/05): No response received from WSC SME Update (23/05) : A meeting will be scheduled by WSC stakeholders for physical sign off by all SME’s on May 29 2023. However, SOUL team has requested for digital sign off
SRS walkthrough of Tot and Life Skills with WSC Academy SME’s | SOUL and WSC | DONE | Final round (third) of SRS walkthrough done with Academy on May 24 2023.

## Slide 5: TASKS PLANNED/ACCOMPLISHED THIS WEEK
TASKS |  |  | 
Description | Owner | Status | Remarks
Gap analysis and SRS walkthrough of Finance and Accounting module with WSC SME’s | SOUL and WSC | DONE | SRS walkthrough done on May 22 2023
Integration - Payment Gateway | SOUL - WSC | ON GOING | Meeting initiated on 12 May 2023 Update 16/05: Meeting with POS team Update : Follow up email sent by SOUL to provide the POS device
SRS documents walkthrough with Examination | SOUL - WSC | DONE | Final round (second) of SRS walkthrough done on May 26 2023
ToT module SRS clarifications done with SOE SME | SOUL - WSC | DONE | SOUL team clarified the points on May 26 2023

## Slide 6: TASKS PLANNED/ACCOMPLISHED THIS WEEK
TASKS |  |  | 
Description | Owner | Status | Remarks
GAP analysis and SRS documents shared with SOE SME’s for sign off | WSC | DELAYED | 09/05 - 12/05: SOUL shared the SRS documents. Update (17/05): No response received from WSC SME Update (23/05) : A meeting will be scheduled by WSC stakeholders for physical sign off by all SME’s on May 29 2023.However, SOUL team has requested for digital sign off
Gap analysis and SRS documents shared with Placement WSC SME’s for sign off | WSC | DELAYED | 19-May-23: SOUL shared the SRS documents. Update (23/05): No response received from WSC SME Update (23/05) : A meeting will be scheduled by WSC stakeholders for physical sign off by all SME’s on May 29 2023.However, SOUL team has requested for digital sign off
SOUL highlighted the addition to scope (change request) for the features that were discovered during the requirements study but were not specified in the request for proposal document | SOUL - WSC | ON GOING | The point was discussed during project review meeting with WSC stakeholder Update: Change request documents will be shared with WSC stakeholder

## Slide 7: OVERALL PROJECT PROGRESS TIMELINE

## Slide 8: ISSUES
ISSUES |  |  |  |  |  | 
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
A delay in discussing and capturing requirements | High | The revised project plan was discussed on 06-Apr, during weekly Project review meeting update : schedule has been reviwed with WSC stakeholders | WSC | OPEN | WSC stakeholders to acknowledge the delay | 
Faculty workload, Appraisal template discussion with WSC Principal | High | Meeting will be organised by WSC stakeholder | WSC | CLOSED | WSC stakeholders to arrange a meeting with the WSC Principal or senior management to discuss all open (pending) issues | SOUL team presented the process / template to WSC senior management during ERP review meeting on May 23 2023

## Slide 9: ISSUES
ISSUES |  |  |  |  |  | 
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
Procurement & Inventory Gap analysis and SRS documents sign off by WSC SME's | High | WSC stakeholder to ensure that documents are signed off on time | WSC | OPEN | WSC Stakeholders to coordinate with SME's for timely sign off | Update 18/05: SRS sign off shall be discussed during WSC stakeholders meeting Update (23/05) : A meeting will be scheduled by WSC stakeholders for physical sign off by all SME’s on May 29 2023
Required information / template from Admission - Student Grievance & Student Feedback | High | Dependency on WSC stakeholders to ensure information is shared with SOUL team | WSC | CLOSED | WSC stakeholders will coordinate with all the SME’s to participate in weekly review meeting in order to to discuss and resolve open issues | SOUL team presented the process / template to WSC senior management during ERP review meeting on May 23 2023

## Slide 10: ISSUES
ISSUES |  |  |  |  |  | 
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
HRMS Gap analysis and SRS documents sign off by WSC SME's | High | WSC stakeholder to ensure that documents are signed off on time | WSC | OPEN | WSC Stakeholders to coordinate with SME's for timely sign off | Update 18/05: SRS sign off shall be discussed during WSC stakeholders meeting Update (23/05) : A meeting will be scheduled by WSC stakeholders for physical sign off by all SME’s on May 29 2023
Admission (Students support) Gap analysis and SRS documents sign off by WSC SME's | High | WSC stakeholder to ensure that documents are signed off on time | WSC | OPEN | WSC Stakeholders to coordinate with SME's for timely sign off | Update 18/05: SRS sign off shall be discussed during WSC stakeholders meeting Update (23/05) : A meeting will be scheduled by WSC stakeholders for physical sign off by all SME’s on May 29 2023

## Slide 11: ISSUES
ISSUES |  |  |  |  |  | 
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
Gap analysis and SRS documents sign off by WSC SOE | High | WSC stakeholder to ensure that documents are signed off on time | WSC | OPEN | WSC Stakeholders to coordinate with SME's for timely sign off | Update 18/05: SRS sign off shall be discussed during WSC stakeholders meeting Update (23/05) : A meeting will be scheduled by WSC stakeholders for physical sign off by all SME’s on May 29 2023
Training Gap analysis and SRS documents sign off by WSC SME's | High | WSC stakeholder to ensure that documents are signed off on time | WSC | OPEN | WSC Stakeholders to coordinate with SME's for timely sign off | Update 18/05: SRS sign off shall be discussed during WSC stakeholders meeting Update (23/05) : A meeting will be scheduled by WSC stakeholders for physical sign off by all SME’s on May 29 2023

## Slide 12: ISSUES
ISSUES |  |  |  |  |  | 
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
Placement Gap analysis and SRS documents sign off by WSC SME's | High | WSC stakeholder to ensure that documents are signed off on time | WSC | OPEN | WSC Stakeholders to coordinate with SME's for timely sign off | Update 18/05: SRS sign off shall be discussed during WSC stakeholders meeting Update (23/05) : A meeting will be scheduled by WSC stakeholders for physical sign off by all SME’s on May 29 2023
Availability of OCAC server | High | WSC stakeholder to ensure availability of the requested server version | WSC | OPEN | SOUL technical team / higher mgmt and WSC higher mgmt to discuss the issue | SOUL has been provided with desktop version Update 18/05: OCAC poc stated server version with CentOS shall be provided. SOUL will check with technical team for feasibility Update 23/05: SOUL team, WSC stakeholder and OCAC poc will have a meeting to discuss further

## Slide 13: RISKS & ISSUES
RISKS |  |  |  | 
Description | Risk Impact | Mitigation | Risk Owner | Status

## Slide 14: UPCOMING WORK
WHAT’S NEXT |  |  | 
Description | Owner | Status | Remarks
SOUL will share the updated version of Gap analysis and SRS documents with Finance & Accounting SME for sign off | SOUL | Open | SOUL team discussed few points with WSC SME on May 26 2023. The updated documents shall be shared by May 29th
Monthly Steering Committee meeting | SOUL - WSC | Open | Not Started
Availability of OCAC server | SOUL - WSC | Open | Meeting to be scheduled this week for the provision of server version
Required information / template from Admission - Documents verification checklist | SOUL - WSC | Open | SOUL team will send an email to WSC director for assistance
Gap analysis and SRS documents sign off by WSC Academy | SOUL - WSC | Open | SOUL team to share the updated version with SME for their digital sign off

## Slide 15
THANK YOU