## Slide 1
Campus Management Application
At
World Skill Center
WEEKLY PROJECT STATUS REPORT
28-Apr-2023

## Slide 2: PROJECT SUMMARY
OVERALL PROJECT STATUS (R)ed, (A)mber, (G)reen | DELAY
PROJECT NAME | Campus Management Application At World Skill Center(WSC) |  | 
SOUL POC | sharmistha.panda@soulunileaders.com | WSC POC | 
PROJECT START DATE | 03-02-2023 | PROJECT END DATE | 03-02-2024
Red | Likely delay in overall project schedule | Amber | Some Activities are delayed | Green | On track

## Slide 3: TASKS PLANNED/ACCOMPLISHED THIS WEEK
TASKS |  |  | 
Description | Owner | Status | Remarks
Gap analysis and SRS walkthrough of Admission module with WSC SME (Mr. Anil Das) | SOUL and WSC | DONE | The meetings were held on 24th and 26th Apr 2023
Gap analysis and SRS walkthrough of Procurement and Inventory management module with WSC SME (Mr. Samarendra Barik) | SOUL and WSC | DONE | The meeting was held on 25th Apr 2023
Gap analysis and SRS documents shared with Procurement and Inventory Management WSC SME (Mr. Chandan Kumar) for sign off | WSC | In-Progress | Documents shared on 27th Apr 2023. WSC SME to sign the documents and share it with SOUL by 3rd May 2023
Start of gap analysis and requirements study for Infrastructure Management | SOUL and WSC | DONE | Requirements discussions were held on 17th and 25th April
Gap analysis and SRS walkthrough of HRMS module with WSC SME’s (Ms. Shweta Choudhury & Ms. Upali Parida) | SOUL and WSC | DONE | The meetings was held on 28th Apr 2023

## Slide 4: OVERALL PROJECT PROGRESS TIMELINE

## Slide 5: ISSUES
ISSUES |  |  |  |  |  | 
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
A delay in discussing and capturing requirements | High | The revised project plan was discussed on 06-Apr, during weekly Project review meeting update : schedule has been reviwed with WSC stakeholders | WSC | OPEN | WSC stakeholders to acknowledge the delay | 
Unavailibity of WSC SME’s for requirments gathering of Students Management module and Procurement and Inventory | High | WSC leadership team to ensure availability of the SME’s or concerned team | WSC | OPEN | Discussed on 6th Apr, during weekly Project review meeting. WSC stakeholder’s will raise it to the concerned authority | Discussed the point on 27th Apr during weekly project review meeting
Required information / template from Admission / Examination / Procurement WSC SME’s | High | Dependency on WSC stakeholders to ensure information is shared with SOUL team | WSC | OPEN | WSC stakeholders will coordinate with all the SME’s to participate in weekly review meeting in order to to discuss and resolve open issues | 

## Slide 6: ISSUES
ISSUES |  |  |  |  |  | 
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
Faculty workload, Appraisal template to be discussed with WSC Principal | High | Meeting will be organised by WSC stakeholder | WSC | OPEN | WSC stakeholders to arrange a meeting with the WSC Principal or senior management to discuss all open (pending) issues | 20-Apr-23: SOUL team communicated to WSC stakeholder
Delay in capturing the Infrastructure module requirements due to unavailability of WSC SME’s | High | WSC stakeholders to coordinate with the SME’s for their timely availability | WSC | CLOSED | 27-Apr-23: WSC stakeholder communicated with the concerned SME to participate in the requirement meeting | The meeting was supposed to take place on April 19 but was postponed because WSC SME's were involved in an organization-level event.

## Slide 7: RISKS & ISSUES
RISKS |  |  |  | 
Description | Risk Impact | Mitigation | Risk Owner | Status

## Slide 8: UPCOMING WORK
WHAT’S NEXT |  |  | 
Description | Owner | Status | Remarks
Requirements gathering session of Finance and Accounting module | SOUL - WSC | Open | 26-Apr-23: Communication sent by SOUL to WSC SME’s for their availability. 28-Apr-23: Follow up communication done. Awaiting for response
Monthly Steering Committee meeting | SOUL - WSC | Open | Not Started
SRS document walkthrough with SOE, Academy and SOS | SOUL - WSC | Open | 28-Apr-23: SOUL team communicated with the WSC SME's to inquire about their availability
Gap analysis and SRS documents sign off by HRMS SME’s | SOUL - WSC | Open | Not Started
SRS documents walkthrough with Infrastructure SME’s | SOUL - WSC | Open | Not Started

## Slide 9
THANK YOU