## Slide 1
Campus Management Application
At
World Skill Center
WEEKLY PROJECT STATUS REPORT
05-May-2023

## Slide 2: PROJECT SUMMARY
OVERALL PROJECT STATUS (R)ed, (A)mber, (G)reen | DELAY
PROJECT NAME | Campus Management Application At World Skill Center(WSC) |  | 
SOUL POC | sharmistha.panda@soulunileaders.com | WSC POC | 
PROJECT START DATE | 03-02-2023 | PROJECT END DATE | 03-02-2024
Red | Likely delay in overall project schedule | Amber | Some Activities are delayed | Green | On track

## Slide 3: TASKS PLANNED/ACCOMPLISHED THIS WEEK
TASKS |  |  | 
Description | Owner | Status | Remarks
Gap analysis and SRS walkthrough of students management and academics module with SOS | SOUL and WSC | DONE | The meeting was held on 4th May 2023
Gap analysis and SRS walkthrough of Infrastructure and Project management module with WSC SME’s | SOUL and WSC | TO BE DONE | 01-May-23: Communication sent to WSC SME's for their availability to review the SRS (walkthrough) 05-May-23: SOUL has proposed the dates for SRS walkthrough
Gap analysis and SRS documents shared with Procurement and Inventory Management WSC SME (Mr. Chandan Kumar) for sign off | WSC | DELAYED | Documents shared on 27th Apr 2023. WSC SME to sign the documents and share it with SOUL by 3rd May 2023 Update: No response received from WSC SME
Gap analysis and SRS documents shared with HRMS WSC SME’s for sign off | WSC | TO BE DONE | 02-May-23: SOUL shared the Gap analysis and SRS documents.WSC SME’s to sign off by 5th May 2023

## Slide 4: TASKS PLANNED/ACCOMPLISHED THIS WEEK
TASKS |  |  | 
Description | Owner | Status | Remarks
Gap analysis and SRS documents shared with Admission WSC SME’s for sign off | WSC | TO BE DONE | 3-May-23: SOUL shared the Gap analysis and SRS documents.WSC SME’s to sign off by 5th May 2023
Gap analysis and requirements study with accounting WSC SME’s | SOUL and WSC | ON GOING | 02-May-23: Requirements discussion started

## Slide 5: OVERALL PROJECT PROGRESS TIMELINE

## Slide 6: ISSUES
ISSUES |  |  |  |  |  | 
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
A delay in discussing and capturing requirements | High | The revised project plan was discussed on 06-Apr, during weekly Project review meeting update : schedule has been reviwed with WSC stakeholders | WSC | OPEN | WSC stakeholders to acknowledge the delay | 
Unavailibity of WSC SME’s for requirments gathering of Students Management module and Procurement and Inventory | High | WSC leadership team to ensure availability of the SME’s or concerned team | WSC | OPEN | Discussed on 6th Apr, during weekly Project review meeting. WSC stakeholder’s will raise it to the concerned authority | Discussed the point on 27th Apr during weekly project review meeting
Required information / template from Admission / Examination / Procurement WSC SME’s | High | Dependency on WSC stakeholders to ensure information is shared with SOUL team | WSC | OPEN | WSC stakeholders will coordinate with all the SME’s to participate in weekly review meeting in order to to discuss and resolve open issues | 

## Slide 7: ISSUES
ISSUES |  |  |  |  |  | 
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
Faculty workload, Appraisal template to be discussed with WSC Principal | High | Meeting will be organised by WSC stakeholder | WSC | OPEN | WSC stakeholders to arrange a meeting with the WSC Principal or senior management to discuss all open (pending) issues | 20-Apr-23: SOUL team communicated to WSC stakeholder Update: SOUL team discussed with WSC stakeholder on 4th May
The accounting requirements meeting was delayed since WSC SME was late | High | WSC stakeholder to ensure SME’s availability for the scheduled meetings | WSC | OPEN | WSC Stakeholders to coordinate with the SME's for their timely availability | SOUL team raised the issue during weekly project review meeting on 4th May 2023
Procurement & Inventory Gap analysis and SRS documents sign off by WSC SME's | High | WSC stakeholder to ensuree that documents are signed off on time | WSC | OPEN | WSC Stakeholders to coordinate with SME's for timely sign off | Numerous follow up done by SOUL team
Unavailability of WSC SME’s SOE for SRS walkthrough | High | WSC stakeholder to ensure availability of SME’s | WSC | OPEN | WSC Stakeholders to coordinate with SME's for SRS walkthrough participation | Numerous follow up done by SOUL team

## Slide 8: RISKS & ISSUES
RISKS |  |  |  | 
Description | Risk Impact | Mitigation | Risk Owner | Status

## Slide 9: UPCOMING WORK
WHAT’S NEXT |  |  | 
Description | Owner | Status | Remarks
SRS walkthrough with Infrastructure WSC SME’s | SOUL - WSC | Open | SOUL has proposed the dates to WSC SME’s
Monthly Steering Committee meeting | SOUL - WSC | Open | Not Started
SRS document walkthrough with SOE, Academy | SOUL - WSC | Open | SOE: Meeting to be scheduled by WSC stakeholder SOA: Meeting schedule to be checked by SOUL
Gap analysis and SRS documents sign off by Training WSC SME | SOUL - WSC | Open | Not Started
SRS documents walkthrough with Examination | SOUL - WSC | Open | SOUL has proposed the dates
Integration - Payment Gateway | SOUL - WSC | Open | WSC coordinate with third party for discussion

## Slide 10
THANK YOU