## Slide 1
Campus Management Application
At
World Skill Center
WEEKLY PROJECT STATUS REPORT
06-Apr-2023

## Slide 2: PROJECT SUMMARY
OVERALL PROJECT STATUS (R)ed, (A)mber, (G)reen | DELAY
PROJECT NAME | Campus Management Application At World Skill Center(WSC) |  | 
SOUL POC | sharmistha.panda@soulunileaders.com | WSC POC | 
PROJECT START DATE | 03-02-2023 | PROJECT END DATE | 03-02-2024
Red | Likely delay in overall project schedule | Amber | Some Activities are delayed | Green | On track

## Slide 3: TASKS PLANNED/ACCOMPLISHED THIS WEEK
TASKS |  | 
Description | Owner | Status
Start of gap analysis and requirements study for Procurement and Inventory | SOUL and WSC | In Progress (started on 3rd Apr 2023)
Clarification of pending topics of Students Management module | SOUL-WSC | Done

## Slide 4: OVERALL PROJECT PROGRESS TIMELINE

## Slide 5: RISKS & ISSUES
ISSUES |  |  |  |  | 
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Remarks
A delay in discussing and capturing requirements | High |  | WSC | Open | The revised project plan was discussed in today’s weekly Project review meeting
Unavailibity of WSC SME’s for requirments gathering of Students Management module and Procurement and Inventory | High | WSC leadership team to ensure availability of the SME’s or concerned team | WSC | Open | Discussed in today’s weekly Project review meeting. WSC stakeholder’s will raise it to the concerned authority
RISKS |  |  |  | 
Description | Risk Impact | Mitigation | Risk Owner | Status

## Slide 6: UPCOMING WORK
WHAT’S NEXT |  |  | 
Description | Owner | Status | Remarks
Gap analysis and requirement study of Human Resources Management System | SOUL-WSC | Yet to Start | Meeting schedule for the week 10th Apr - 13th Apr has been shared with WSC SME’s
WSC SME’s to have a hands-on experience of Procurement and Inventory module | SOUL-WSC | Yet to Start | A schedule to be proposed by SOUL

## Slide 7
THANK YOU