## Slide 1
Campus Management Application
At
World Skill Center
WEEKLY PROJECT STATUS REPORT
09-June-2023

## Slide 2: PROJECT SUMMARY
OVERALL PROJECT STATUS (R)ed, (A)mber, (G)reen | DELAY
PROJECT NAME | Campus Management Application At World Skill Center(WSC) |  | 
SOUL POC | sharmistha.panda@soulunileaders.com | WSC POC | 
PROJECT START DATE | 03-02-2023 | PROJECT END DATE | 03-02-2024
Red | Likely delay in overall project schedule | Amber | Some Activities are delayed | Green | On track

## Slide 3: TASKS PLANNED/ACCOMPLISHED THIS WEEK
TASKS |  |  | 
Description | Owner | Status | Remarks
Training Gap Analysis and SRS documents digital Sign off | WSC | DONE | 29/05: Digital sign-off received Update: Meeting will be held on June 12 for physical sign off
Placement Gap Analysis and SRS documents digital Sign off | WSC | DONE | 29/05: Digital sign-off received Update: Meeting will be held on June 12 for physical sign off
Academy - Gap Analysis and SRS documents digital Sign off | WSC | DONE | 29/05: Digital sign-off received Update: Meeting will be held on June 12 for physical sign off
School Of Engineering (SOE) - Gap Analysis and SRS documents digital Sign off | WSC | DONE | 31/05: Digital sign-off received for ToT documents Update: Meeting will be held on June 12 for physical sign off
Admission Gap Analysis and SRS documents digital Sign off | WSC | DONE | 31/05: Digital sign-off received Update: Meeting will be held on June 12 for physical sign off

## Slide 4: TASKS PLANNED/ACCOMPLISHED THIS WEEK
TASKS |  |  | 
Description | Owner | Status | Remarks
Procurement and Inventory Management Gap analysis and SRS documents digital Sign off | WSC | DONE | 02/06: Digital sign-off received Update: Meeting will be held on June 12 for physical sign off
HRMS Gap analysis and SRS documents digital Sign off | WSC | DONE | 02/06: Digital sign-off received Update: Meeting will be held on June 12 for physical sign off
School Of Services (SOS) - Gap Analysis and SRS documents digital Sign off | WSC | DONE | 18/05: Digital sign-off received Update: Meeting will be held on June 12 for physical sign off
Examination - Gap Analysis and SRS documents digital Sign off | WSC | DONE | 31/05: Digital sign-off received Update: Meeting will be held on June 12 for physical sign off
Infrastructure - Gap Analysis and SRS documents digital Sign off Project Monitoring Tool Infrastructure Management and Maintenance | WSC | DONE | 03/06: Digital sign-off received Update: Meeting will be held on June 12 for physical sign off

## Slide 5: TASKS PLANNED/ACCOMPLISHED THIS WEEK
TASKS |  |  | 
Description | Owner | Status | Remarks
Finance & Accounting Gap Analysis and SRS documents digital Sign off | WSC | DONE | 03/06: Digital sign-off received Update: Meeting will be held on June 12 for physical sign off
Integration - Payment Gateway | SOUL - WSC | ON GOING | Meeting initiated on 12 May 2023 Update 16/05: Meeting with POS team Update : Follow up email sent by SOUL to provide the POS device 02/06: Follow up email sent by SOUL team Update: Discussed the pending action points with WSC stakeholders on June 9th meeting. WSC authority to share the domain name.
Meeting with WSC stakeholder to discuss current project status and Change Requests | SOUL - WSC | DONE | 
Start of Design phase | SOUL | ON GOING | SOUL team has started working on the design phase

## Slide 6: OVERALL PROJECT PROGRESS TIMELINE

## Slide 7: ISSUES
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
A delay in discussing and capturing requirements | High | The revised project plan was discussed on 06-Apr, during weekly Project review meeting update : schedule has been reviwed with WSC stakeholders | WSC | OPEN | WSC stakeholders to acknowledge the delay | 
SOUL highlighted the addition to scope (change request) for the features that were discovered during the requirements study but were not specified in the request for proposal document | High | WSC stakeholders to acknowledge the change request | WSC | OPEN | SOUL team will send WSC an email with the change requests. The change requests will be acknowledged by WSC | SOUL team discussed the change requests on June 9th 2023. Change request listed in slide 13

## Slide 8: ISSUES
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
Procurement & Inventory Gap analysis and SRS documents sign off | High | WSC stakeholder to ensure that documents are signed off on time | WSC | OPEN | WSC Stakeholders to coordinate with SME's for timely sign off | SOUL has received digital sign off. Physical sign off to be scheduled on June 12th
HRMS Gap analysis and SRS documents sign off | High | WSC stakeholder to ensure that documents are signed off on time | WSC | OPEN | WSC Stakeholders to coordinate with SME's for timely sign off | SOUL has received digital sign off. Physical sign off to be scheduled on June 12th

## Slide 9: ISSUES
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
Admission (Students support) Gap analysis and SRS documents sign off | High | WSC stakeholder to ensure that documents are signed off on time | WSC | OPEN | WSC Stakeholders to coordinate with SME's for timely sign off | SOUL has received digital sign off. Physical sign off to be scheduled on June 12th
SOE Gap analysis and SRS documents sign off | High | WSC stakeholder to ensure that documents are signed off on time | WSC | OPEN | WSC Stakeholders to coordinate with SME's for timely sign off | SOUL has received digital sign off for ToT. Physical sign off to be scheduled on June 12th

## Slide 10: ISSUES
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
Academy Gap analysis and SRS documents sign off | High | WSC stakeholder to ensure that documents are signed off on time | WSC | OPEN | WSC Stakeholders to coordinate with SME's for timely sign off | SOUL has received digital sign off for ToT. Physical sign off to be scheduled on June 12th
SOS Gap analysis and SRS documents sign off | High | WSC stakeholder to ensure that documents are signed off on time | WSC | OPEN | WSC Stakeholders to coordinate with SME's for timely sign off | SOUL has received digital sign off for ToT. Physical sign off to be scheduled on June 12th
SOS Gap analysis and SRS documents sign off | High | WSC stakeholder to ensure that documents are signed off on time | WSC | OPEN | WSC Stakeholders to coordinate with SME's for timely sign off | SOUL has received digital sign off for ToT. Physical sign off to be scheduled on June 12th

## Slide 11: ISSUES
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
Training Gap analysis and SRS documents sign off by WSC SME's | High | WSC stakeholder to ensure that documents are signed off on time | WSC | OPEN | WSC Stakeholders to coordinate with SME's for timely sign off | SOUL has received digital sign off. Physical sign off to be scheduled on June 12th
Placement Gap analysis and SRS documents sign off by WSC SME's | High | WSC stakeholder to ensure that documents are signed off on time | WSC | OPEN | WSC Stakeholders to coordinate with SME's for timely sign off | SOUL has received digital sign off. Physical sign off to be scheduled on June 12th
Finance & Accounting Gap analysis and SRS documents sign off by WSC SME's | High | WSC stakeholder to ensure that documents are signed off on time | WSC | OPEN | WSC Stakeholders to coordinate with SME's for timely sign off | SOUL has received digital sign off. Physical sign off to be scheduled on June 12th

## Slide 12: ISSUES
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
Availability of OCAC server | High | WSC stakeholder to ensure availability of the requested server version | WSC | OPEN | SOUL team will install the application and database on the same server and test the desktop version of the application | 02/06: Since OSDC is unable to provide the required server version, SOUL team has suggested alternate options to WSC Update: The issue was discussed today during meeting with WSC

## Slide 13: CHANGE REQUESTS
Description | Module
Entrance Examination Process | Students Management
TrainingOfTrainers(TOT) | Students Management
Recruitment Process | Human Resources Management System
Employee Re-Engagement | Human Resources Management System
Budget | Finance & Accounting
Payroll | Finance & Accounting
Testing effort for application installation in desktop version | OCAC Server

## Slide 14: UPCOMING WORK
WHAT’S NEXT |  |  | 
Description | Owner | Status | Remarks
Physical sign off | WSC | OPEN | To be conducted on June 12th
Monthly Steering Committee meeting | SOUL - WSC | OPEN | To be conducted on June 13th
Design and Development phase plan | SOUL | OPEN | The plan will be shared by SOUL team during upcoming project review meeting

## Slide 15
THANK YOU