## Slide 1
Campus Management Application
At
World Skill Center
WEEKLY PROJECT STATUS REPORT
14-Apr-2023

## Slide 2: PROJECT SUMMARY
OVERALL PROJECT STATUS (R)ed, (A)mber, (G)reen | DELAY
PROJECT NAME | Campus Management Application At World Skill Center(WSC) |  | 
SOUL POC | sharmistha.panda@soulunileaders.com | WSC POC | 
PROJECT START DATE | 03-02-2023 | PROJECT END DATE | 03-02-2024
Red | Likely delay in overall project schedule | Amber | Some Activities are delayed | Green | On track

## Slide 3: TASKS PLANNED/ACCOMPLISHED THIS WEEK
TASKS |  |  | 
Description | Owner | Status | Remarks
Start of gap analysis and requirements study for Procurement and Inventory | SOUL and WSC | Done | 
Start of gap analysis and requirements study for Human Resource Management System | SOUL and WSC | In-Progress | Identifying questions / clarifications to be discussed further with WSC SME’s
Assistance to Procurement and Inventory WSC SME’s for ERP application hands-on | SOUL-WSC | Done | Session conducted on 03-Apr-2023

## Slide 4: OVERALL PROJECT PROGRESS TIMELINE

## Slide 5: ISSUES
ISSUES |  |  |  |  |  | 
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
A delay in discussing and capturing requirements | High | The revised project plan was discussed on 06-Apr, during weekly Project review meeting update : schedule has been reviwed with WSC stakeholders | WSC | Open | WSC stakeholders to acknowledge the delay | 
Unavailibity of WSC SME’s for requirments gathering of Students Management module and Procurement and Inventory | High | WSC leadership team to ensure availability of the SME’s or concerned team | WSC | Open | Discussed on 6th Apr, during weekly Project review meeting. WSC stakeholder’s will raise it to the concerned authority | 
Required information / template from Admission / Examination / Procurement WSC SME’s | High | Dependency on WSC leadership team to ensure information is shared with SOUL team | WSC | Open | WSC leadership team / stakeholder’s to help SOUL team gathering the information | Communication and follow up email sent by SOUL team

## Slide 6: RISKS & ISSUES
RISKS |  |  |  | 
Description | Risk Impact | Mitigation | Risk Owner | Status

## Slide 7: UPCOMING WORK
WHAT’S NEXT |  |  | 
Description | Owner | Status | Remarks
Requirements gathering session of Infrastructure module | SOUL - WSC | Open | Communication sent to WSC SME’s for their availability. Awaiting response with thier availability to proceed wit the next steps
Monthly Steering Committee meeting | SOUL - WSC | Open | Not Started
Students Management and Academics module SRS document walkthrough | SOUL - WSC | Open | Not Started

## Slide 8
THANK YOU