## Slide 1
Campus Management Application
At
World Skill Center
WEEKLY PROJECT STATUS REPORT
14-July-2023

## Slide 2: PROJECT SUMMARY
OVERALL PROJECT STATUS (R)ed, (A)mber, (G)reen | DELAY
PROJECT NAME | Campus Management Application At World Skill Center(WSC) |  | 
SOUL POC | sharmistha.panda@soulunileaders.com | WSC POC | 
PROJECT START DATE | 03-02-2023 | PROJECT END DATE | 03-02-2024
Red | Likely delay in overall project schedule | Amber | Some Activities are delayed | Green | On track

## Slide 3: TASKS PLANNED/ACCOMPLISHED THIS WEEK
TASKS |  |  | 
Description | Owner | Status | Remarks
Integration - Payment Gateway | SOUL - WSC | ON GOING | 12-Jul-2023: Received the test kit from HDFC team. SOUL team has initiated the implementation
Start of Design phase | SOUL | ON GOING | Training & Program design document has been shared with WSC IT team for their review. The document shall be shared with module owner post review and feedback
Role permission template | SOUL | ON GOING | Update: SOUL team has shared the revised version of Roles and Permission templates based on the feedback received 14-Jul-23: WSC will fill out role and permission templates and share them with SOUL by next week

## Slide 4: TASKS PLANNED/ACCOMPLISHED THIS WEEK
TASKS |  |  | 
Description | Owner | Status | Remarks
Design Document Template | SOUL | CLOSED | SOUL team shared the document template with WSC for review and feedback Update: SOUL team has requested WSC to share the sample HLD & LLD sample documents for clarifications 14-Jul-23: SOUL team prepared the Training and Program document with reference to the template shared by WSC (wherever applicable)
Master data template for SLCM and HRMS | SOUL | ON GOING | SOUL team has shared the data template 14-jul-23: WSC will go through the master data template (SLCM & HRMS) shared by SOUL for further clarification

## Slide 5: OVERALL PROJECT PROGRESS TIMELINE

## Slide 6: ISSUES
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
A delay in discussing and capturing requirements | High | The revised project plan was discussed on 06-Apr, during weekly Project review meeting update : schedule has been reviwed with WSC stakeholders | WSC | OPEN | WSC stakeholders to acknowledge the delay | 
SOUL highlighted the addition to scope (change request) for the features that were discovered during the requirements study but were not specified in the request for proposal document | High | WSC stakeholders to acknowledge the change request | WSC | OPEN | The change requests will be acknowledged by WSC | Update: SOUL team sent an email to WSC to acknowledge the change reqests and the additional effort required for development. The change requests have been listed in Slide 9

## Slide 7: ISSUES
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
Availability of OCAC server | High | WSC stakeholder to ensure availability of the requested server version | WSC | OPEN | SOUL team has installed the application and database on the same server in the desktop version WSC to acknowledge the additional effort required (CR) to test the desktop version of the application | 

## Slide 8: CHANGE REQUESTS
Description | Module
Entrance Examination Process | Students Management
TrainingOfTrainers(TOT) | Students Management
Recruitment Process | Human Resources Management System
Employee Re-Engagement | Human Resources Management System
Testing effort for application installation in desktop version | OCAC Server
As discussed on 9th June 2023, the change requests Budget and Payroll have been removed from the the list

## Slide 9: UPCOMING WORK
WHAT’S NEXT |  |  | 
Description | Owner | Status | Remarks
Monthly Steering Committee meeting | WSC | OPEN | WSC will coordinate with higher management / relevant stakeholders on their availability for the Steering Committee Meeting
Continuation of the design phase - Design documentation | SOUL | OPEN | 

## Slide 10
THANK YOU