## Slide 1
Campus Management Application
At
World Skill Center
WEEKLY PROJECT STATUS REPORT
30-June-2023

## Slide 2: PROJECT SUMMARY
OVERALL PROJECT STATUS (R)ed, (A)mber, (G)reen | DELAY
PROJECT NAME | Campus Management Application At World Skill Center(WSC) |  | 
SOUL POC | sharmistha.panda@soulunileaders.com | WSC POC | 
PROJECT START DATE | 03-02-2023 | PROJECT END DATE | 03-02-2024
Red | Likely delay in overall project schedule | Amber | Some Activities are delayed | Green | On track

## Slide 3: TASKS PLANNED/ACCOMPLISHED THIS WEEK
TASKS |  |  | 
Description | Owner | Status | Remarks
SRS Physical Sign Off | WSC | ON GOING | Sign Off done on 12th June for the following: Academy, SOS, SOE and Admission HRMS Training & Placement Infrastructure Management and Maintenance Finance and Accounting update: to be done for Infrastructure project plan & monitoring and Procurement
Integration - Payment Gateway | SOUL - WSC | ON GOING | SOUL team is awaiting for Integration test kit from HDFC bank. update: WSC shared the sub domain name on June 28 2023. SOUL team has reminded HDFC team to provide the testing kit

## Slide 4: TASKS PLANNED/ACCOMPLISHED THIS WEEK
TASKS |  |  | 
Description | Owner | Status | Remarks
Start of Design phase | SOUL | ON GOING | SOUL team is working on the design documentation
Design Document Template | SOUL | CLOSED | SOUL team shared the document template with WSC for review and feedback
Role permission template | SOUL | CLOSED | SOUL team shared the roles & permission template with WSC
Master Sign Off Page | SOUL | CLOSED | SOUL shared prepared and shared the master sign off page with WSC for review and feedback. Feedback received by WSC

## Slide 5: OVERALL PROJECT PROGRESS TIMELINE

## Slide 6: ISSUES
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
A delay in discussing and capturing requirements | High | The revised project plan was discussed on 06-Apr, during weekly Project review meeting update : schedule has been reviwed with WSC stakeholders | WSC | OPEN | WSC stakeholders to acknowledge the delay | 
SOUL highlighted the addition to scope (change request) for the features that were discovered during the requirements study but were not specified in the request for proposal document | High | WSC stakeholders to acknowledge the change request | WSC | OPEN | The change requests will be acknowledged by WSC | Update: SOUL team sent an email to WSC to acknowledge the change reqests and the additional effort required for development. The change requests have been listed in Slide 9

## Slide 7: ISSUES
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
Procurement & Inventory Gap analysis and SRS documents sign off | High | WSC stakeholder to ensure that documents are signed off on time | WSC | CLOSED | WSC Stakeholders to coordinate with SME's for timely sign off | SOUL has received digital sign off for ToT. Physical sign off to be done Update: Physical sign off done
Infrastructure Gap analysis and SRS documents sign off | High | WSC stakeholder to ensure that documents are signed off on time | WSC | CLOSED | WSC Stakeholders to coordinate with SME's for timely sign off | SOUL has received digital sign off Physical sign off to be done Update: Physical sign off done

## Slide 8: ISSUES
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
Availability of OCAC server | High | WSC stakeholder to ensure availability of the requested server version | WSC | OPEN | SOUL team has installed the application and database on the same server in the desktop version WSC to acknowledge the additional effort required (CR) to test the desktop version of the application | 

## Slide 9: CHANGE REQUESTS
Description | Module
Entrance Examination Process | Students Management
TrainingOfTrainers(TOT) | Students Management
Recruitment Process | Human Resources Management System
Employee Re-Engagement | Human Resources Management System
Testing effort for application installation in desktop version | OCAC Server
As discussed on 9th June 2023, the change requests Budget and Payroll have been removed from the the list

## Slide 10: UPCOMING WORK
WHAT’S NEXT |  |  | 
Description | Owner | Status | Remarks
Monthly Steering Committee meeting | WSC | OPEN | To be scheduled by WSC
Continuation of the design phase - Design documentation | SOUL | OPEN | 
Master data template for SLCM and HRMS | SOUL | OPEN | 

## Slide 11
THANK YOU