## Slide 1
Campus Management Application
At
World Skill Center
WEEKLY PROJECT STATUS REPORT
31-Mar-2023

## Slide 2: PROJECT SUMMARY
OVERALL PROJECT STATUS (R)ed, (A)mber, (G)reen | DELAY
PROJECT NAME | Campus Management Application At World Skill Center(WSC) |  | 
SOUL POC | sharmistha.panda@soulunileaders.com | WSC POC | 
PROJECT START DATE | 03-02-2023 | PROJECT END DATE | 03-02-2024
Red | Likely delay in overall project schedule | Amber | Some Activities are delayed | Green | On track

## Slide 3: TASKS PLANNED/ACCOMPLISHED THIS WEEK
TASKS |  | 
Description | Owner | Status
Start of gap analysis and requirements study for Students Management Module | SOUL and WSC | In Progress (20th Mar 2023)

## Slide 4: OVERALL PROJECT PROGRESS TIMELINE

## Slide 5: RISKS & ISSUES
ISSUES |  |  |  | 
Description | Issue Priority | Proposed Solution | Issue Owner | Status
A delay in discussing and capturing requirements | High | The project completion date should be reviewed and revised | WSC | Open
Unavailibity of WSC SME’s for requirments gathering of Students Management module | High | WSC leadership team to ensure availability of the SME’s or concerned team | WSC | Open
RISKS |  |  |  | 
Description | Risk Impact | Mitigation | Risk Owner | Status

## Slide 6: UPCOMING WORK
WHAT’S NEXT |  |  | 
Description | Owner | Status | Remarks
Gap analysis and requirement study of Procurement and Inventory Management | SOUL-WSC | Not Yet Started | Meeting schedule for the week 03rd Apr - 05th Apr has been shared with WSC SME
Clarification of pending topics of Students Management module | SOUL-WSC | Pending | 

## Slide 7
THANK YOU