## Employee Profile Updation Req
Phase | New Screen | Child Table | Workflow | No of hrs per person(new) | Effort | Effort in days
Requirement Analysis |  |  |  |  | 10% | 8
Design |  |  |  |  | 10% | 8
Development | Employee Profile Updation Request | 4 | Yes | 32 | 40% | 32
Testing |  |  |  |  | 15% | 12
UAT Support |  |  |  |  | 10% | 8
Deployment |  |  |  |  | 5% | 4
Project Management |  |  |  |  | 10% | 8
80
0.5
[6 empty] | 1 | Price in lakhs

## Recruitment Process
Phase | New Screen |  | Child Table | Workflow | No of hrs per person(new) | Effort | Effort in days
Requirement Analysis | [5 empty] | 10% | 36.75
Design | [5 empty] | 10% | 36.75
Development | Recruitment Exam Declaration | N | 1 |  | 40
| Recruitment Exam Admit Card Generation Tool | N | 1 |  | 32
| Recruitment Exam Admit Card Generation | N |  |  | 16
| Recruitment Exam Result Declaration Tool | N | 1 |  | 32
| Recruitment Exam Result Declaration | N | 0 |  | 16
| Job Applicant | M | 1 |  | 3
| Job Opening | M | 1 |  | 8
[5 empty] | 147 | 40% | 147
Testing | [5 empty] | 15% | 55.125
UAT Support | [5 empty] | 10% | 36.75
Deployment | [5 empty] | 5% | 18.375
Project Management | [5 empty] | 10% | 36.75
367.5
2.2969
4.5938

## Employee Re-engagement
Phase | New Screen |  | Child Table | Workflow | No of hrs per person(new) | Effort | Effort in days
Requirement Analysis | [5 empty] | 10% | 24
Design | [5 empty] | 10% | 24
Development | Employee Re-engagement | N |  | Yes | 32
| Notifications | N |  |  | 32
| Job Offer | M |  |  | 32
[5 empty] | 96 | 40% | 96
Testing | [5 empty] | 15% | 36
UAT Support | [5 empty] | 10% | 24
Deployment | [5 empty] | 5% | 12
Project Management | [5 empty] | 10% | 24
[6 empty] | 100% | 240
1.5
[7 empty] | 3 | Price in lakhs