## Slide 1
Campus Management Application
At
World Skill Center
WEEKLY PROJECT STATUS REPORT
04-Nov-2023

## Slide 2: PROJECT SUMMARY
OVERALL PROJECT STATUS (R)ed, (A)mber, (G)reen | DELAY
PROJECT NAME | Campus Management Application At World Skill Center(WSC) |  | 
SOUL POC | sharmistha.panda@soulunileaders.com | WSC POC | bishnupriya.panda@worldskillcenter.org
PROJECT START DATE | 03-02-2023 | PROJECT END DATE | 03-02-2024
Red | Likely delay in overall project schedule | Amber | Some Activities are delayed | Green | On track

## Slide 3: PRIORITY1 RELEASE HIGHLIGHTS
SLCM release was scheduled in two phases, priority 1 and priority 2
Priority 1 release date was scheduled on 31 Aug 2023
The Student Applicant feature, which was part of priority 2, was requested
to be Go Live on September 26, 2023
The spreadsheet Priority1ImplementationChanges.xlsx lists all the 25 changes
The ppt SLCM & HRMS Priority1 Release.pptx lists all the release features
Release Planned | 1
Release Requested | 2
Priority1 Release Effort | ~ 536
Changes Requested during Implementation | 25
Change Implementation Effort (hrs) | ~ 327
Chart: Change Implementation Effort
| Customization | Data Upload | New Development
 | 10 | 3 | 12

## Slide 4: MODULE MILESTONE STATUS
** Procurement & Infrastructure - Training to the module owners could not be done due to their unavailability (procurement - second session)
PRIORITY 2 | Requirement | Design | Development | System Testing | Deployment | Training
SLCM | Complete | Complete | Complete | Complete | Not Started | Not Started
TnP | Complete | Complete | Complete | Complete | Not Started | Not Started
Procurement | Complete | Complete | Complete | Complete | Not Started | Partial**
HRMS | Complete | Complete | Complete | In Progress | Not Started | Not Started
Infrastructure | Complete | Complete | Complete | Complete | Not Started | Delay**
Finance | Complete | Complete | Complete | In Progress | Not Started | Not Started
PRIORITY 1 | Requirement | Design | Development | System Testing | Deployment | Training
SLCM | Complete | Complete | Complete | Complete | Complete | Complete
HRMS | Complete | Complete | Complete | Complete | Complete | Complete

## Slide 5: TASKS PLANNED/ACCOMPLISHED THIS WEEK
Sl No. | Description | Owner | Status | Remarks
1 | Student Admission / Enrollment / Applicant | SOUL - WSC | On-Going | Course enrollment of the students (SOE / SOS) - started on 4th October 2023 - Done
 |  |  |  | Online Payment by the students (SOE / SOS) - started on 4th October 2023 - Done
 |  |  |  | Support to WSC trainers, Accounts team, IT Team to handle students query, issues (defect fix) , change requests- 26 September ~ 31 October 2023 - Done
 |  |  |  | Developed student admission reports as requested by WSC team on 25 Oct 2023 - Done
 |  |  |  | SOUL team disabled online access of all students as requested by WSC - Done
2 | Development | SOUL | On-Going | Development activities of SLCM priority2 continuing - Done
3 | System Integration Testing | SOUL | On-Going | Testing activities continuing - On Going
4 | User / Training Manual | SOUL | On-Going | SOUL team working on the user manual documentation - Done

## Slide 6: OVERALL PROJECT PROGRESS TIMELINE
Milestone 1 - Gap Analysis Document and SRS documents signed off on 12 June, 2023
Milestone 2 - Design Document digital sign off done

## Slide 7: ISSUES
Sl No. | Description | Issue Date | Issue Owner | Status | Action Items
1 | A delay in discussing and capturing requirements | 19-Jan-23 | WSC | OPEN | WSC stakeholders to acknowledge the delay
2 | Availability of OCAC server | 11-May-23 | WSC | OPEN | WSC to acknowledge the additional effort required (CR) to test the desktop version of the application
3 | SOUL highlighted the addition to scope (change request) for the features that were discovered during the requirements study but were not specified in the request for proposal document | 09-June-23 | WSC | OPEN | WSC stakeholders to acknowledge the change request
4 | Demonstration : Procurement and Inventory management | 08-Sep-23 | SOUL - WSC | DELAY | WSC IT team should liaise with stakeholders to ensure their availability
5 | Pending Action Items from WSC | 19-Sep-23 | WSC | OPEN | WSC IT teams should assist SOUL to close the pending open points
6 | Money Receipt Generation | 30-Oct-23 | SOUL - WSC | OPEN | SOUL team explained the temporary solution to finance team member. For further analysis and permanent fix, SOUL team has requested OCAC to share the image of the server in OVA format. To proceed further on this, WSC needs to sign a backup restore form and share with OCAC.
7 | Integration - Payment Gateway (Axis) | 01-Nov-23 | SOUL - WSC | OPEN | SOUL team has requested for sample python code to call Get Status API

## Slide 8: CHANGE REQUESTS (Requested during Requirement Gathering Stage)
Sl No. | Description | Module | Effort (hr)
1 | Counselling and Entrance Examination Process | Students Management | ~ 475
2 | Training Of Trainers(TOT) | Students Management | ~ 900
3 | Recruitment Process | Human Resources Management System | ~ 368
4 | Employee Re-Engagement | Human Resources Management System | ~ 240
5 | Testing effort for application installation in desktop version | OCAC Server | ~ 160
As discussed on 9th June 2023, the change requests Budget and Payroll have been removed from the the list

## Slide 9: UPCOMING WORK
Sl No. | Description | Owner | Status | Remarks
1 | System Integration Testing | SOUL | On-Going | System testing will be continued for HRMS (Payroll) and Finance & Accounting
2 | Application demonstration to module owners | SOUL - WSC | OPEN | WSC IT team to prepare the training timetable and share with SOUL team by 4th November, 2023
3 | SOUL team will propose the payment refund process | SOUL | OPEN | 
4 | SOUL team will analyze the money receipt generation issue after receiving the OVA from OCAC | SOUL - WSC | OPEN | 

## Slide 10
THANK YOU