## Slide 1
Campus Management Application
At
World Skill Center
WEEKLY PROJECT STATUS REPORT
10-Nov-2023

## Slide 2: PROJECT SUMMARY
OVERALL PROJECT STATUS (R)ed, (A)mber, (G)reen | DELAY
PROJECT NAME | Campus Management Application At World Skill Center(WSC) |  | 
SOUL POC | sharmistha.panda@soulunileaders.com | WSC POC | bishnupriya.panda@worldskillcenter.org
PROJECT START DATE | 03-02-2023 | PROJECT END DATE | 03-02-2024
Red | Likely delay in overall project schedule | Amber | Some Activities are delayed | Green | On track

## Slide 3: PRIORITY1 RELEASE HIGHLIGHTS
SLCM release was scheduled in two phases, priority 1 and priority 2
Priority 1 release date was scheduled on 31 Aug 2023
The Student Applicant feature, which was part of priority 2, was requested
to be Go Live on September 26, 2023
The spreadsheet Priority1ImplementationChanges.xlsx lists all the 25 changes
The ppt SLCM & HRMS Priority1 Release.pptx lists all the release features
Release Planned | 1
Release Requested | 2
Priority1 Release Effort | ~ 536
Changes Requested during Implementation | 25
Change Implementation Effort (hrs) | ~ 327
Chart: Change Implementation Effort
| Customization | Data Upload | New Development
 | 10 | 3 | 12

## Slide 4: MODULE MILESTONE STATUS
*Infrastructure - Maintenance and Management training done on 9 November, 2023. Project plan and monitoring to be done.
PRIORITY 2 | Requirement | Design | Development | System Testing | Deployment | Training
SLCM | Complete | Complete | Complete | Complete | Not Started | Not Started
TnP | Complete | Complete | Complete | Complete | Not Started | Complete
Procurement | Complete | Complete | Complete | Complete | Not Started | Complete
HRMS | Complete | Complete | Complete | Complete | Not Started | Complete
Infrastructure | Complete | Complete | Complete | Complete | Not Started | *Partial
Finance | Complete | Complete | Complete | Complete | Not Started | Not Started
PRIORITY 1 | Requirement | Design | Development | System Testing | Deployment | Training
SLCM | Complete | Complete | Complete | Complete | Complete | Complete
HRMS | Complete | Complete | Complete | Complete | Complete | Complete

## Slide 5: TASKS PLANNED/ACCOMPLISHED THIS WEEK
Sl No. | Description | Owner | Status | Remarks
1 | Student Admission / Enrollment / Applicant | SOUL - WSC | Done | Student admission process completed
3 | System Integration Testing | SOUL | Done | Testing activities completed
4 | User / Training Manual | SOUL | Done | SOUL team completed user manual documentation
5 | Training to WSC module owners | SOUL - WSC | Done | SOUL team demonstrated the following features : Training & Placement Procurement & Inventory HRMS Infrastructure Maintenance and Management

## Slide 6: OVERALL PROJECT PROGRESS TIMELINE
Milestone 1 - Gap Analysis Document and SRS documents signed off on 12 June, 2023
Milestone 2 - Design Document digital sign off done

## Slide 7: ISSUES
Sl No. | Description | Issue Date | Issue Owner | Status | Action Items
1 | A delay in discussing and capturing requirements | 19-Jan-23 | WSC | OPEN | WSC stakeholders to acknowledge the delay
2 | Availability of OCAC server | 11-May-23 | WSC | OPEN | WSC to acknowledge the additional effort required (CR) to test the desktop version of the application
3 | SOUL highlighted the addition to scope (change request) for the features that were discovered during the requirements study but were not specified in the request for proposal document | 09-June-23 | WSC | OPEN | WSC stakeholders to acknowledge the change request
4 | Demonstration : Procurement and Inventory management | 08-Sep-23 | SOUL - WSC | DONE | Demonstration done on 6 November, 2023
5 | Pending Action Items from WSC | 19-Sep-23 | WSC | OPEN | WSC IT teams should assist SOUL to close the pending open points
6 | Money Receipt Generation | 30-Oct-23 | SOUL - WSC | OPEN | Received the server image in OVA format from OCAC. SOUL team trying to setup the environment
7 | Integration - Payment Gateway (Axis) | 01-Nov-23 | SOUL - WSC | DONE | SOUL team has requested for sample python code to call Get Status API update: SOUL team completed development and has sent for UAT sign off

## Slide 8: CHANGE REQUESTS (Requested during Requirement Gathering Stage)
Sl No. | Description | Module | Effort (hr)
1 | Counselling and Entrance Examination Process | Students Management | ~ 475
2 | Training Of Trainers(TOT) | Students Management | ~ 900
3 | Recruitment Process | Human Resources Management System | ~ 368
4 | Employee Re-Engagement | Human Resources Management System | ~ 240
5 | Testing effort for application installation in desktop version | OCAC Server | ~ 160
As discussed on 9th June 2023, the change requests Budget and Payroll have been removed from the the list

## Slide 9: UPCOMING WORK
Sl No. | Description | Owner | Status | Remarks
1 | Application demonstration to module owners | SOUL - WSC | OPEN | 
2 | SOUL team will propose the payment refund process | SOUL | OPEN | 
3 | SOUL team will incorporate the feedback received during Procurement and Training and Placement training | SOUL | OPEN | 

## Slide 10
THANK YOU