## Slide 1
Campus Management Application
At
World Skill Center
WEEKLY PROJECT STATUS REPORT
20-Oct-2023

## Slide 2: PROJECT SUMMARY
OVERALL PROJECT STATUS (R)ed, (A)mber, (G)reen | DELAY
PROJECT NAME | Campus Management Application At World Skill Center(WSC) |  | 
SOUL POC | sharmistha.panda@soulunileaders.com | WSC POC | bishnupriya.panda@worldskillcenter.org
PROJECT START DATE | 03-02-2023 | PROJECT END DATE | 03-02-2024
Red | Likely delay in overall project schedule | Amber | Some Activities are delayed | Green | On track

## Slide 3: PRIORITY1 RELEASE HIGHLIGHTS
SLCM release was scheduled in two phases, priority 1 and priority 2
Priority 1 release date was scheduled on 31 Aug 2023
The Student Applicant feature, which was part of priority 2, was requested to be Go Live on September 26, 2023
The spreadsheet Priority1ImplementationChanges.xlsx lists all the 23 changes
The ppt SLCM & HRMS Priority1 Release.pptx lists all the release features
Release Planned | 1
Release Requested | 2
Priority1 Release Effort | ~ 536
Changes Requested during Implementation | 23
Change Implementation Effort (hrs) | ~ 302
Chart: Change Implementation Effort
| Customization | Data Upload | New Development
 | 10 | 2 | 11

## Slide 4: MODULE MILESTONE STATUS
*Procurement - WSC design document sign off pending
** Procurement & Infrastructure - Training to the module owners could not be done due to their unavailability (procurement - second session)
PRIORITY 2 | Requirement | Design | Development | System Testing | Deployment | Training
SLCM | Complete | Complete | In Progress | In Progress | Not Started | Not Started
TnP | Complete | Complete | Complete | In Progress | Not Started | Not Started
Procurement | Complete | Complete* | Complete | In Progress | Not Started | Partial**
HRMS | Complete | Complete | Complete | In Progress | Not Started | Not Started
Infrastructure | Complete | Complete | Complete | In Progress | Not Started | Delay**
Finance | Complete | Complete | Complete | In Progress | Not Started | Not Started
PRIORITY 1 | Requirement | Design | Development | System Testing | Deployment | Training
SLCM | Complete | Complete | Complete | Complete | Complete | Complete
HRMS | Complete | Complete | Complete | Complete | Complete | Complete

## Slide 5: TASKS PLANNED/ACCOMPLISHED THIS WEEK
Sl No. | Description | Owner | Status | Remarks
1 | Student Admission / Enrollment / Applicant | SOUL - WSC | On-Going | Student admission process for SOE completed on 13 Oct 2023
 |  |  |  | Training to the WSC trainers on student course enrollment for SOS department by SOUL team ~ 4th October 2023 - Done
 |  |  |  | Course enrollment of the students (SOS) - started on 4th October 2023 - On-Going
 |  |  |  | Online Payment by the students (SOS) - started on 4th October 2023 - On-Going
 |  |  |  | Support to WSC trainers, Accounts team, IT Team to handle students query, issues (defect fix) , change requests- 26 September ~ 13 October 2023 - On-Going
 |  |  |  | SOUL team provided training to WSC trainers / IT team for SPOT Admission of students at WSC - 12 October 2023 - Done
2 | Development | SOUL | On-Going | Development activities of SLCM priority2 continuing
3 | System Integration Testing | SOUL | On-Going | Testing activities continuing
4 | User / Training Manual | SOUL | On-Going | SOUL team working on the user manual documentation. The following modules have been completed : Procurement, HRMS, Counselling, Infrastructure

## Slide 6: OVERALL PROJECT PROGRESS TIMELINE
Milestone 1 - Gap Analysis Document and SRS documents signed off on 12 June, 2023
Milestone 2 - Design Document digital sign off pending from WSC stakeholders

## Slide 7: ISSUES
Sl No. | Description | Issue Date | Issue Owner | Status | Action Items
1 | A delay in discussing and capturing requirements | 19-Jan-23 | WSC | OPEN | WSC stakeholders to acknowledge the delay
2 | Availability of OCAC server | 11-May-23 | WSC | OPEN | WSC to acknowledge the additional effort required (CR) to test the desktop version of the application
3 | SOUL highlighted the addition to scope (change request) for the features that were discovered during the requirements study but were not specified in the request for proposal document | 09-June-23 | WSC | OPEN | WSC stakeholders to acknowledge the change request
4 | Demonstration : Procurement and Inventory management | 08-Sep-23 | SOUL - WSC | DELAY | WSC IT team should liaise with stakeholders to ensure their availability
5 | Pending Action Items from WSC | 19-Sep-23 | WSC | OPEN | WSC IT teams should assist SOUL to close the pending the open points
6 | Integration - Payment Gateway (Axis) | 03-Oct-23 | SOUL - WSC | OPEN | There was an authentication issue from Axis so, they provided SOUL team API key and merchant ID which is being implemented now
7 | Integration - Payment Gateway (HDFC) | 13-Oct-23 | SOUL | DONE | There was transactional status difference between CCAvenue and ERP. SOUL team updated the actual status manually

## Slide 8: CHANGE REQUESTS (Requested during Requirement Gathering Stage)
Sl No. | Description | Module | Effort (hr)
1 | Counselling and Entrance Examination Process | Students Management | ~ 475
2 | Training Of Trainers(TOT) | Students Management | ~ 900
3 | Recruitment Process | Human Resources Management System | ~ 368
4 | Employee Re-Engagement | Human Resources Management System | ~ 240
5 | Testing effort for application installation in desktop version | OCAC Server | ~ 16
As discussed on 9th June 2023, the change requests Budget and Payroll have been removed from the the list

## Slide 9: UPCOMING WORK
Sl No. | Description | Owner | Status | Remarks
1 | User Manual Documentation | SOUL | On-Going | SOUL team will continue working on the documentation
2 | Development | SOUL | On-Going | SLCM Priority 2 will be completed
3 | System Integration Testing | SOUL | On-Going | System testing will be continued

## Slide 10
THANK YOU