## Slide 1
Campus Management Application
At
World Skill Center
WEEKLY PROJECT STATUS REPORT
08-Dec-2023

## Slide 2: PROJECT SUMMARY
OVERALL PROJECT STATUS (R)ed, (A)mber, (G)reen | DELAY
PROJECT NAME | Campus Management Application At World Skill Center(WSC) |  | 
SOUL POC | sharmistha.panda@soulunileaders.com | WSC POC | bishnupriya.panda@worldskillcenter.org
PROJECT START DATE | 03-02-2023 | PROJECT END DATE | 03-02-2024
Red | Likely delay in overall project schedule | Amber | Some Activities are delayed | Green | On track

## Slide 3: PRIORITY1 RELEASE HIGHLIGHTS
SLCM release was scheduled in two phases, priority 1 and priority 2
Priority 1 release date was scheduled on 31 Aug 2023
The Student Applicant feature, which was part of priority 2, was requested to be Go Live on September 26, 2023
The spreadsheet Priority1ImplementationChanges.xlsx lists all the 25 changes
The ppt SLCM & HRMS Priority1 Release.pptx lists all the release features
Release Planned | 1
Release Requested | 2
Priority1 Release Effort | ~ 536
Changes Requested during Implementation | 26
Change Implementation Effort (hrs) | ~ 329
Chart: Change Implementation Effort
| Customization | Data Upload | New Development
 | 10 | 4 | 12

## Slide 4: APPLICATION TRAINING CHANGES
Procurement session-2 and Training & Placement trainings were conducted on 6 november, 2023
HRMS & Infrastructure - Maintenance and Management training conducted on 9 November, 2023
*ToT and Infrastructure - Project Plan and Monitoring training conducted on 4 December, 2023
The file ApplicationTraining_ChangesList.xls lists all the changes that was not provided during requirement gathering sessions but was shared at the time of training to WSC SME’s
New Changes Effort (in Hrs) |  |  |  | 
Procurement | HRMS | Infrastructure | Training and Placement | ToT
~27 | ~354 | ~45 | ~48 | ~68
* ToT training was given to WSC IT team

## Slide 5: MODULE MILESTONE STATUS
*Infrastructure - Maintenance and Management training done on 9 November, 2023. Project plan and monitoring done on 4th December, 2023
PRIORITY 2 | Requirement | Design | Development | System Testing | Deployment | Training
SLCM | Complete | Complete | Complete | Complete | Not Started | Not Started
TnP | Complete | Complete | Complete | Complete | Not Started | Complete
Procurement | Complete | Complete | Complete | Complete | Not Started | Complete
HRMS | Complete | Complete | Complete | Complete | Not Started | Complete
Infrastructure | Complete | Complete | Complete | Complete | Not Started | Complete
Finance | Complete | Complete | Complete | Complete | Not Started | Not Started
PRIORITY 1 | Requirement | Design | Development | System Testing | Deployment | Training
SLCM | Complete | Complete | Complete | Complete | Complete | Complete
HRMS | Complete | Complete | Complete | Complete | Complete | Complete
Development and System Testing Completed for all modules

## Slide 6: TASKS PLANNED/ACCOMPLISHED THIS WEEK
Sl No. | Description | Owner | Status | Remarks
1 | ToT and Infrastructure Project Plan | SOUL-WSC | Done | SOUL team demonstrated : ToT module to WSC IT team Infrastructure Project Plan Monitoring to WSC SME (Mr. Sanjay Padhi)
2 | WSC Test Server Deployment | SOUL | Done | The first deployment of latest code done on 4 December , 2023
3 | Money Receipt (PDF Generation) Analysis | WSC | On Hold | On December 5th, 2023, an email follow-up was sent to the WSC IT team
4 | HRMS Workflows discussion with WSC: Job Requisition Job Offer Creation Request Goal Settings Employee Renewal Employee Resignation | SOUL | On Going | The workflow for (a) and (b) implemented as per the discussion with WSC IT team The existing workflow of (c), (d) and (e) was discussed on 7th December 2023. SOUL team will analyze whether or not it can be made dynamic
5 | Infrastructure Module Data Template | SOUL | Done | Data template shared with WSC IT team on 8th December, 2023

## Slide 7: OVERALL PROJECT PROGRESS TIMELINE
Milestone 1 - Gap Analysis Document and SRS documents sign off completed in June, 2023
Milestone 2 & 3 - High Level Design (HLD) Document and Prototype digital sign off completed in October, 2023
Milestone 4 - Development of priority 1 & 2 features completed in Aug & October, 2023 respectively

## Slide 8: ISSUES
Sl No. | Description | Issue Date | Issue Owner | Status | Action Items
1 | A delay in discussing and capturing requirements | 19-Jan-23 | WSC | OPEN | WSC stakeholders to acknowledge the delay
2 | Availability of OCAC server | 11-May-23 | WSC | OPEN | WSC to acknowledge the additional effort required (CR) to test the desktop version of the application
3 | SOUL highlighted the addition to scope (change request) for the features that were discovered during the requirements study but were not specified in the request for proposal document | 09-June-23 | WSC | OPEN | WSC stakeholders to acknowledge the change request
6 | Money Receipt (PDF Generation) | 30-Oct-23 | WSC | HOLD | SOUL team trying to debug the issue to determine its underlying cause Update: SOUL team is awaiting for OCAC to provide the pre-production server. Follow up mail has been sent to WSC IT team on 5th December 2023
7 | Integration - Payment Gateway (Axis) | 01-Nov-23 | WSC | HOLD | Axis bank team has provided live kit but development working key is different than the development kit Update: Production integration development is done. WSC IT team to perform the testing

## Slide 9: CHANGE REQUESTS (Requested during Requirement Gathering Stage)
Sl No. | Description | Module | Effort (hr)
1 | Counselling and Entrance Examination Process | Students Management | ~ 475
2 | Training Of Trainers(TOT) | Students Management | ~ 900
3 | Recruitment Process | Human Resources Management System | ~ 368
4 | Employee Re-Engagement | Human Resources Management System | ~ 240
5 | Testing effort for application installation in desktop version | OCAC Server | ~ 160
As discussed on 9th June 2023, the change requests Budget and Payroll have been removed from the the list

## Slide 10: UPCOMING WORK
Sl No. | Description | Owner | Status | Remarks
1 | Application demonstration to module owners: Counselling ToT Academics Payroll Accounting | WSC | OPEN | WSC IT team to coordinate with the module SME’s for scheduling the training sessions
2 | Support to WSC for the following activities: Provisional admission to actual admitted students Roll number generation process Student group generation Class Scheduling Hostel Admission Room Allotment | SOUL - WSC | OPEN | 
3 | ToT Data Template Training | SOUL - WSC | OPEN | After the WSC IT team confirms the availability of the SME, one of the SOUL team member will visit to explain the ToT data template
4 | Dynamic Workflow HRMS | SOUL | OPEN | SOUL team will analyze the feasibility of dynamic workflow for Goal Settings/ Employee Renewal Form/Employee Resignation further
5 | UAT Sign Off | WSC | OPEN | SOUL team will perform another deployment, and the requirements for *all modules will be available to the WSC team for their UAT * SLCM, HRMS,Procurement,Infrastructure,TnP, Accounting

## Slide 11
THANK YOU