## Slide 1
Campus Management Application
At
World Skill Center
WEEKLY PROJECT STATUS REPORT
17-Nov-2023

## Slide 2: PROJECT SUMMARY
OVERALL PROJECT STATUS (R)ed, (A)mber, (G)reen | DELAY
PROJECT NAME | Campus Management Application At World Skill Center(WSC) |  | 
SOUL POC | sharmistha.panda@soulunileaders.com | WSC POC | bishnupriya.panda@worldskillcenter.org
PROJECT START DATE | 03-02-2023 | PROJECT END DATE | 03-02-2024
Red | Likely delay in overall project schedule | Amber | Some Activities are delayed | Green | On track

## Slide 3: PRIORITY1 RELEASE HIGHLIGHTS
SLCM release was scheduled in two phases, priority 1 and priority 2
Priority 1 release date was scheduled on 31 Aug 2023
The Student Applicant feature, which was part of priority 2, was requested to be Go Live on September 26, 2023
The spreadsheet Priority1ImplementationChanges.xlsx lists all the 25 changes
The ppt SLCM & HRMS Priority1 Release.pptx lists all the release features
Release Planned | 1
Release Requested | 2
Priority1 Release Effort | ~ 536
Changes Requested during Implementation | 26
Change Implementation Effort (hrs) | ~ 329
Chart: Change Implementation Effort
| Customization | Data Upload | New Development
 | 10 | 4 | 12

## Slide 4: APPLICATION TRAINING CHANGES
New Changes Effort (in Hrs) |  |  | 
Procurement | HRMS | Infrastructure | Training and Placement
~34 | ~208 | ~33 | ~48
Procurement training session-2 conducted on 6 november, 2023
HRMS & Infrastructure - Maintenance and Management training conducted on 9 November, 2023
The file ApplicationTraining_ChangesList.xls lists all the changes that was not provided during requirement gathering sessions but was shared at the time of training to WSC SME’s

## Slide 5: MODULE MILESTONE STATUS
*Infrastructure - Maintenance and Management training done on 9 November, 2023. Project plan and monitoring to be done
PRIORITY 2 | Requirement | Design | Development | System Testing | Deployment | Training
SLCM | Complete | Complete | Complete | Complete | Not Started | Not Started
TnP | Complete | Complete | Complete | Complete | Not Started | Complete
Procurement | Complete | Complete | Complete | Complete | Not Started | Complete
HRMS | Complete | Complete | Complete | Complete | Not Started | Complete
Infrastructure | Complete | Complete | Complete | Complete | Not Started | *Partial
Finance | Complete | Complete | Complete | Complete | Not Started | Not Started
PRIORITY 1 | Requirement | Design | Development | System Testing | Deployment | Training
SLCM | Complete | Complete | Complete | Complete | Complete | Complete
HRMS | Complete | Complete | Complete | Complete | Complete | Complete
Development and System Testing Completed for all modules

## Slide 6: TASKS PLANNED/ACCOMPLISHED THIS WEEK
Sl No. | Description | Owner | Status | Remarks
1 | Incorporation of the changes / modifications proposed by WSC SME’s during application training | SOUL | On Going | Procurement - Done Training & Placement - On Going HRMS - On Going Infrastructure - Done
2 | SOUL team analyzing existing refund process and money receipt generation (pdf) | SOUL | On Going | 

## Slide 7: OVERALL PROJECT PROGRESS TIMELINE
Milestone 1 - Gap Analysis Document and SRS documents sign off completed in June, 2023
Milestone 2 & 3 - High Level Design (HLD) Document and Prototype digital sign off completed in October, 2023
Milestone 4 - Development of priority 1 & 2 features completed in Aug & October, 2023 respectively

## Slide 8: ISSUES
Sl No. | Description | Issue Date | Issue Owner | Status | Action Items
1 | A delay in discussing and capturing requirements | 19-Jan-23 | WSC | OPEN | WSC stakeholders to acknowledge the delay
2 | Availability of OCAC server | 11-May-23 | WSC | OPEN | WSC to acknowledge the additional effort required (CR) to test the desktop version of the application
3 | SOUL highlighted the addition to scope (change request) for the features that were discovered during the requirements study but were not specified in the request for proposal document | 09-June-23 | WSC | OPEN | WSC stakeholders to acknowledge the change request
5 | Pending Action Items from WSC | 19-Sep-23 | WSC | OPEN | WSC IT teams should assist SOUL to close the pending open points
6 | Money Receipt Generation | 30-Oct-23 | SOUL - WSC | OPEN | SOUL team trying to debug the issue to determine its underlying cause
7 | Integration - Payment Gateway (Axis) | 01-Nov-23 | SOUL - WSC | OPEN | Axis bank team has provided live kit but development working key is different than the development kit

## Slide 9: CHANGE REQUESTS (Requested during Requirement Gathering Stage)
Sl No. | Description | Module | Effort (hr)
1 | Counselling and Entrance Examination Process | Students Management | ~ 475
2 | Training Of Trainers(TOT) | Students Management | ~ 900
3 | Recruitment Process | Human Resources Management System | ~ 368
4 | Employee Re-Engagement | Human Resources Management System | ~ 240
5 | Testing effort for application installation in desktop version | OCAC Server | ~ 160
As discussed on 9th June 2023, the change requests Budget and Payroll have been removed from the the list

## Slide 10: UPCOMING WORK
Sl No. | Description | Owner | Status | Remarks
1 | Application demonstration to module owners | SOUL - WSC | OPEN | WSC IT team will check the availability of Infrastructure - Project plan monitoring SME, Payroll, Accounting SME’s
2 | SOUL team will propose the payment refund process to WSC | SOUL | OPEN | 

## Slide 11
THANK YOU