## Slide 1
Campus Management Application
At
World Skill Center
WEEKLY PROJECT STATUS REPORT
29-Sep-2023

## Slide 2: PROJECT SUMMARY
OVERALL PROJECT STATUS (R)ed, (A)mber, (G)reen | DELAY
PROJECT NAME | Campus Management Application At World Skill Center(WSC) |  | 
SOUL POC | sharmistha.panda@soulunileaders.com | WSC POC | bishnupriya.panda@worldskillcenter.org
PROJECT START DATE | 03-02-2023 | PROJECT END DATE | 03-02-2024
Red | Likely delay in overall project schedule | Amber | Some Activities are delayed | Green | On track

## Slide 3: CAMPUS MANAGEMENT SOFTWARE AT WORLD SKILL CENTER
SLCM Priority 1 Release Activities (Student Admission) |  |  | 
Description | Owner | Status | Remarks
Campus Management Software At World Skill Center - Priority 1 Release - SLCM MODULE ~ Student Admission / Enrollment / Applicant (Slide 22,23) | SOUL - WSC | On-Going | SOUL team will work on the changes suggested by WSC team during demonstration / training and prepatory work for Go-Live- 22 September 2023 - Done
 |  |  | Go - Live of Student Admission - 25 September 2023 - Done on 26 September 2023
 |  |  | Assistance or support to the trainers in responding to student inquiries (issue code fix, incorporation of changes / feedback from WSC) - 26 ~ 30 September 2023 - On-Going
 |  |  | Course enrollment of the students - to be scheduled by WSC stakeholders
 |  |  | Online Payment by the students - to be scheduled by WSC stakeholders

## Slide 4: CAMPUS MANAGEMENT SOFTWARE AT WORLD SKILL CENTER
SLCM & HRMS Priority 1 Release Activities |  |  | 
Description | Owner | Status | Remarks
Campus Management Software At World Skill Center - Priority 1 Release - SLCM MODULE (features listed in slides 16 to 19) | SOUL - WSC | OPEN | Update : As Student Admission / Enrollment (Applicant) is high priority for WSC, production roll-out of SLCM features (listed in slides 16-18) shall be planned / scheduled post Student Admission (Applicant) release
Campus Management Software At World Skill Center - Priority 1 Release - HRMS MODULE (features listed in slides 20 to 21) | SOUL - WSC | OPEN | On August 28, 2023, SOUL team demonstrated the application to WSC stakeholders after completion of development activities. During the demonstration, SOUL team received feedback (changes) Update : As Student Applicant is high priority for WSC, production roll-out of HRMS shall be planned / scheduled post Student Applicant release

## Slide 5: TASKS PLANNED/ACCOMPLISHED THIS WEEK
TASKS |  |  | 
Description | Owner | Status | Remarks
Design phase | SOUL | DELAY | The design documents of the following modules have been shared with module owners for their digital sign off: Students Management & Academic System Training Of Trainers Procurement & Inventory Management Human Resources Management System Training & Placement Infrastructure Management Finance and Accounting System The details of design phase shared in Slide 7 and 8
Application demonstration to WSC stakeholders | SOUL | OPEN | Details shared in slide 9

## Slide 6: TASKS PLANNED/ACCOMPLISHED THIS WEEK
TASKS |  |  | 
Description | Owner | Status | Remarks
Backup plan for Campus Management Software At World Skill Center application server | SOUL-WSC | OPEN | Backup Responsibility : Virtual Machine (VM) Backup by OCAC (monthly ) Database Backup with files by SOUL but stored in OCAC remote server file location (Daily at 12:00AM) SOUL team has completed the database backup in their own server till OCAC has provided the remote server file location SOUL team followed with OCAC to provide the file location

## Slide 7: DESIGN PHASE - DIGITAL SIGN OFF STATUS
Module | Owner(WSC) | Status | Remarks
Training and Placement | Mr. Rajan Pradhan | DONE | 21-Aug-23: Documents sent to module owner for digital sign off 25-Sep-23: Received sign off (approval) from Academy module owner
Procurement & Inventory Management | Mr. Chandan Kumar | DELAY | 21-Aug-23: Documents sent to module owner for digital sign off
Human Resources Management System | Ms. Shweta Choudhury | DONE | 22-Aug-23: Documents sent to module owner for digital sign off 22-Sep-23: Received sign off today
Infrastructure Management : Maintenance & Management | Mr. Brahmananda Sahoo | DONE | 22-Aug-23: Documents sent to module owner for digital sign off 24-Aug-23: WSC module owner has approved
Infrastructure Management : Project Plan and Monitoring | Mr. Sanjay Padhi | DELAY | 22-Aug-23: Documents sent to module owner for digital sign off
Finance and Accounting System | Mr. Bibhu Behura / Mr. Subodha Patra | DELAY | 22-Aug-23: Documents sent to module owner for digital sign off
Students Management Modules, Academic System - Admission | Mr. Anil Das | DELAY | 05-Sep-23: Documents sent to module owner for digital sign off

## Slide 8: DESIGN PHASE - DIGITAL SIGN OFF
Module | Owner(WSC) | Status | Remarks
Students Management Modules, Academic System - Academics | Ms. Suppiah Nagammal / Mr. Subhasis Das, Mr. Anil Das, Ms. Suguna Srinivasan | PARTIALLY DONE | 05-Sep-23: Documents sent to module owner for digital sign off 08-Sep-23: Received sign off (approval) from Academy module owner
Students Management Modules,Academic System - Examination | Mr. Suresh Kumar | DONE | 05-Sep-23: Documents sent to module owner for digital sign off 25-Sep-23: Received sign off (approval) from Academy module owner
Training Of Trainers (ToT) - Academy | Ms. Suppiah Nagammal | DELAY | 05-Sep-23: Documents sent to module owner for digital sign off
Training Of Trainers (ToT) - SOE | Mr. Subhasis Das | DELAY | 05-Sep-23: Documents sent to module owner for digital sign off
Students Management Modules,Academic System - Faculty workload, Hostel, Student clearance, Grievance,Feedback | Ms. Sushree / Mr. Anil Das | DELAY | 12-Sep-23: Documents sent to module owner for digital sign off
Update : The WSC module owners' digital approval is still pending. For the digital sign-off, the WSC IT team will coordinate

## Slide 9: CAMPUS MANAGEMENT SOFTWARE AT WORLD SKILL CENTER APPLICATION DEMONSTRATION
Description | Owner | Status | Remarks
SLCM (Admission, Academics, Examination) | SOUL | DONE | SOUL team demonstrated the application to WSC stakeholders on 16th and 17th August, 2023
HRMS | SOUL | DONE | SOUL team demonstrated the application to WSC stakeholders on 28 August, 2023
Hostel and Student Admission Fees | SOUL | DONE | SOUL team demonstrated the application to WSC stakeholders on 01 September, 2023
Procurement and Inventory management | SOUL-WSC | DELAY | 08-Sep-23:SOUL team demonstrated the application to WSC stakeholders on 08 September, 2023 Update: Subsequent meeting in the week of 11-Sep ~ 15-Sep could not be conducted due to unavailablity of stakeholders
Infrastructure management | SOUL-WSC | DELAY | SOUL team initiated feature demonstration to module owners on 31 Aug 2023. The demonstration could not be scheduled due to their unavailablity

## Slide 10: OVERALL PROJECT PROGRESS TIMELINE
Milestone 1 - Gap Analysis Document and SRS documents signed off on 12 June, 2023
Milestone 2 - Design Document digital sign off pending from WSC stakeholders

## Slide 11: ISSUES
TASKS |  |  |  | 
Description | Issue Owner | Status | Action Items | Remarks
Integration - Payment Gateway (Axis) | SOUL - WSC | OPEN | WSC IT team to coordinate with Axis bank for issue resolution | 22-Sep-23: Axis bank development team is checking the issue Update: SOUL team has communicated Axis bank / WSC for the mandatory fields removal
Application demonstration to WSC stakeholders - Infrastructure Module | SOUL - WSC | DELAY | WSC IT team should liaise with stakeholders to ensure their availability | 08-Sep-23: The demonstration was scheduled for the week of September 4–8, 2023 however it was canceled due to unavailability of stakeholders Update: No meeting held
Procurement and Inventory management | SOUL - WSC | DELAY | WSC IT team should liaise with stakeholders to ensure their availability | 08-Sep-23:SOUL team demonstrated the application to WSC stakeholders on 08 September, 2023 Update: Subsequent meeting in the week of 11-Sep ~ 15-Sep could not be conducted due to unavailablity of stakeholders

## Slide 12: ISSUES
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
A delay in discussing and capturing requirements | High | The revised project plan was discussed on 06-Apr, during weekly Project review meeting update : schedule has been reviwed with WSC stakeholders | WSC | OPEN | WSC stakeholders to acknowledge the delay | 
SOUL highlighted the addition to scope (change request) for the features that were discovered during the requirements study but were not specified in the request for proposal document | High | WSC stakeholders to acknowledge the change request | WSC | OPEN | The change requests will be acknowledged by WSC | Update: SOUL team sent an email to WSC to acknowledge the change reqests and the additional effort required for development. The change requests have been listed in Slide 8

## Slide 13: ISSUES
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
Availability of OCAC server | High | WSC stakeholder to ensure availability of the requested server version | WSC | OPEN | SOUL team has installed the application and database on the same server in the desktop version WSC to acknowledge the additional effort required (CR) to test the desktop version of the application | 

## Slide 14: CHANGE REQUESTS
Description | Module
Entrance Examination Process | Students Management
TrainingOfTrainers(TOT) | Students Management
Recruitment Process | Human Resources Management System
Employee Re-Engagement | Human Resources Management System
Testing effort for application installation in desktop version | OCAC Server
As discussed on 9th June 2023, the change requests Budget and Payroll have been removed from the the list

## Slide 15: UPCOMING WORK
WHAT’S NEXT |  |  | 
Description | Owner | Status | Remarks
Campus Management Software At World Skill Center - Priority 1 Release - SLCM MODULE ~ Student Admission Enrollment (Applicant) | SOUL - WSC | On-Going | Activities mentioned in slide 3

## Slide 16: Campus Management Software At World Skill Center Priority 1 Release
MODULE | SCOPE | SCREENS
Admission | Masters | Department
 |  | Course Type
 |  | Courses
 |  | Semester
 |  | Modules
 |  | Topic
 |  | Class Rooms
 | Admission Master | Academic Year
 |  | Academic Term
 |  | Academic Events
 |  | Academic Calendar Template
 |  | Documents
 |  | Documents Template
 |  | Eligibility Parameters
 | Student and Trainer | Student
 |  | Trainer
 |  | Student Categories
 |  | Student Btach
 | Tool | Course Enrollment Tool

## Slide 17: Campus Management Software At World Skill Center Priority 1 Release
MODULE | SCOPE | SCREENS
Academics | Groups & Schedules | Student Group
 |  | Class Schedule
 | Attendance and Leave Application | Student Attendance
 |  | Student Attendance Tool
 |  | Reason for Leave
 |  | Class Advisor and Manager Assignment
 |  | Student Leave Application
 | Mentor - Mentee | Mentor - Mentee
 |  | Communication
 | Tools | Class Scheduling Tool
 |  | Student Attendance Tool

## Slide 18: Campus Management Software At World Skill Center Priority 1 Release
MODULE | SCOPE | SCREENS
Examination | Master | Exam Type
 |  | Assessment Component
 |  | Grading Scale
 | Examination | Exam Declaration
 |  | Module Wise Exam Group
 |  | Exam Evaluation Plan
 |  | Exam Paper Setting
 |  | Student Backpaper Tracking
 | Evaluation | Component Evaluation
 |  | Component Re-Evalaution
 |  | Final Semester Result
 | Tools | Component Evaluation Tool
 |  | Component Re-Evalaution Tool
 |  | Final Semester Result Tool
 |  | Cumulative Marksheet Tool

## Slide 19: Campus Management Software At World Skill Center Priority 1 Release
ADDITIONAL FEATURES
Following are the additional features that will be part of priority 1 release : Student Enrollment Student Hostel Infrastructure (Maintenance & Management / Project Plan and Monitoring) Online Payment for HDFC (as long as HDFC gives SOUL team the live kit)

## Slide 20: Campus Management Software At World Skill Center Priority 1 Release
MODULE | SCOPE | SCREENS
HRMS | Masters | Employment Type
 |  | Branch (Location)
 |  | Department
 |  | Designation
 |  | Employee Grade
 |  | Employee Group
 |  | Holiday List
 |  | Employee Separation Template
 | Employee Lifecyle | Employee
 |  | Employee Profile Updation
 |  | Employee Resgination
 |  | Employee Separation
 |  | Employee Suggestion
 |  | Employee Transfer

## Slide 21: Campus Management Software At World Skill Center Priority 1 Release
MODULE | SCOPE | SCREENS
HRMS | Leave Management | Leave Type
 |  | Leave Policy Assignment
 |  | Leave Allocation
 |  | Leave Application
 |  | Leave Block List
 |  | Compensatory Leave Request
 |  | Leave Policy
 | Shift Management | Shift Type
 |  | Shift Assignment
 |  | Shift Request
 | Attendance Management | Attendance
 |  | Employee Attendance Tool
 |  | Attendance Request
 |  | Employee Checkin
 | Settings | HR Settings

## Slide 22: Campus Management Software At World Skill Center Priority 1 Release
Release Details Overview
Student applicant records (3000+) that were provided by WSC as part of the admission process were uploaded to the application by SOUL Student applicant ,Trainer and WSC IT team credentials created by SOUL team Student Applicant form Course enrollment of students Online Payment (HDFC) Student Additionally, the release includes the changes (listed in slide 4) that were recommended by WSC at the time / post release of Student admission (applicant) feature

## Slide 23: Changes
SUB FEATURES | STATUS | REMARKS
“Instruction to Apply Form” to be renamed | DONE | 
The form must include a declaration message | DONE | 
The size of the declaration block will be large and the second line will be in a paragraph | DONE | 
WSC logo size and address to be changed in the print form along with the font | Partially Done | SOUL team is working on it
The spelling of “Course Preference Details” spelling to be corrected | DONE | 
The system-generated ID will be the acknowledgment number that is displayed in the message that appears after submitting the form | DONE | 
No change should be allowed in the form post approval | DONE | 
Day and timestamp should be shown in the application print format | DONE | 
The option “Rejected” should be removed and “Not Approved” to be added | DONE | 
Additional changes are being incorporated in response to the on-going feedback from WSC team

## Slide 24
THANK YOU