## TC1_Item_Group
Test Case ID | TC1_Item_Group | Test Case Description | An Item Group is a way to classify items based on types. Item Group should be visible in a tree view so that it becomes easier to view and differentiate between parent and child Item Group.
Created By | Aman Kumar Singh | Reviewed By
S# | Pre-requisite |  | Test Data
1 |  |  | url: wscdemo.eduleadonline.com
Test Scenario | New Item Group, Defaults, Item Tax, Authorization for Requisition
Step No. | Step Description | Expected Result | Actual Results | Pass/Fail/Not Executed/Suspended | Comment | Bug_ID
Home > Material Management > Items & Pricing > Item Group
1 | Click on Home > Material Management > Items & Pricing > Item Group | Item Group page should be open | Item group page is opening as expected | Pass
2 | View the Item Group page | saved data should be shown on Item Group page | The saved data is visible in the list view of item group as expected | Pass
3 | Click Add Item Group button | Add Item Group button should be clickable and new Item Group page should be open | the button is clickable and New Item Group page is visible as expected | Pass
4 | Without fill any mandatory fields, click on save button | Page should not proceed. Alert message should be shown for unfilled mandatory fields. Mandatory fields should be mentioned as * symbol. | page is not procceding without filling mandatory fields and also alert message is thrown to fill mandatory fields as expected | Pass
5 | fill only mandatory fields, click on save button | Page should be saved successfully | yes saving as expected | Pass
6 | Click on item group name text field | User should able to fill this text field | user is able to fill item group name by giving user input as expected | Pass
7 | click on parent item group dropdown , select the data | parent item group dropdown should be clickable and open. user should able to select the data from dropdown | parent item group is appearing as dropdown and user is able to select option by clicking on it as expected | Pass
8 | click on is group checkbox | User will checked the checkbox then it should be fetched Parent Item Group when new item group will created | Yes working as expected | Pass
9 | click on add row button of defaults section | new row should be open. item group defaults row & it's respective fields should be shown | when user clicks on Add row button a new row is added in the table and all the respective fields are visible as expected | Pass
10 | click on company dropdown, select the company | user should able to select the company | by default when user clicks on Add Row the company gets visible and also user is able to select company from dropdown | Pass
11 | click on default store dropdown, select the default store | user should able to select the default store | by default when user clicks on Add Row the company gets visible and also user is able to select from dropdown | Pass
12 | click on default price list dropdown, select the default price list | user should able to select the default price list | user is able to select default price list by clicking on the dropdown | Pass
13 | click on add row button of item tax section | new row should be open. taxes row & it's respective fields should be shown | when user clicks on Add row button a new row is added in the table and all the respective fields are visible as expected | Pass
14 | click on item tax template dropdown, select the template | user should able to select the template | user is able to select the item tax template from the dropdown as expected | Pass
15 | click on tax category dropdown, select the tax category | user should able to select the tax category | user is able to select the tax category from the dropdown as expected | Pass
16 | click on valid from, choose the date | Date picker box should be open, user should able to put the date | user is able to select the date from the datepicker calendar as well as can enter the date in the defined format | Pass
17 | click on minimum net rate, put the value | user should able to put the value | Accepting -ve value | Fail |  | 2
18 | click on maximum net rate, put the value | user should able to put the value | Accepting -ve value | Fail |  | 2
19 | click on add row button of Authorization for Requisition section | new row should be open. Authorization Table & it's respective fields should be shown | when user clicks on Add row button a new row is added in the table and all the respective fields are visible as expected | Pass
20 | click on authority dropdown, select the data | user should able to select the authority | when user clicks on authority a dorpdown is appearing as expected an user can select option | Pass
21 | click on from amount, put the value | user should able to put the value | from amount is clickable and user is able to put the amount but accepting negative value | Fail |  | 3
22 | click on To amount, put the value | user should able to put the value | To amount is clickable and user is able to put the amount but accepting negative value | Fail |  | 3
23 | After fill the mandatory & required fields, click on save button | page should be saved successfully | page is saving with all the mandatory fields and required fields and it is reflecting in the list view as expected | Pass
| Roles And Permission |  | Actual Result | Status | Bug_ID
| Login as GM-Procurement & Contract Management and check the access privileges | The user should have all the following accesses: Select, Read,Write,Create & Delete | GM - Procurement & Contract management has Read, Select, Write which is edit, create but cannot delete | Fail | 59
| Login as Purchase Manager and check the access privileges | The user should have all the following accesses: Select, Read,Write,Create & Delete | Purchase Manager has Read, Select, Write which is edit, create but cannot delete | Fail | 59

## TC2_Item
Test Case ID | TC2_Item | Test Case Description | Item can be a product or a service offered by your company. The term Item is also applicable to raw materials or components of products yet to be produced.
Created By | Aman Kumar Singh | Reviewed By
S# | Pre-requisite |  | Test Data
1 | 1)Item Group 2)Warehouse 3)A Unit of Measure (If Required) |  | url: wscdemo.eduleadonline.com
Test Scenario | New Item, Details, Inventory - Serial Nos and Batches, Accounting, Purchasing- Supplier Details, Tax, Quality
Step No. | Step Description | Expected Result | Actual Results | Pass/Fail/NotExecuted/Suspended | Comment | Bug_ID
Home > Material Management > Items & Pricing > Item
1 | Click on Home > Material Management > Items & Pricing > Item | Item page should be open | Item page is opening as expected | Pass
2 | View the Item page | saved data should be shown on Item page | The saved data is visible in the list view of item as expected | Pass
3 | Click Add Item button | Add Item button should be clickable and new Item page should be open | the button is clickable and New Item page is visible as expected | Pass
4 | Without fill any mandatory fields, click on save button | Page should not proceed. Alert message should be shown for unfilled mandatory fields. Mandatory fields should be mentioned as * symbol. | page is not procceding without filling mandatory fields and also alert message is thrown to fill mandatory fields as expected | Pass
5 | fill only mandatory fields, click on save button | Page should be saved successfully | yes saving as expected | Pass
6 | verify the addition of new item screen | for creating a New item, respective sections should be shown. like Details, Inventory, Accounting, Purchasing, Tax Quality | yes the moment user clicks on Add item button to create a new item all the section like Details, Inventory, Accounting, Purchasing, Tax Quality is visible to the user | Pass
7 | Verify the Item code field | Item code field should be auto fetched from item group name | Yes Item code is fetched automatially when user gives input in the item group | Pass
8 | click on item name , fill it | user should able to fill item name text field | yes user is able to enter Item name and also when user selects the item group item name is fetched from the saved item group | Pass
9 | click on item group dropdown, select the data | user should able to select the item group name. it should be a link field, it should be linked with item group screen | when user click on item group an auto-suggetsive dropdown appears and user is able to select the item group name from it which is linked with the master of item group screen | Pass
10 | click on Default Unit of Measure dropdown, select the data | user should able to select theDefault Unit of Measure it should be a link field, it should be linked with Default Unit of Measure screen | when user click on Default Unit of Measure an auto-suggetsive dropdown appears and user is able to select the from it which is linked with the master of Default Unit of Measure screen | Pass
11 | click on disable checkbox | If you disable an Item, it should not be selected in any transaction. | yes disable checkbox is clicakble and when checked then status will be disabled and the item will not be used in any of the transactions | Pass
12 | click on Maintain Stock checkbox | If you are maintaining stock of this Item in your Inventory,then it should make a stock ledger entry for each transaction of this item when checkbox is checked. Ensure to keep this option unchecked when creating a non-stock Item or a service. | by default this checkbox is checked and user can also uncheck as per their need and when checked then stock ledger entry will be made with each transaction of this item in the inventory | Pass
13 | click on opening stock text field, fill the value with numeric data | user should able to fill the value with numeric data in opening stock | yes only +ve numeric value is accepted in this field | Pass
14 | click on Valuation Rate text field, fill the value with numeric data | user should able to fill the value with numeric data in Valuation Rate | accepting -ve value as input | Fail |  | 6
15 | click on Standard Selling Rate text field, fill the value with numeric data | user should able to fill the value with numeric data in Standard Selling Rate | accepting -ve value as input | Fail |  | 6
16 | click on Is Fixed Asset checkbox | Tick this checkbox if this item is a company Asset. | yes Is Fixed Asset checkbox is clickable and when clicked Asset Category field gets visible & Auto Create Assets on Purchase chcekbox also gets visible | Pass
17 | click on Auto Create Assets on Purchase checkbox | If Item is a Company Asset, tick this checkbox if you want to auto create assets while purchasing this item through Purchase Cycle. | yes Auto Create Assets on Purchase checkbox is clickable and when clicked Asset Naming Series field gets visible | Pass
18 | click on Asset Category dropdown, select the data | user should able select the Asset Category data, it should be a link field. it should linked with Asset Category screen | when user click on Asset Category an auto-suggetsive dropdown appears and user is able to select the Asset Category name from it which is linked with the master of Asset Category screen | Pass
19 | click on Asset Naming Series, fill it | user should able to fill the Asset Naming Series field | when user clicks on Asset Naming Series a dropdown is appearing where is user is able to select a single option | Pass
20 | click on description textarea, fill it | user should able to fill the description text area. | user is able to give user input in description | Pass
21 | Go to inventory section | Inventory related fields should be shown | Inventory section is clickable and all the field associated with it is visible | Pass
22 | click on Shelf Life In Days text field, fill it | user should able to fill Shelf Life In Days text field. | user is able to fill Shelf Life In Days but accepting -ve input also | Fail |  | 8
23 | click on end of life field, put the date | End of life date field should be clickable. datepicker box should be open. user should able to put the date | End of Life is clickable & and user is able to selcet the date either from the datepicker or can enter manully in the defined format | Pass
24 | click on Default Material Request Type dropdown, select the data | Default Material Request Type dropdown should be clickable. user should able to select the data. | yes it is appering as a dropdown and user is able to select single option from it | Pass
25 | click on Valuation Method dropdown, select the data | Valuation Method dropdown should be clickable. user should able to select the data | yes it is appering as a dropdown and user is able to select single option from it | Pass
26 | click on Warranty Period (in days) text field, fill it | Warranty Period (in days) should be clickable. user should able to fill it | user is able to click on Warranty Period (in days) field and can enter the numeric data but also accepting -ve value | Fail |  | 11
27 | click on Weight Per Unit text field, fill it | Weight Per Unit text field should be clickable. user should able to fill it | Weight Per Unit is accepting -ve vaue as input | Fail |  | 12
28 | click on Weight UOM dropdown, select the data | Weight UOM dropdown should be clickable. user should able to select the data | Weight UOM is apperaing as a dropdown but only few records are being fetched | Pass | weight UOM is fetching only few records from UOM master screen
29 | click on Allow Negative Stock check box | When checked the item will be allowed to go negative even if negative stock is disabled from Stock Settings. This is useful if you don't want to enable negative stock on high value items but few select low value items are allowed to go negative for few days. | yes the checkbox is clickable and when checked then negative stock can be permitted but only for low value items from stock settings | Pass
30 | click on Has Batch No check box | Options for batch number, expiry date, and retaining sample stock will be revealed on ticking this checkbox. You cannot activate this if there is any pre-existing transaction for this item. If this is disabled, you'll have to enter the serial numbers manually for every transaction. | yes user is able to check the checkbox on new transaction and when checked batch number, expiry date will be revealed | Pass
31 | click on Automatically Create New Batch check box | If the batch number is not mentioned in transactions, then they will be automatically created according to a format like AAAA.00001. If you always want to manually create a batch number for this item, leave this field blank. This setting will override 'Naming Series Prefix' in Stock Settings. Batch numbers can be set to be generated automatically if you manufacture the Items or can be entered manually if it comes from an external manufacturer. | yes user is able to check the checkbox in an ongoing transaction and when checked batch number will be created manually over naming series prefix | Pass
32 | click on Batch Number Series text field , fill it | user should able to fill Batch Number Series text field | batch number series is accepting -ve value as well as special characters | Fail |  | 15
33 | click on Has Serial No check box | This is similar to Batch Number Series, it'll be created when you make transactions/manufacture | yes user is able to check the checkbox when any new transaction is made by the user and when checked Serial number series field should get visible and user is able to give input in the defined format | Pass
34 | click on Serial Number Series text field , fill it | user should able to fill Serial Number Series text field | Serial number series is accepting -ve value as well as special characters | Fail |  | 15
35 | click on Has Expiry Date checkbox | If you tick this, the batch number will be created according to the expiry date. The expiry dates can be set in the 'Batch' master. | yes user is able to check on the checkbox and when checked the batch number should be created based upom the Expiry date | Pass
36 | Go to accounting section | Accounting related field should be shown | Accounting section is clickable and all the field associated with it is visible | Pass
37 | click on add row button of Item Defaults section | Item Defaults fields should be shown on new field | Add row button is clickable and the new row is being inserted in the Item Defaults table & default values are being auto-fetched and alos user can edit as per their needs | Pass
38 | click on company dropdown, select data | user should able to select the company. it should be a link field. it should be linked with company screen | when user click on the company a dropdown appears as expected and user is able to select the single option from company which is linked with the company master | Pass
39 | click on Default Store dropdown, select data | user should able to select the Default Store. it should be a link field. it should be linked with Default Store screen | when user clicks on Default Store a dropdown is appears as expected and user is able to select a single option from the Default Store which is linked with the Default Store screen | Pass
40 | click on Default Price List dropdown, select data | user should able to select theDefault Price List. it should be a link field. it should be linked withDefault Price List screen | when user clicks on Default Price List a dropdown appears as expected and user is able to select a single option from Default Price List | Pass
41 | go to purchasing section | purchase related fields should be shown | Purchasing section is clickable and all the field associated with it is visible | Pass
42 | click on Default Purchase Unit of Measure dropdown, select the data | Default Purchase Unit of Measure dropdown should be click able. user should able to select the data. it should be linked with Default Purchase Unit of Measure screen | when user clicks on Default Purchase Unit of Measure a dropdown appears as expected where is able to select a single option which is linked with the Default Purchase Unit of Measure master screen | Pass
43 | click on Minimum Order Qty text field, fill it | user should able to fill Minimum Order Qty text field. Minimum quantity should be as per Stock UOM | Minimum Order Qty field is clickable but accepting -ve input | Fail |  | 16
44 | click on Safety Stock text field, fill it | user should able to fill Safety Stock text field | Safety Stock field is clickable but accepting -ve input | Fail |  | 17
45 | click on allow purchase check box | allow purchase check box should be clickable. User will tick then it should be allow you to purchase | Allow Purchase checkbox is checked by default when user switch to purchase section and also user is able to perform chceck and uncheck action | Pass
46 | click on add row of Supplier Items section | Supplier Items fields should be shown . | when user clicks on Supplier details a table is visible and the moment user clicks on Add row button a new row is inserted in the table | Pass
47 | click on supplier dropdown, select supplier | dropdown should be clickable & open. user should able to select supplier | when user clicks on Supplier a dropdown is appears as expected and user is able to select a single option from the Supplier which is linked with the master of Supplier screen | Pass
48 | click on Date of Empanelment date field, put the date | date picker box should be open. user should able to put the date | when user clicks on Date of Empanelment a datepicker calendar is open as expected and also user can enter the date maually in the defined format | Fail |  | 18
49 | click on attach button of attachment, attach the document | attach button should be worked properly. user should able attach the document | when user try to click on attach button it is clickable and a dilog-pop window opens where user can attach & upload image but preview functionality is not working properly | Fail |  | 21
50 | go to Tax section | tax related field should be shown | Tax section is clickable and all the field associated with it is visible | Pass
51 | click on add row of taxes | Item Tax Template, Tax Category and it's related field should be open in the new row | Add row button is clickable and the new row is being inserted in the Taxes Will also apply for variants table and all the fields associated with the table is visible as expected | Pass
52 | click on Item Tax Template dropdown | Item Tax Template dropdown should be click able . user should able to select the data. it should be a link field. it should be linked with Item Tax Template screen | Item Tax Template is clickable by the user and appears as a dropdown as expected where user can select a single option which is fetched from Item Tax Template which is the master screen | Pass
53 | click on Tax Category dropdown | Tax Category dropdown should be click able . user should able to select the data. it should be a link field. it should be linked with Tax Category screen | Tax Category is clickable by the user and appears as a dropdown as expected where user can select a single option which is fetched from Tax Category which is the master screen | Pass
54 | click on valid from date field, put the date | valid from field should be clickable. datepicker box should be open. user should able to put the date | Valid from is clickable & and user is able to selcet the date either from the datepicker or can enter manully in the defined format | Pass
55 | click on Minimum Net Rate field, put the value | user should able to put the value | user is able to click on Minimum Net Rate but accepting -ve value | Fail |  | 2
56 | click on maximum Net Rate field, put the value | user should able to put the value | user is able to click on Maximum Net Rate but accepting -ve value | Fail |  | 2
57 | go to quality section | quality related fields should be shown | Quality section is clickable and all the field associated with it is visible | Pass
58 | click on Inspection Required before Purchase checkbox | Inspection Required before Purchase should be clickable. If an inspection is mandatory before the item is purchased, i.e., before you generate Purchase Receipt, tick this checkbox. | Inspection Required before Purchase chcekbox is clickable and when checked then before puchasing any item inspection will be mandatory | Pass
59 | click on Quality Inspection Template dropdown, put the data | Quality Inspection Template dropdown should be clickable. user should able to put the data. it should be a link field. it should be linked with Quality Inspection Template screen. | Quality Inspection Template clikable and the moment user clicks on it a dropdown is appearing as expected where user can select a single option which is linked with the master of Quality Inspection Template screen | Pass
60 | click on Inspection Required before Delivery checkbox | Inspection Required before Delivery should be clickable.If an inspection is required at the time of delivery from your Supplier is mandatory for this Item, tick this checkbox. | Inspection Required before Delivery checkbox is clickable and when checked then before delivery of any item from supplier inspection will be mandatory | Pass
61 | fill all mandatory and required fields, then click on save button | page should be saved successfully | yes after filling all the required mandatory fields the page is saving as expected | Pass
62 | click on view button | Stock Ledger: On click of this button you will be able to see the stock ledger Stock Balance: On click of this button you will be able to see the stock balance Stock Projected Qty: On click of this button you will see the projected stock o the items based on your previous transaction history | view button is clickable but when user clicks on any of the 3 options of view button alert message disaplys "dont have the permission to access" | Fail
63 | click on action button | Add/ Edit Prices: On click of this button you will be able to add/ edit item price by creating a new or editing an existing Item price | action button dropdown is clickable and 2 options gets visible adn user clicks on the Add/Edit Prices of that item which is also present in the item price screen then it navigates to the item price of that particluar item as expected or else it is saying to add the item price of the item which the user is trying to edit | Pass
64 | click on duplicate button | On click of this button you can create a duplicate item with the same details as existing | when user cliks on duplicate button a copy of same item will be created as expected | Pass
| Roles And Permission |  | Actual Result | Status | Bug_ID
| Login as GM-Procurement & Contract Management and check the access privileges | The user should have all the following accesses: Select, Read,Write,Create & Delete | GM - Procurement & Contract management has Read, select, Write which is edit, create but cannot delete | Fail | 59
| Login as Purchase Manager and check the access privileges | The user should have all the following accesses: Select, Read,Write,Create & Delete | Purchase Manager has Read, select, Write which is edit, create but cannot delete | Fail | 59

## TC3_Item_Price
Test Case ID | TC3_Item_Price | Test Case Description | Item Price is the record in which you can log the selling and buying rate of an item.
Created By | Aman Kumar Singh | Reviewed By
S# | Pre-requisite |  | Test Data
1 | 1)Item 2)Price List |  | url: wscdemo.eduleadonline.com
Test Scenario | New Item Price, Price List,
Step No. | Step Description | Expected Result | Actual Results ( Hostel Administrator) | Pass/Fail/Not Executed/Suspended | Comment | Bug_ID
Home > Material Management > Items & Pricing > Item Price
1 | Click on Home > Material Management > Items & Pricing > Item Price | Item Price page should be open | item price page is opening as expected | Pass
2 | View the Item Price page | saved data should be shown on Item Price page | The saved data is visible in the list view of item price page as expected | Pass
3 | Click Add Item Price button | Add Item Price button should be clickable and new Item Price page should be open | the button is clickable and New Item price page is visible as expected | Pass
4 | Without fill any mandatory fields, click on save button | Page should not proceed. Alert message should be shown for unfilled mandatory fields. Mandatory fields should be mentioned as * symbol. | page is procceding without filling rate which is a mandatory field and also alert message is thrown for only 2 of the mandatory field where rate is not present in the alert message | Fail |  | 26
5 | fill only mandatory fields, click on save button | Page should be saved successfully | yes saving as expected | Pass
6 | click on item code dropdown, select the data | item code dropdown should be clickable . user should able to put the data. it should be a link field. after select the item code, item name & item description should be auto fetched | Yes when user cliks on item code a dropdown appears as expected and user is able to select a single option which is linked with master of item and the moment user selects the option Item name and item description fields gets visible and the value is fetched automatically in both the fields | Pass
7 | click on UOM dropdown, put the UOM | UOM dropdown should be clickable. user should able to put the UOM from dropdown. it should be a link field. | UOM is clickable and when user clicks on it a dropdown appears as expected where user can select a single option from it | Pass
8 | click on Packing Unit text field, fill it | user should able to fill Packing Unit text field Quantity that must be bought or sold per UOM | user is able to give input in packing unit but accepting -ve input | Fail |  | 27
9 | click on price list dropdown, select the price list | dropdown should be open. user should able to select the data . it should be a link field. after select the price list, supplier and currency field should be open automatic | when user clicks on price list a dropdown appears as expected and user can select a single option from it which is linked with the master price list and the moment user select a price list, Supplier and currency field gets visible | Pass
10 | click on supplier dropdown, select the supplier | dropdown should be open. user should able to select the data . it should be a link field. | when user clicks on supplier a dropdown appears as expected where user can select a single option and is linked with the master screen of supplier | Pass
11 | click on Batch No dropdown, select the Batch No | dropdown should be open. user should able to select the data . it should be a link field. | when user clicks on Batch No a dropdown appears as expected where user can select a single option and is linked with the Batch screen | Pass
12 | verify the currency field | currency field should be default as INR | yes currency field is default to INR which is read only and user is not able to change | Pass
13 | click on rate field, enter the value | user should able to put the value on rate field | user is able to click on the rate field and can give input but rate is accepting -ve value | Fail |  | 28
14 | click on Valid From date field, put the date | datepicker box should be open. user should able to put the date | when user clicks on Valid from field a datepicker calendar is open as expected and also user can enter the date maually in the defined format | Pass
15 | click on Valid upto date field, put the date | datepicker box should be open. user should able to put the date | when user clicks on Valid upto field a datepicker calendar is open as expected and also user can enter the date maually in the defined format | Pass
16 | click on note text area, enter the text | note text area should be clickable. user should able to enter data | user is clickable on the field and can give user input | Pass
17 | check if buying checkbox is read only | after selecting the price list the checkbox will auto-check or uncheck accordingly | when user select price list for buying then buying checkbox gets auto-checked which is read only | Pass
18 | check if Selling checkbox is read only | after selecting the price list the checkbox will auto-check or uncheck accordingly | when user select price list for selling then selling checkbox gets auto-checked which is read only | Pass
19 | click on Lead Time in days, fill it | user should able to click and give user input | user is able to click on the Lead Time in days but accepting -ve value | Fail |  | 29
20 | After fill all mandatory & required fields, click on save button | page should be saved successfully | page is saving with all the mandatory fields and required fields and it is reflecting in the list view as expected | Pass
21 | click on action button, click approve | page should be approved successfully as per user & roles | when purchase manager approves a particular item price then only action button gets visible to GM when GM logs In using his credentials as per workflow | Pass
| Roles And Permission |  | Actual Result | Status | Bug_ID
| Login as GM-Procurement & Contract Management and check the access privileges | The user should have all the following accesses: Select, Read,Write,Create & Delete | GM - Procurement & Contract management has Read, select, Write which is edit, create but cannot delete | Fail | 59
| Login as Purchase Manager and check the access privileges | The user should have all the following accesses: Select, Read,Write,Create & Delete | Purchase Manager has Read, select, Write which is edit, create but cannot delete | Fail | 59

## TC4_Price_List
Test Case ID | TC4_Price_List | Test Case Description | A Price List is a collection of Item Prices either Selling, Buying, or both.User maintain multiple Selling and Buying Item Prices using Price Lists.
Created By | Aman Kumar Singh | Reviewed By
S# | Pre-requisite |  | Test Data
1 | Currency |  | url: wscdemo.eduleadonline.com
Test Scenario | New Price List
Step No. | Step Description | Expected Result | Actual Results ( Hostel Administrator) | Pass/Fail/Not Executed/Suspended | Comment | Bug_ID
Home > Material Management > Items & Pricing > Price List
1 | Click on Home > Material Management > Items & Pricing > Price List | Price List page should be open | price list page is opening as expected | Pass
2 | View thePrice List page | saved data should be shown on Price List page | The saved data is visible in the list view of price list page as expected | Pass
3 | Click Add Price List button | Add Price List button should be clickable and new Price List page should be open | the button is clickable and New price list page is visible as expected | Pass
4 | Without fill any mandatory fields, click on save button | Page should not proceed. Alert message should be shown for unfilled mandatory fields. Mandatory fields should be mentioned as * symbol. | page is not procceding without filling mandatory fields and also alert message is thrown to fill mandatory fields as expected | Pass
5 | fill only mandatory fields, click on save button | Page should be saved successfully | yes saving as expected | Pass
6 | click on Price List Name text field, enter the name | Price List Name text field should be clickable. user should able to fill Price List Name | Price list name field is clickable as expected and user is able to fill the price list name | Pass
7 | click on currency dropdown. put the currency type | currency dropdown should be clickable, user should able to put the currency. it should be a link field | yes currency field is clickable which appears as a dropdown as expected and is default to INR which is linked with the currency but user can able to change as per their needs | Pass
8 | click on add row button of Applicable for Countries section | new row should be open. country column should be shown | Add row button is clickable and the new row is being inserted in the Applicable for Countries table & default values are being auto-fetched and also user can edit but throwing an alert message insufficient permission | Fail |  | 38
9 | click on buying checkbox | checkbox should be clickable. If checked then this price list will visible for buying transaction | yes buying chcekbox is clickable as expected and when user checked this checkbox then price list for buying will be applicable & visible in the transaction | Pass
10 | click on Price Not UOM Dependent checkbox | checkbox should be clickable. If checked then this price list is not dependent with UOM | Price Not UOM Dependent checkbox is clickable as expected and when checked then price list will not be dependent of UOM | Pass
11 | fill all mandatory and required fields, click on save button | page should be saved successfully | page is saving with all the mandatory fields and required fields and it is reflecting in the list view as expected | Pass
| Roles And Permission |  | Actual Result | Status | Bug_ID
| Login as GM-Procurement & Contract Management and check the access privileges | The user should have all the following accesses: Select, Read,Write,Create & Delete | GM - Procurement & Contract management has Read, select, Write which is edit, create but cannot delete | Fail | 59
| Login as Purchase Manager and check the access privileges | The user should have all the following accesses: Select, Read,Write,Create & Delete | Purchase Manager has Read, select, Write which is edit, create but cannot delete | Fail | 59