## Slide 1
Campus Management Application
At
World Skill Center
WEEKLY PROJECT STATUS REPORT
18-Aug-2023

## Slide 2: PROJECT SUMMARY
OVERALL PROJECT STATUS (R)ed, (A)mber, (G)reen | DELAY
PROJECT NAME | Campus Management Application At World Skill Center(WSC) |  | 
SOUL POC | sharmistha.panda@soulunileaders.com | WSC POC | 
PROJECT START DATE | 03-02-2023 | PROJECT END DATE | 03-02-2024
Red | Likely delay in overall project schedule | Amber | Some Activities are delayed | Green | On track

## Slide 3: TASKS PLANNED/ACCOMPLISHED THIS WEEK
TASKS |  |  | 
Description | Owner | Status | Remarks
Integration - Payment Gateway (HDFC) | SOUL - WSC | ON GOING | 11-Aug-23: Deployment to production server is complete but we are not getting the response from CCAvenue. We are in the process of checking the same Update: Development with testing completed by SOUL team. The details have been shared with HDFC team for their audit
Design phase | SOUL | ON GOING | 11-Aug-23: Finance and Accounting document has been shared with WSC IT team for review. WSC to intimate SOUL team if the documents have to be shared with module owners Update: HRMS design document review is being done. The final version along with other documents (Training and Placement, Infrastructure, Procurement, Finance) will shared with module owners for their sign off.

## Slide 4: TASKS PLANNED/ACCOMPLISHED THIS WEEK
TASKS |  |  | 
Description | Owner | Status | Remarks
Role permission template | SOUL | ON GOING | 28-Jul-23: WSC has shared HRMS roles permission. SLCM role permission is pending Update: WSC to share the SLCM role permission with SOUL team
Master data template for SLCM and HRMS | SOUL | ON GOING | 04-Aug-23: Meeting was held to clarify queries raised by WSC. The master data shall be shared by WSC in the upcoming week Update: SOUL team yet to receive the master data
SLCM (Admission, Academics, Examination) demonstration to WSC stakeholders | SOUL | DONE | On August 16 and 17, SOUL team demonstrated the SLCM (admission, academics, examination) module to WSC stakeholders

## Slide 5: OVERALL PROJECT PROGRESS TIMELINE

## Slide 6: ISSUES
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
A delay in discussing and capturing requirements | High | The revised project plan was discussed on 06-Apr, during weekly Project review meeting update : schedule has been reviwed with WSC stakeholders | WSC | OPEN | WSC stakeholders to acknowledge the delay | 
SOUL highlighted the addition to scope (change request) for the features that were discovered during the requirements study but were not specified in the request for proposal document | High | WSC stakeholders to acknowledge the change request | WSC | OPEN | The change requests will be acknowledged by WSC | Update: SOUL team sent an email to WSC to acknowledge the change reqests and the additional effort required for development. The change requests have been listed in Slide 8

## Slide 7: ISSUES
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
Availability of OCAC server | High | WSC stakeholder to ensure availability of the requested server version | WSC | OPEN | SOUL team has installed the application and database on the same server in the desktop version WSC to acknowledge the additional effort required (CR) to test the desktop version of the application | 

## Slide 8: CHANGE REQUESTS
Description | Module
Entrance Examination Process | Students Management
TrainingOfTrainers(TOT) | Students Management
Recruitment Process | Human Resources Management System
Employee Re-Engagement | Human Resources Management System
Testing effort for application installation in desktop version | OCAC Server
As discussed on 9th June 2023, the change requests Budget and Payroll have been removed from the the list

## Slide 9: UPCOMING WORK
WHAT’S NEXT |  |  | 
Description | Owner | Status | Remarks
HRMS - Demonstration to WSC Stakeholders | SOUL | OPEN | To be Scheduled
Continuation of the design phase - Design documentation | SOUL | OPEN | HRMS documentation will be shared.

## Slide 10
THANK YOU