## Pointers
No. of workflow | 7
Total No of forms | 7
Child forms | 6 + 1
Forms Schema
Validation
Logic
No. of Users
Design of Workflow

## MASTER_DOCTYPE
Forms | Child Forms | Field Type | Field Validation | Estimated hours | Person |  | Validations
1.1 Department: |  |  |  | 24
1. Department Name |  | Drop down |  |  |  |  | Migrating Department DocType from Erpnext/Frappe to our custom application The Department doctype is an essential part of setup for the application and we are going to borrow all its functionality from erpnext. It falls under the “Setup” module of erpnext. Fields Datatypes department_name Data parent_department Link / Department company Link / Company is_group Check disabled Check In order to construct the tree for the departments in the form of childs and parents we need to write code after creating the department_tree.js file. This js file will set up the parameters of the tree and invoke two definitions from the department.py file namely, get_children and add_node. Moreover, it will have filters based on company since there would be separate trees for separate companies. Also, wherever a new department is added, it will recognize its position on the tree based on the parameters (whether it is a child or a parent) and place it in the correct order. Next comes the department.js file where all the events of the doctype are written. This includes the onload, refresh and validate events. The onload event will set up a filter on the field parent_department so that only the parent departments appear in the list of options available to the user. The refresh event takes care of the fact that if there isn’t any pre-existing parent department, the parent department field will remain read only. This especially applies for the time when we first start to set up the application where there is no preexisting department. So the first department to be created should ideally be a parent department. The validate event oversees the fact that we should not be able to edit the root node(parent) if available. This comes down to the final file which contains most of the backend logic present in the department doctype which is the department.py file. At first, we start by importing the necessary definitions and libraries such as frappe, the class called NestedSet present in frappe.utils.nestedset to get the definition get_root_of, and the delete_events definition present in erpnext.utilities.transaction_base. The class Department which have several definitions which are as follows: Autoname Validate Before_rename On_update On_trash The definitions present outside the class are: On_doctype_update Get_abbreviated_name Get_children Add_node The definition ‘autoname’ will be used to generate the primary key / name of the department depending on the inputs given by the user. For example, if the input on the department_name is “Consulting” and the name of the underlying company is ‘SOUL’, the department’s name will be set to “Consulting - SOUL”. The definition ‘validate’ will be used to get the root of a department each time a department is added to the database. First will first check if the department added is a parent and if not it will add the department under a particular parent mentioned by the user or it will assign the department to the topmost parent on the tree. The definition ‘before_rename’ will get the value of the company abbreviation mentioned by the user and pass it onto the autoname definition to enable the construction of the primary key of the record entered. The ‘on_trash’ definition will ensure that the department is deleted properly from the database as well as the tree view. The ‘get_children’ definition is called by the department_tree.js as mentioned earlier to all the records of all the departments which fall under a parent department, another parent department falling under the previous parent department which also has children and so on. Similar to the ‘get_children’ definition, the ‘add_node’ definition is also called by the department_tree.js which imports the treeview from frappe.desk.treeview and the function called make_tree_args takes the arguments for the treeview and forms a tree in the frontend. Whenever a new record is created, the tree is updated accordingly.
2. Department Abbr.
3. Company
4. Parent Department
5. Is Group (checklist)
6. Is Stream (checklist)
7. Disabled (checklist)
8. Shift Request Approver (Child Table) ---> Approver & Period(Start Date and End Date)
1.2 Supplier Group: |  |  |  | 1
1. Supplier Group Name | [6 empty] | Functionality For grouping of supplier
1.3 Supplier: |  |  |  | 6
Name and Type | [6 empty] | Functionality 1)As a user I should able create Supplier
1. Supplier Name
2. Supplier Group
3. Country
4. Supplier Type -> Company & Individual (Note: When we choose ‘Company then Company Field going to fetch.
5. GST No.
6. PAN No.
Primary Address and Contact Detail
7. Supplier Primary Contact
8. Supplier Primary Address
9. Mobile No.
10. Email Id
More Information
11. Website
12. Print Language
13. Supplier Details
1.4 Employee List |  |  |  | 26
1. First Name | [6 empty] | Functionality 1)Email id should be unique per employee 2)As employee is created user should be created automatically 3)When employee is disabled if user automatically get disabled. 4)Email id is changed it should automatically get updated in user 5)Password can be change form the employee Reset password link can be generated from emp doc
2. Middle Name
3. Last Name
4. Salutation(drop down)
a) Dr
b) Madam
c) Master
d) Miss
e) Mr
f) Mrs
g) Ms
h) MX
i) Prof
5. Full Name
6. Employment Type (drop down)
a) Apprentice
b) Intern
c) Piecework
d) Commission
e) Contract
f) Probation
g) Part-time
h) Full-time
7. Company
8. Status
9. Gender (drop down)
a) Male
b) Female
c) Other
10. Date of Birth
11. Date of Joining
12. Employee Number
Emergency Contact
13. Emergency Contact Name
14. Emergency Phone
15. Relation
ERPNext User
16. User ID
17. Create User Permission (checklist)
18. Create User (button)
Department and Grade
19. Department
20. Designation
21. Reports to
22. Grade
23. Branch
24. Role Profile
25. Signature
1.8 Company |  |  |  | 1
1. Company
2. Company Address
1.9 Material/Service Group |  |  |  | 1
1. Material type/Service type
1.10 Material/Service |  |  |  | 1
1. Material/Service Code | [6 empty] | Functionality 1)As a user I should able create Material
2. Material/Service Name
3. Manufacturer
4. Manufacturer Email
5. Material/Service Group
6. Serial Number
7. Mac Id
8. Warrant Period
9. Warranty Ends on
1.12 Role Permission Creation |  |  |  | 10
1.13 User Creation |  |  |  | 10
1.14 User Permission |  |  |  | 14 |  |  | Functionality 1)Department wise role and permission should be given to the employee
1.15 Workspace Creation |  |  |  | 1
1.16 Testing |  |  |  | 30
Total Hours |  |  |  | 95 |  | 11.875
|  |  |  | 280 |  | 35

## PO_CONSUMABLE
A) | DOCTYPE HEADER
| FIELD NAME | FIELD TYPE | MANDATORY | OPTIONS | ESTIMATION (in Hrs) | 16
1 | Company | Link Field | Y | Company
2 | Note Sheet No. | Data Field | Y
3 | Date Of Note Sheet | Date | Y
4 | Name Of School/Department | Link Field | Y | Department
5 | For which Department | Link Field | Y | Department
6 | Item Of Purchase/Expense | Link Field | Y | Item
7 | Item Name | Data Field | Y
8 | Supplier Code | Link Field | Y | Supplier
9 | Name Of Supplier | Data Field | Y
10 | Amount Clearance Period (in Days) | Int | Y
11 | Priority | Drop Down Urgent High Priority Normal Low Priority | Y
12 | Master Invoice Attachment | Attachment | N
13 | Note sheet Attachment | Attachment | N
B) | Details of Invoices & PO (CHILD DOCTYPE)
1 | Details of Invoices & P.O. | Data Field | Y
2 | Sl.No. | Auto Fill | Y
3 | Invoice No. | Data Field | Y
4 | Invoice Date | Date | Y
5 | Invoices Amount(in Rs) | Currency Field | Y
6 | P.O. No. | Data Field | Y
7 | Invoice Attachment | Attachment | Y
8 | PO | Attachment | Y
9 | Delivery Challan | Attachment | N
10 | Bill Summary | Attachment | N
11 | Credit Memo | Attachment | N
12 | GRN | Attachment | N
13 | Others | Attachment | N
C) | DOCTYPE FOOTER
10 | Total Amount (IN Rs.) | Currency Field | Y
11 | TDS Amount To Be Deducted (In Rs.) | Currency Field | N
12 | Advance Amount Already Paid (In Rs.) | Currency Field | N
13 | Net Final Amount To Be Paid (In Rs.) | Currency Field | N
D) | Authorized Signature Child doctype
1 | Sl NO. | Auto Fill | Y
2 | Emp ID | Link Field | Y | Employee
3 | Emp Name | Data Field | Y
4 | Designation | Data Field | Y
5 | Date of Approval | Date | Y
6 | Date of Receivable | Date | Y
7 | Approval Status | Data Field | Y
8 | Remarks | Data Field | N
9 | Department | Link Field | Y | Department
Total = 16
Functionality
1) Approval of the note-sheet will follow workflow as per the not-sheet.
2) On each approval Authorized Signature Child doctype should be filled.
3) On rejection user should be select which level of workflow it should be send for verification.
4) Mail should be send to the supplier when user receivers the invoice.
5) 10 days before the thrash hold payment date if payment is not cleared to all the user of the workflow.
6) When payment is processed and payment is done supplied will receive mail of confirmation of payment.
7) At any level user can edit the note-sheet.
8) If a user approve/rejects the note-sheet he/she can’t edit the note sheet till it comes for again for approval.
9) Total amount to be calculated form the note- sheet form child doctype.

## PO_MM
A) | DOCTYPE HEADER
| FIELD NAME | FIELD TYPE | MANDATORY | OPTIONS | ESTIMATION (in Hrs) | 16
1 | Company | Link Field | Y | Company
2 | Note Sheet No. | Data Field | Y
3 | Date Of Note Sheet | Date | Y
4 | Name Of School/Department | Link Field | Y | Department
5 | For which Department | Link Field | Y | Department
6 | Item Of Purchase/Expense | Link Field | Y | Item
7 | Item Name | Data Field | Y
8 | Supplier Code | Link Field | Y | Supplier
9 | Name Of Supplier | Data Field | Y
10 | Amount Clearance Period (in Days) | Int | Y
11 | Priority | Drop Down Urgent High Priority Normal Low Priority | Y
12 | Master Invoice Attachment | Attachment | N
13 | Note sheet Attachment | Attachment | N
B) | Details of Invoices & PO (CHILD DOCTYPE)
1 | Sl.No. | Auto Fill | Y
2 | Invoices No. | Data Field | Y
3 | Invoices Date | Date | Y
4 | Invoices Amount(in Rs) | Currency Field | Y
5 | P.O. No. | Data Field | Y
6 | P.O. Date | Date | Y
7 | Vendor Code | Link Field | Y | Supplier
8 | Invoice Attachment | Attachment | Y
9 | PO | Attachment | Y
10 | Delivery Challan | Attachment | N
11 | Bill Summary | Attachment | N
12 | Credit Memo | Attachment | N
13 | GRN | Attachment | N
14 | Others | Attachment | N
C) | DOCTYPE FOOTER
10 | Total Amount (IN Rs.) | Currency Field | Y
11 | TDS Amount To Be Deducted (In Rs.) | Currency Field | N
12 | Advance Amount Already Paid (In Rs.) | Currency Field | N
13 | Net Final Amount To Be Paid (In Rs.) | Currency Field | N
D) | Authorized Signature Child doctype
1 | Sl NO. | Auto Fill | Y
2 | EMP ID | Link Field | Y | Employee
3 | Emp Name | Data Field | Y
4 | Designation | Data Field | Y
5 | Date of Approval | Date | Y
6 | Date of Receivable | Date | Y
7 | Approval Status | Data Field | Y
8 | Remarks | Data Field | N
9 | Department | Link Field | Y | Department
Functionality
1) Approval of the note-sheet will fellow workflow as per the not-sheet.
2) On each approval Authorized Signature Child doctype should be filled.
3) On rejection user should be select which level of workflow it should be send for verification.
4) Mail should be send to the supplier when user receivers the invoice.
5) 10 days before the thrash hold payment date if payment is not cleared to all the user of the workflow.
6) When payment is processed and payment is done supplied will receive mail of confirmation of payment.
7) At any level user can edit the note-sheet.
8) If a user approve/rejects the note-sheet he/she can’t edit the note sheet till it comes for again for approval.
9) Total amount to be calculated form the note- sheet form child doctype.

## PO_CONSIGNMENT
A) | DOCTYPE HEADER
| FIELD NAME | FIELD TYPE | MANDATORY | OPTIONS | ESTIMATION (in Hrs) | 16
1 | Company | Link Field | Y | Company
2 | Note Sheet No. | Data Field | Y
3 | Date Of Note Sheet | Date | Y
4 | Name Of School/Department | Link Field | Y | Department
5 | For which Department | Link Field | Y | Department
6 | Item Of Purchase/Expense | Link Field | Y | Item
7 | Item Name | Data Field | Y
8 | Supplier Code | Link Field | Y | Supplier
9 | Name Of Supplier | Data Field | Y
10 | Amount Clearance Period (in Days) | Int | Y
11 | Priority | Drop Down Urgent High Priority Normal Low Priority | Y
12 | Master Invoice Attachment | Attachment | N
13 | Note sheet Attachment | Attachment | N
B) | Details of Invoices, Credit Note & PO (CHILD DOCTYPE)
1 | Sl.No. | Auto Fill | Y
2 | INV. NO. | Data Field | Y
3 | INVOICE DATE | Date | Y
4 | DOCUMENT RECEIVING DATE | Date | Y
5 | INVOICE AMOUNT | Currency | Y
6 | HOSPITAL MARGIN NOTE NO. | Data Field | Y
7 | HOSPITAL MARGIN NOTE DATE | Date | Y
8 | HOSPITAL MARGIN AMOUNT | Currency | Y
9 | TO-PAY | Data Field | Y
10 | PATIENT NAME | Data Field | Y
11 | MRN NO. | Data Field | Y
12 | Document No. | Data Field | Y
13 | Document Date | Date | Y
14 | Vendor code | Link Field | Y | Supplier
15 | Invoice Attachment | Attachment | Y
16 | PO | Attachment | Y
17 | Delivery Challan | Attachment | N
18 | Bill Summary | Attachment | N
19 | Credit Memo | Attachment | N
20 | GRN | Attachment | N
21 | Others | Attachment | N
C) | DOCTYPE FOOTER
10 | Total Amount (IN Rs.) | Currency | Y
11 | Less Credit Note Amount (IN Rs.) | Currency | N
12 | Net Final Amount To Be Paid (In Rs.) | Currency | N
D) | Authorized Signature Child doctype
1 | Sl NO. | Auto Fill | Y
2 | EMP ID | Link Field | Y | Employee
3 | Emp Name | Data Field | Y
4 | Designation | Data Field | Y
5 | Date of Approval | Date | Y
6 | Date of Receivable | Date | Y
7 | Approval Status | Data Field | Y
8 | Remarks | Data Field | N
9 | Department | Link Field | Y | Department
Functionality
1) Approval of the note-sheet will fellow workflow as per the not-sheet.
2) On each approval Authorized Signature Child doctype should be filled.
3) On rejection user should be select which level of workflow it should be send for verification.
4) Mail should be send to the supplier when user receivers the invoice.
5) 10 days before the thrash hold payment date if payment is not cleared to all the user of the workflow.
6) When payment is processed and payment is done supplied will receive mail of confirmation of payment.
7) At any level user can edit the note-sheet.
8) If a user approve/rejects the note-sheet he/she can’t edit the note sheet till it comes for again for approval.
9) Total amount to be calculated form the note- sheet form child doctype.

## NON PO _ CONTRACT
A) | DOCTYPE HEADER
| FIELD NAME | FIELD TYPE | MANDATORY | OPTIONS | ESTIMATION (in Hrs) | 16
1 | Company | Link Field | Y | Company
2 | Note Sheet No. | Data Field | Y
3 | Date Of Note Sheet | Date | Y
4 | Name Of School/Department | Link Field | Y | Department
5 | For which Department | Link Field | Y | Department
6 | Item Of Purchase/Expense | Link Field | Y | Item
7 | Item Name | Data Field | Y
8 | Supplier Code | Link Field | Y | Supplier
9 | Name Of Supplier | Data Field | Y
10 | Amount Clearance Period (in Days) | Int | Y
11 | Priority | Drop Down Urgent High Priority Normal Low Priority | Y
12 | Purchase Order No | Data Field | N
13 | Date of Purchase Order | Date | N
14 | Master Invoice Attachment | Attachment | N
15 | Note sheet Attachment | Attachment | N
B) | Details of Enclosed Bills (CHILD DOCTYPE)
1 | Sl.No. | Auto Fill | Y
2 | INV. NO. | Data Field | Y
3 | INVOICE DATE | Date | Y
5 | INVOICE AMOUNT | Currency | Y
6 | Vendor code | Link Field | Y | Supplier
7 | Remarks, If Any | Data Field | Y
8 | Invoice Attachment | Attachment | Y
9 | PO | Attachment | Y
10 | Delivery Challan | Attachment | N
11 | Bill Summary | Attachment | N
12 | Credit Memo | Attachment | N
13 | GRN | Attachment | N
14 | Others | Attachment | N
C) | DOCTYPE FOOTER
10 | Total Amount (IN Rs.) | Currency | Y
11 | TDS Amount To Be Deducted (In Rs.) | Currency | N
12 | Advance Amount Already Paid (In Rs.) | Currency | N
13 | Net Final Amount To Be Paid (In Rs.) | Currency | N
D) | Authorized Signature Child doctype
1 | Sl NO. | Auto Fill | Y
2 | EMP ID | Link Field | Y | Employee
3 | Emp Name | Data Field | Y
4 | Designation | Data Field | Y
5 | Date of Approval | Date | Y
6 | Date of Receivable | Date | Y
7 | Approval Status | Data Field | Y
8 | Remarks | Data Field | N
9 | Department | Link Field | Y | Department
Functionality
1) Approval of the note-sheet will fellow workflow as per the not-sheet.
2) On each approval Authorized Signature Child doctype should be filled.
3) On rejection user should be select which level of workflow it should be send for verification.
4) Mail should be send to the supplier when user receivers the invoice.
5) 10 days before the thrash hold payment date if payment is not cleared to all the user of the workflow.
6) When payment is processed and payment is done supplied will receive mail of confirmation of payment.
7) At any level user can edit the note-sheet.
8) If a user approve/rejects the note-sheet he/she can’t edit the note sheet till it comes for again for approval.
9) Total amount to be calculated form the note- sheet form child doctype.

## NON PO _ NON-CONTRACT
A) | DOCTYPE HEADER
| FIELD NAME | FIELD TYPE | MANDATORY | OPTIONS | ESTIMATION (in Hrs) | 16
1 | Company | Link Field | Y | Company
2 | Note Sheet No. | Data Field | Y
3 | Date Of Note Sheet | Date | Y
4 | Name Of School/Department | Link Field | Y | Department
5 | For which Department | Link Field | Y | Department
6 | Item Of Purchase/Expense | Link Field | Y | Item
7 | Item Name | Data Field | Y
8 | Supplier Code | Link Field | Y | Supplier
9 | Name Of Supplier | Data Field | Y
10 | Amount Clearance Period (in Days) | Int | Y
11 | Priority | Drop Down Urgent High Priority Normal Low Priority | Y
12 | Purchase Order No | Data Field | N
13 | Date of Purchase Order | Date | N
14 | Master Invoice Attachment | Attachment | N
15 | Note sheet Attachment | Attachment | N
B) | Details of Enclosed Bills (CHILD DOCTYPE)
1 | Sl.No. | Auto Fill | Y
2 | INV. NO. | Data Field | Y
3 | INVOICE DATE | Date | Y
4 | INVOICE AMOUNT | Currency | Y
5 | Remarks, If Any | Data Field | Y
6 | Invoice Attachment | Attachment | Y
7 | PO | Attachment | Y
8 | Delivery Challan | Attachment | N
9 | Bill Summary | Attachment | N
10 | Credit Memo | Attachment | N
11 | GRN | Attachment | N
12 | Others | Attachment | N
C) | DOCTYPE FOOTER
10 | Total Amount (IN Rs.) | Currency | Y
11 | TDS Amount To Be Deducted (In Rs.) | Currency | N
12 | Advance Amount Already Paid (In Rs.) | Currency | N
13 | Net Final Amount To Be Paid (In Rs.) | Currency | N
D) | Authorized Signature Child doctype
1 | Sl NO. | Auto Fill | Y
2 | EMP ID | Link Field | Y | Employee
3 | Emp Name | Data Field | Y
4 | Designation | Data Field | Y
5 | Date of Approval | Date | Y
6 | Date of Receivable | Date | Y
7 | Approval Status | Data Field | Y
8 | Remarks | Data Field | N
9 | Department | Link Field | Y | Department
Functionality
1) Approval of the note-sheet will fellow workflow as per the not-sheet.
2) On each approval Authorized Signature Child doctype should be filled.
3) On rejection user should be select which level of workflow it should be send for verification.
4) Mail should be send to the supplier when user receivers the invoice.
5) 10 days before the thrash hold payment date if payment is not cleared to all the user of the workflow.
6) When payment is processed and payment is done supplied will receive mail of confirmation of payment.
7) At any level user can edit the note-sheet.
8) If a user approve/rejects the note-sheet he/she can’t edit the note sheet till it comes for again for approval.
9) Total amount to be calculated form the note- sheet form child doctype.

## OTHERS
A) | PHARMACY (DOCTYPE HEADER)
| FIELD NAME | FIELD TYPE | MANDATORY | OPTIONS | ESTIMATION (in Hrs) | 16
1 | Company | Link Field | Y | Company
2 | Note Sheet No. | Data Field | Y
3 | Date Of Note Sheet | Date | Y
4 | Name Of School/Department | Link Field | Y | Department
5 | For which Department | Link Field | Y | Department
6 | Item Of Purchase/Expense | Link Field | Y | Item
7 | Item Name | Data Field | Y
8 | Supplier Code | Link Field | Y | Supplier
9 | Name Of Supplier | Data Field | Y
10 | Amount Clearance Period (in Days) | Int | Y
11 | Priority | Drop Down Urgent High Priority Normal Low Priority | Y
12 | Purchase Order No | Data Field | N
13 | Date of Purchase Order | Date | N
14 | Master Invoice Attachment | Attachment | N
15 | Note sheet Attachment | Attachment | N
Functionality
B) | Details of Enclosed Bills (CHILD DOCTYPE) | [5 empty] | 1) Approval of the note-sheet will fellow workflow as per the not-sheet.
1 | Sl.No. | Auto Fill | Y |  |  |  | 2) On each approval Authorized Signature Child doctype should be filled.
2 | Vendor Invoice No | Data Field | Y |  |  |  | 3) On rejection user should be select which level of workflow it should be send for verification.
3 | Vendor Invoice Date | Date | Y |  |  |  | 4) Mail should be send to the supplier when user receivers the invoice.
4 | Vendor Invoice Value | Currency | Y |  |  |  | 5) 10 days before the thrash hold payment date if payment is not cleared to all the user of the workflow.
5 | Remarks, If Any | Data Field | N |  |  |  | 6) When payment is processed and payment is done supplied will receive mail of confirmation of payment.
6 | Invoice Attachment | Attachment | Y |  |  |  | 7) At any level user can edit the note-sheet.
7 | PO | Attachment | Y
8 | Delivery Challan | Attachment | N
9 | Bill Summary | Attachment | N
10 | Credit Memo | Attachment | N
11 | GRN | Attachment | N
12 | Others | Attachment | N
9) Total amount to be calculated form the note- sheet form child doctype.
C) | DOCTYPE FOOTER
10 | Total Amount | Currency
11 | Credit Note Attached
12 | Advance Amount Already Paid (In Rs.) | Currency
13 | Net Final Amount To Be Paid (In Rs.) | Currency
D) | Authorized Signature Child doctype
1 | Sl NO. | Auto Fill | Y
2 | EMP ID | Link Field | Y | Employee
3 | Emp Name | Data Field | Y
4 | Designation | Data Field | Y
5 | Date of Approval | Date | Y
6 | Date of Receivable | Date | Y
7 | Approval Status | Data Field | Y
8 | Remarks | Data Field | N
9 | Department | Link Field | Y | Department
PATIENT REFUND
A) | DOCTYPE HEADER | FIELD TYPE | MANDATORY | OPTIONS | ESTIMATION (in Hrs) | 16
1 | Name of the Patient | Data Field | Y
2 | IP / UHID No. | Data Field | Y
3 | Department | Data Field | Y
4 | Total Bill | Currency | Y |  |  |  |  | Functionality
5 | Approval of TPA / Insurance / Corporate / OSTF | Data Field | N |  |  |  |  | 1) Approval of the note-sheet will fellow workflow as per the not-sheet.
6 | Amount Deposited By patient | Currency | Y |  |  |  |  | 2) On each approval Authorized Signature Child doctype should be filled.
7 | Less : Approval (Approval letter to be attached) | Attachment | N |  |  |  |  | 3) On rejection user should be select which level of workflow it should be send for verification.
8 | Approval Attachment | Attachment | N |  |  |  |  | 4) Mail should be send to the supplier when user receivers the invoice.
9 | Cash Refund | Currency | N |  |  |  |  | 5) 10 days before the thrash hold payment date if payment is not cleared to all the user of the workflow.
10 | Less : Non-admissible item / Discount amount | Currency | N |  |  |  |  | 6) When payment is processed and payment is done supplied will receive mail of confirmation of payment.
11 | Net Refundable (in figures) | Currency | Y |  |  |  |  | 7) At any level user can edit the note-sheet.
12 | Net Refundable (in words) | Data Field | Y |  |  |  |  | 8) If a user approve/rejects the note-sheet he/she can’t edit the note sheet till it comes for again for approval.
13 | Remarks | Data Field | Y |  |  |  |  | 9) Total amount to be calculated form the note- sheet form child doctype.
14 | Mode of Payment | Drop Down RTGS - UTR , Date of Transaction NEFT - UTR, Date of Transaction IMPS - UTR, Date of Transaction Cheque - Cheque No. , Date of Transaction Cash - Cash Receipt No., Date of Transaction | N
DOCTYPE FOOTER
15 | Patient IP No | Data Field | Y
16 | Patient's Name | Data Field | Y
17 | Amount Deposited | Currency | N
18 | Amount Deposited Through |  | N
19 | Date of Submission of Fees | Date | N
20 | Date of Cancellation | Date | N
21 | Reason of Cancellation | Data Field | N
22 | Account Type | Data Field | N
23 | ACCOUNT HOLDER NAME | Data Field | Y
24 | JOINT ACCOUNT HOLDER NAME | Data Field | N
25 | NAME OF THE BANK | Data Field | Y
26 | BRANCH | Data Field | Y
27 | IFSC CODE | Data Field | Y
28 | ACCOUNT NO | Data Field | Y
29 | ACCOUNT HOLDER RELATION WITH THE PATIENT | Data Field | Y
30 | Documents to be attached with Cancellation / Refund Application form | Attachment
31 | Original Money Receipt | Attachment
32 | Xerox Copy of any itenty Proof | Attachment
Authorized Signature Child doctype
1 | Sl NO. | Auto Fill | Y
2 | EMP ID | Link Field | Y | Employee
3 | Emp Name | Data Field | Y
4 | Designation | Data Field | Y
5 | Date of Approval | Date | Y
6 | Date of Receivable | Date | Y
7 | Approval Status | Data Field | Y
8 | Remarks | Data Field | N
9 | Department | Link Field | Y | Department
Attachments
1 | Patient Cancellation / Refund application Form | Y
2 | Self declaration form | N
3 | Refund sheet | Y
4 | Final Bill | N
5 | Refund Receipt | Y
6 | Insurance Document | Y
7 | Self identification document which should have photo (like Aadhar, Pan card,etc) | Y

## Payment Workflow
A) | DOCTYPE HEADER
| FIELD NAME | FIELD TYPE | MANDATORY | OPTIONS | ESTIMATION (in Hrs) | 32
1 | Company | Link | Y | Company
2 | Document Status | Data | N
3 | Account Section | Section break | N
4 | Account Reference No | Data | Y
5 | Account Post Date | Date | Y
6 | Paying Bank | Link | N | Bank Details For Payment
7 | Bank A/C No | Data | N
8 | Branch Details | Data | N
9 | Bank Name | Data | N
10 | IFSC Code | Data | N
11 | Audit Section | Section break | N
12 | Audit Reference No | Data | N
13 | Audit Posting Date | Date | N
14 | Cheque Details Section | Section break | N
15 | Cheque No | Data | N
16 | Cheque Date | Date | N
17 | Amount | Currency | N
18 | Cheque Attachment | Attach | N
19 | Note Sheet Attachment | Attach | N
20 | Contact Person | Link | Y | Employee
21 | Contact Phone No | Data | N
22 | Contact Email Id | Data | N
23 | Batch Payment Child | Table | N | Batch Payment Child
24 | Approval Hierarchy | Section break | N
25 | Approval Hierarchy | Table | N | Authorized Signature
B) | CHILD DOCTYPE
1 | Invoice tracking number | Data Field | N
2 | Document Date | Date | Y
3 | Vendor Code | Data Field | Y
4 | Vendor Name | Data Field | Y
5 | IFSC Code | Data Field | Y
6 | A/C No. | Data Field | N
7 | Amount | Currency | N
8 | Amount | Currency | N
9 | SAP document number | Data Field | N
10 | Mode of Payment | Data Field | N
11 | UTR Number | Data Field | N
C) | Authorized Signature Child doctype
1 | Sl NO. | Auto Fill | Y
2 | EMP ID | Link Field | Y | Employee
3 | Emp Name | Data Field | Y
4 | Designation | Data Field | Y
5 | Date of Approval | Date | Y
6 | Date of Receivable | Date | Y
7 | Approval Status | Data Field | Y
8 | Remarks | Data Field | N
9 | Department | Link Field | Y | Department
D) | Filter of Invoices will be based on
1 | Posting Date | Label
| Start Date | Date
| End Date | Date
2 | Type of Invoice | Select |  | Consumable, Consignment, Equipment, Non PO Contract, Non PO Non Contract, Pharmacy, Patient refund, All
3 | Clearing Amount | Label
| Greater than amount | Float
| Less than amount | Float
4 | Vendor | Link |  | Supplier
5 | Priority | Select |  | Urgent, Non Urgent
* | Only Invoice with Workflow state Process for Payment should appear when get invoice is selected

## Estimation
R&D 1. for the Reject Workflow 2. Password Change from Employee Doctype | 40
Doctype | 112
Master Doctype | 95
| 247 | 30.875
|  |  | TASK | Concerned Team | Resource 1 | Resource 2 | Resource 3
|  |  | Business Requirment Analysis | 32
|  |  | High Level Requirement Document | 12
|  |  | Design Document | 16
|  |  | Company |  | 1
|  |  | Department |  |  | 24
|  |  | Employee |  | 26
|  |  | Item & Item Group |  |  | 2
|  |  | Supplier & Supplier Group |  |  | 7
|  |  | PO_CONSUMABLE |  | 16
|  |  | PO_MM |  |  |  | 16
|  |  | PO_CONSIGNMENT |  |  | 16
|  |  | NON PO _ CONTRACT |  | 16
|  |  | NON PO _ NON-CONTRACT |  |  |  | 16
|  |  | PHARMACY |  |  | 16
|  |  | PATIENT REFUND |  | 16
|  |  | Role Permission |  |  |  | 10
|  |  | User Creation |  |  | 10
|  |  | User Permission |  | 14
|  |  | Workspace Creation |  |  |  | 1
|  |  | Unit Testing |  | 10 | 10 | 10
System Testing (Writing of Test Cases, Test Execution)
|  |  |  | 60 | 99 | 85 | 53
297
37.125

## R&D
Sl No. | Task | Person Assigned
1 | Reject Workflow
2 | Password Change from Employee Doctype
3 | File upload on the server | Subhodeep

## Plan
Task | Task type |  | Total no. of hours | Resource working | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Status | Comments
Requirement Analysis |  |  | 32 | Sharmistha | 2022-10-31 | 2022-11-03 | 2022-10-19 | 2022-11-15 | Completed
Design |  |  | 28 | Priytesh | 2022-10-31 | 2022-11-03 |  |  | Completed
Business Requirement Document |  |  | 24 | Sharmistha | 2022-10-31 |  | 2022-10-31 | 22-12-2022 | Completed | 07/12 - Again updated the req document for Email and third party 12/12 - Update of Req document for Patient Refund 13/12 - Updated the requirement doc for Invoice form, Dashboard 14/12 - formatting, section numbers, print format 22/12 - updated document for PRO VC workflow , Invoice Form UI, user permission tools, employee absent screen, Reports, Role permission tool
High Level Functional Document | Invoice Workflow Print Format Email Notifications Dashboard / Report |  | 24 | Sharmistha | 2022-11-03 | 2022-11-07 | 2022-11-03 | 2022-11-08 | Completed | Did not work on 4th Nov
Master Doctypes | Company |  | 1 | Nehal | 2022-10-31 | 2022-11-02 |  | 2022-10-28 | Completed
| Department |  | 24 | Subhodeep | 2022-10-31 | 2022-11-02 |  | 2022-10-28 | Completed
| Employee |  | 26 | Nehal | 2022-10-31 | 2022-11-04 |  | 2022-10-31 | Completed
| Item & Item Group |  | 2 | Priytesh | 2022-10-31 | 2022-11-04 |  | 2022-10-28 | Completed
| Supplier & Supplier Group |  | 7 | Priytesh | 2022-10-31 | 2022-11-04 |  | 2022-10-28 | Completed
| Bank Details for Payment | [7 empty] | Completed
Invoice | PO_CONSUMABLE | Doctype Creation | 2 | Nehal | 2022-11-01 | 2022-11-01 | 2022-11-01 | 2022-11-01 | Completed
|  | Workflow Creation(Worfklow state, Action, Transition rules) | 6 | Nehal | 2022-11-01 | 2022-11-01 | 2022-11-01 | 2022-11-01 | Completed
|  | Child doctype Calculation(Total, Grand total) | 4 | Nehal | 2022-11-02 | 2022-11-02 | 2022-11-02 | 2022-11-02 | Completed
|  | Cancellation and Transfer to authority within workflow | 8 | Abhishek, Nehal | 2022-11-02 | 2022-11-03 | 2022-11-02 | 2022-11-03 | Completed
|  | Populating childdoctype with workflow history | 10 | Abhishek, Nehal | 2022-11-02 | 2022-11-03 | 2022-11-02 | 2022-11-03 | Completed
|  | Front End Validation(Display and Mandatory depends on) | 2 | Nehal | 2022-11-03 | 2022-11-03 | 2022-11-03 | 2022-11-03 | Completed
|  | Print Format | 8 | Subhodeep | 2022-11-03 | 2022-11-03 | 2022-11-03 | 2022-11-03 | Completed
| PO_MM | Doctype Creation | 2 | Nehal | 2022-11-04 | 2022-11-04 | 2022-11-04 | 2022-11-04 | Completed
|  | Workflow Creation(Worfklow state, Action, Transition rules) | 2 | Nehal | 2022-11-04 | 2022-11-04 | 2022-11-04 | 2022-11-04 | Completed
|  | Child doctype Calculation(Total, Grand total) | 2 | Nehal | 2022-11-04 | 2022-11-04 | 2022-11-04 | 2022-11-04 | Completed
|  | Cancellation and Transfer to authority within workflow | 4 | Nehal | 2022-11-04 | 2022-11-07 | 2022-11-07 | 2022-11-07 | Completed
|  | Populating childdoctype with workflow history | 4 | Nehal | 2022-11-07 | 2022-11-07 | 2022-11-04 | 2022-11-07 | Completed
|  | Front End Validation(Display and Mandatory depends on) | 2 | Nehal | 2022-11-07 | 2022-11-07 | 2022-11-04 | 2022-11-04 | Completed
|  | Print Format | 8 | Nehal | 2022-11-08 | 2022-11-08 | 2022-11-07 | 2022-11-08 | Completed
|  | Add Debit Note Attachment field along with the print format (inside child table) |  | Subhodeep | 2022-12-19 | 2022-12-19 | 2022-12-19 | 2022-12-19 | Completed | Task was part of 9th Dec 2022 discussion
| PO_CONSIGNMENT | Doctype Creation | 2 | Subhodeep | 2022-11-04 | 2022-11-04 | 2022-11-07 | 2022-11-07 | Completed
|  | Workflow Creation(Worfklow state, Action, Transition rules) | 2 | Subhodeep | 2022-11-04 | 2022-11-04 | 2022-11-07 | 2022-11-07 | Completed
|  | Child doctype Calculation(Total, Grand total) | 2 | Subhodeep | 2022-11-04 | 2022-11-04 | 2022-11-07 | 2022-11-07 | Completed
|  | Cancellation and Transfer to authority within workflow | 4 | Subhodeep | 2022-11-04 | 2022-11-07 | 2022-11-07 | 2022-11-07 | Completed
|  | Populating childdoctype with workflow history | 4 | Subhodeep | 2022-11-07 | 2022-11-07 | 2022-11-07 | 2022-11-07 | Completed
|  | Front End Validation(Display and Mandatory depends on) | 2 | Subhodeep | 2022-11-07 | 2022-11-07 | 2022-11-08 | 2022-11-08 | Completed
|  | Print Format | 8 | Subhodeep | 2022-11-08 | 2022-11-08 | 2022-11-08 | 2022-11-08 | Completed
| NON PO _ CONTRACT | Doctype Creation | 2 | Nehal | 2022-11-09 | 2022-11-09 | 2022-11-08 | 2022-11-08 | Completed
|  | Workflow Creation(Worfklow state, Action, Transition rules) | 2 | Nehal | 2022-11-09 | 2022-11-09 | 2022-11-08 | 2022-11-08 | Completed
|  | Child doctype Calculation(Total, Grand total) | 2 | Nehal | 2022-11-09 | 2022-11-09 | 2022-11-08 | 2022-11-08 | Completed
|  | Cancellation and Transfer to authority within workflow | 4 | Nehal | 2022-11-09 | 2022-11-10 | 2022-11-08 | 2022-11-08 | Completed
|  | Populating childdoctype with workflow history | 4 | Nehal | 2022-11-10 | 2022-11-10 | 2022-11-08 | 2022-11-09 | Completed
|  | Front End Validation(Display and Mandatory depends on) | 2 | Nehal | 2022-11-10 | 2022-11-10 | 2022-11-09 | 2022-11-09 | Completed
|  | Print Format | 8 | Nehal | 2022-11-11 | 2022-11-11 | 2022-11-09 | 2022-11-10 | Completed
| NON PO _ NON-CONTRACT Employee to be added as a supplier for employee reiumbursement. In Batch Payment Process the same will be applicable Also apply filter for employee and supplier accordingly. | Doctype Creation | 2 | Subhodeep | 2022-11-09 | 2022-11-09 | 2022-11-09 | 2022-11-09 | Completed
|  | Workflow Creation(Worfklow state, Action, Transition rules) | 2 | Subhodeep | 2022-11-09 | 2022-11-09 | 2022-11-09 | 2022-11-09 | Completed
|  | Child doctype Calculation(Total, Grand total) | 2 | Subhodeep | 2022-11-09 | 2022-11-09 | 2022-11-09 | 2022-11-09 | Completed
|  | Cancellation and Transfer to authority within workflow | 4 | Subhodeep | 2022-11-09 | 2022-11-10 | 2022-11-09 | 2022-11-10 | Completed
|  | Populating childdoctype with workflow history | 4 | Subhodeep | 2022-11-10 | 2022-11-10 | 2022-11-10 | 2022-11-10 | Completed
|  | Front End Validation(Display and Mandatory depends on) | 2 | Subhodeep | 2022-11-10 | 2022-11-10 | 2022-11-10 | 2022-11-10 | Completed
|  | Employee Reimbursement |  | Nehal |  |  | 2022-11-19 | 2022-11-18 | Completed | Task added on 19th Dec 2022
|  | Print Format | 8 | Subhodeep | 2022-11-11 | 2022-11-11 | 2022-11-10 | 2022-11-11 | Completed
| PHARMACY | Doctype Creation | 2 | Subhodeep | 2022-11-14 | 2022-11-14 | 2022-11-11 | 2022-11-11 | Completed
|  | Workflow Creation(Worfklow state, Action, Transition rules) | 2 | Subhodeep | 2022-11-14 | 2022-11-14 | 2022-11-11 | 2022-11-11 | Completed
|  | Child doctype Calculation(Total, Grand total) | 2 | Subhodeep | 2022-11-14 | 2022-11-14 | 2022-11-11 | 2022-11-11 | Completed
|  | Cancellation and Transfer to authority within workflow | 4 | Subhodeep | 2022-11-14 | 2022-11-15 | 2022-11-14 | 2022-11-14 | Completed
|  | Populating childdoctype with workflow history | 4 | Subhodeep | 2022-11-15 | 2022-11-15 | 2022-11-14 | 2022-11-14 | Completed
|  | Front End Validation(Display and Mandatory depends on) | 2 | Subhodeep | 2022-11-15 | 2022-11-15 | 2022-11-14 | 2022-11-14 | Completed
|  | Print Format | 8 | Subhodeep | 2022-11-16 | 2022-11-16 | 2022-11-14 | 2022-11-15 | Completed
| PATIENT REFUND | Doctype Creation | 2 | Nehal | 2022-11-14 | 2022-11-14 | 2022-11-10 | 2022-11-10 | Completed
|  | Workflow Creation(Worfklow state, Action, Transition rules) | 2 | Nehal | 2022-11-14 | 2022-11-14 | 2022-11-11 | 2022-11-11 | Completed
|  | doctype Calculation(Total, Grand total) | 2 | Nehal | 2022-11-14 | 2022-11-14 | 2022-11-10 | 2022-11-10 | Completed
|  | Cancellation and Transfer to authority within workflow | 4 | Nehal | 2022-11-14 | 2022-11-15 | 2022-11-11 | 2022-11-11 | Completed
|  | Populating childdoctype with workflow history | 4 | Nehal | 2022-11-15 | 2022-11-15 | 2022-11-11 | 2022-11-11 | Completed
|  | Front End Validation(Display and Mandatory depends on) | 2 | Nehal | 2022-11-15 | 2022-11-15 | 2022-11-14 | 2022-11-14 | Completed
|  | Print Format | 8 | Nehal | 2022-11-16 | 2022-11-16 | 2022-11-14 | 2022-11-14 | Completed
|  | Update in Calculation as per discussion | 16 | Abhishek |  |  | 2022-12-02 | 2022-12-05 | Completed
| Payment Workflow | Doctype, Child doctype Creation | 1 | Nehal | 2022-11-15 | 2022-11-15 | 2022-11-16 | 2022-11-16 | Completed
|  | Workflow Creation(Worfklow state, Action, Transition rules) | 2 | Nehal | 2022-11-15 | 2022-11-15 | 2022-11-16 | 2022-11-16 | Completed
|  | Cancellation and Transfer to authority within workflow | 2 | Nehal | 2022-11-15 | 2022-11-15 | 2022-11-16 | 2022-11-16 | Completed
|  | Populating childdoctype with workflow history | 2 | Nehal | 2022-11-15 | 2022-11-15 | 2022-11-16 | 2022-11-16 | Completed
|  | Applying Filters to fetch Invoices in Childtable During Audit verification vendor wise grouping of invoice payment must be done | 16 | Nehal | 2022-11-16 | 2022-11-17 | 2022-11-30 | 2022-12-01 | Completed
|  | Front End Validation(Display and Mandatory depends on) | 1 | Nehal | 2022-11-17 | 2022-11-17 | 2022-12-01 | 2022-12-01 | Completed
|  | Print Format | 8 | Nehal | 2022-11-18 | 2022-11-18 | 2022-12-02 | 2022-12-02 | Completed
|  | Only unpaid invoices would be fetched | 12 | Abhishek | 2022-12-05 | 2022-12-06 | 2022-12-05 | 2022-12-06 | Completed
Automation of Worklow | Creation of Role |  | 8 | Abhishek | 2022-11-15 | 2022-11-15 | 2022-11-14 | 2022-11-14 | Completed
| Creation of Workflow State |  | 8 | Abhishek | 2022-11-16 | 2022-11-16 | 2022-11-15 | 2022-11-15 | Completed
| Creation of Workflow Action Master |  | 8 | Abhishek | 2022-11-17 | 2022-11-17 | 2022-11-15 | 2022-11-15 | Completed
| Creation of Workflow, Provision to set amount for conditional state of workflow |  | 8 | Abhishek | 2022-11-18 | 2022-11-18 | 2022-11-16 | 2022-11-16 | Completed
| Creation of Custom role permission |  | 8 | Abhishek | 2022-11-21 | 2022-11-21 | 2022-11-16 | 2022-11-16 | Completed
Employee | Modification in employee | Role Selection from Employee | 4 | Nehal | 2022-11-17 | 2022-11-17 | 2022-11-15 | 2022-11-15 | Completed
Attachments | Checkbox must be present before every attchment field and the attach button should only appear if checkbox is ticked This will be done for all the 7 Notesheets |  | 4 | Nehal | 2022-11-24 | 2022-11-24 | 2022-11-15 | 2022-11-15 | Completed
| Attachments to be added in all Invoices 1. Add a Purchase receipt note attachment for PO Consumable. 2. Requisition form or Indent 3. MM decides from which vendor to buy (Request for Quotation) 4. Vendor Quotation (could be multiple) 5. Comparative Statement 6. Approval Sheet 7. PO (Present) 8. Delivery Challan (Present) 9. Invoice (Present) 10. GRN (Present) |  | 40 | Abhishek, Priytesh | 2022-11-30 | 2022-12-02 | 2022-11-30 | 2022-12-02 | Completed
Login Data | As Soon as user Login the company should be fetched in the Company field of Notesheet |  | 8 | Subhodeep | 2022-11-25 | 2022-11-25 | 2022-11-16 | 2022-11-16 | Completed
Supplier | Add priority wise payment for Supplier |  | 1 | Priytesh | 2022-11-25 | 2022-11-25 |  |  | Completed
Upload requirement | While uploading Attachments user should only be able to upload files in the invoices only in pdf format |  | 8 | Subhodeep | 2022-11-28 | 2022-11-28 | 2022-11-28 | 2022-11-28 | Completed
| Option to upload attachment in Link, Photo and other format must be disabled |  | 16 | Subhodeep | 2022-11-29 | 2022-11-30 | 2022-11-29 | ` | On Hold | Build json not working for frappe V14 Subhodeep has worked on 29th Nov and 30th Nov To research the feasibility
Dynamic allocation of signatures in print format | Employee reviewing the notsheeet would be grouped dynamically to be appended in grouped order whose sequence would be decided by the end user | Needs to create for all print format, 13*7=91+24 (other print format)= 115*3 = 345 | 345 | Abhishek, Priytesh | 2022-11-17 | 2022-11-21 | 2022-11-17 | 2022-11-21 | Completed
Download Attachments | Download button must be created for all attachements after clicking on which the selected attachments along with their line items would be downloaded |  | 32 | Subhodeep | 2022-12-05 | 2022-12-07 | 2022-12-01 | 2022-12-06 | Completed | 7 worklfow
User Roles & Permission | Role Permission - e.g. store keeper will have the permission to add, update, delete forms |  | 16 | Priytesh | 2022-11-16 | 2022-11-17 | 2022-11-16 | 2022-11-17 | Completed
| User Creation - creation of employee / users |  | 8 | Subhodeep | 2022-11-25 | 2022-11-25 | 2022-11-25 | 2022-11-25 | Completed
| User Permission - user will be able to see his / her department information |  | 16 | Subhodeep | 2022-11-16 | 2022-11-17 | 2022-11-16 | 2022-11-17 | Completed | data for corresponding users to be created in production env.
| Workspace Creation |  | 1 | Priytesh |  |  |  |  | Completed
Bank IFSC Code | After entering the IFSC Code the other bank details must be auto fetched using API in all forms where bank details is present |  | 4 | Nehal | 2022-12-02 | 2022-12-02 | 2022-12-02 | 2022-12-02 | Completed
Print Format Attachments | PO_CONSUMABLE | Print Format with all attachments | 2 | Subhodeep | 2022-12-05 | 2022-12-05 | 2022-12-08 | 2022-12-08 | Completed
|  | Print Format for Note sheet along with each attachment like(Notesheet with Invoice, Notesheet with PO, Notesheet with Delivery Challan, Notesheet with Bill Summary, Notesheet with Credit Memo, Notesheet with GRN, Notesheet with others) | 14 | Subhodeep | 2022-12-05 | 2022-12-06 | 2022-12-09 | 2022-12-09 | Completed
| PO_MM | Print Format with all attachments | 2 | Nehal | 2022-12-05 | 2022-12-05 | 2022-12-05 | 2022-12-05 | Completed
|  | Print Format for Note sheet along with each attachment like(Notesheet with Invoice, Notesheet with PO, Notesheet with Delivery Challan, Notesheet with Bill Summary, Notesheet with Credit Memo, Notesheet with GRN, Notesheet with others) | 14 | Nehal | 2022-12-05 | 2022-12-06 | 2022-12-05 | 2022-12-05 | Completed
| PO_CONSIGNMENT | Print Format with all attachments | 2 | Subhodeep | 2022-12-07 | 2022-12-07 | 2022-12-06 | 2022-12-07 | Completed
|  | Print Format for Note sheet along with each attachment like(Notesheet with Invoice, Notesheet with PO, Notesheet with Delivery Challan, Notesheet with Bill Summary, Notesheet with Credit Memo, Notesheet with GRN, Notesheet with others) | 14 | Subhodeep | 2022-12-07 | 2022-12-08 | 2022-12-07 | 2022-12-07 | Completed | 15 Print Formats completed for consignment of attachments present in child table Credit Note and PO
| NON PO _ CONTRACT | Print Format with all attachments | 2 | Nehal | 2022-12-07 | 2022-12-07 | 2022-12-06 | 2022-12-06 | Completed
|  | Print Format for Note sheet along with each attachment like(Notesheet with Invoice, Notesheet with PO, Notesheet with Delivery Challan, Notesheet with Bill Summary, Notesheet with Credit Memo, Notesheet with GRN, Notesheet with others) | 14 | Nehal | 2022-12-07 | 2022-12-08 | 2022-12-07 | 2022-12-07 | Completed
| NON PO _ NON-CONTRACT | Print Format with all attachments | 2 | Nehal | 2022-12-07 | 2022-12-07 | 2022-12-09 | 2022-12-09 | Completed
|  | Print Format for Note sheet along with each attachment like(Notesheet with Invoice, Notesheet with PO, Notesheet with Delivery Challan, Notesheet with Bill Summary, Notesheet with Credit Memo, Notesheet with GRN, Notesheet with others) | 14 | Nehal | 2022-12-07 | 2022-12-09 | 2022-12-09 | 2022-12-09 | Completed
| PHARMACY | Print Format with all attachments | 2 | Subhodeep | 2022-12-09 | 2022-12-09 | 2022-12-07 | 2022-12-08 | Completed
|  | Print Format for Note sheet along with each attachment like(Notesheet with Invoice, Notesheet with PO, Notesheet with Delivery Challan, Notesheet with Bill Summary, Notesheet with Credit Memo, Notesheet with GRN, Notesheet with others) | 14 | Subhodeep | 2022-12-09 | 2022-12-12 | 2022-12-08 | 2022-12-08 | Completed | 14 Print Formats completed for pharmacy of attachments present in child table Credit Note and PO
| PATIENT REFUND | Print Format with all attachments | 2 | Nehal | 2022-12-09 | 2022-12-09 | 2022-12-08 | 2022-12-08 | Completed
|  | Print Format for Note sheet along with each attachment like(Notesheet with Patient Cancellation / Refund application Form, Notesheet with Self Declaration Form, Notesheet with Refund Sheet, Notesheet with Final Bill, Notesheet with Refund receipt, Notesheet with Insurance document, Notesheet with Self Identification document) | 14 | Nehal | 2022-12-09 | 2022-12-12 | 2022-12-08 | 2022-12-08 | Completed
|  | KIMS demo feedback (20th dec) - 1.Account Holder name will be same as Name of the person” field of ID Proof Section 2. MRN no should be fetched from Patient IP/UHID no |  | Nehal | 2022-12-21 | 2022-12-21 | 2022-12-21 | 2022-12-21 | Completed
New Print Format | Print format for newly added attachment field for PO Consumable | Print format for Following 1. Add a Purchase receipt note attachment for PO Consumable. 2. Requisition form or Indent 3. MM decides from which vendor to buy (Request for Quotation) 4. Vendor Quotation (could be multiple) 5. Comparative Statement 6. Approval Sheet | 12 | Priytesh | 2022-12-09 | 2022-12-12 | 2022-12-09 | 2022-12-09 | Completed | Each doctype contain 13 attachment(Estimation for 7 is above new 6 attachments will be added) Each print format would take 2 hours So 7*6= 42 Printformats, 42*2= 84 hours
| Print format for newly added attachment field for PO Consignment | Print format for Following 1. Add a Purchase receipt note attachment for PO Consumable. 2. Requisition form or Indent 3. MM decides from which vendor to buy (Request for Quotation) 4. Vendor Quotation (could be multiple) 5. Comparative Statement 6. Approval Sheet | 12 | Priytesh | 2022-12-12 | 2022-12-13 | 2022-12-09 | 2022-12-09 | Completed
| Print format for newly added attachment field for PO Material Management | Print format for Following 1. Add a Purchase receipt note attachment for PO Consumable. 2. Requisition form or Indent 3. MM decides from which vendor to buy (Request for Quotation) 4. Vendor Quotation (could be multiple) 5. Comparative Statement 6. Approval Sheet | 12 | Subhodeep | 2022-12-13 | 2022-12-14 | 2022-12-09 | 2022-12-09 | Completed
| Print format for newly added attachment field for Pharmacy | Print format for Following 1. Add a Purchase receipt note attachment for PO Consumable. 2. Requisition form or Indent 3. MM decides from which vendor to buy (Request for Quotation) 4. Vendor Quotation (could be multiple) 5. Comparative Statement 6. Approval Sheet | 12 | Nehal | 2022-12-13 | 2022-12-14 | 2022-12-09 | 2022-12-09 | Completed
| Print format for newly added attachment field for Non Po contract | Print format for Following 1. Add a Purchase receipt note attachment for PO Consumable. 2. Requisition form or Indent 3. MM decides from which vendor to buy (Request for Quotation) 4. Vendor Quotation (could be multiple) 5. Comparative Statement 6. Approval Sheet | 12 | Priytesh | 2022-12-14 | 2022-12-15 | 2022-12-09 | 2022-12-09 | Completed
| Print format for newly added attachment field for Non Po Non contract | Print format for Following 1. Add a Purchase receipt note attachment for PO Consumable. 2. Requisition form or Indent 3. MM decides from which vendor to buy (Request for Quotation) 4. Vendor Quotation (could be multiple) 5. Comparative Statement 6. Approval Sheet | 12 | Subhodeep | 2022-12-14 | 2022-12-15 | 2022-12-09 | 2022-12-09 | Completed
| Print format for newly added attachment field for Patient refund | Print format for Following 1. Add a Purchase receipt note attachment for PO Consumable. 2. Requisition form or Indent 3. MM decides from which vendor to buy (Request for Quotation) 4. Vendor Quotation (could be multiple) 5. Comparative Statement 6. Approval Sheet | 12 | Nehal | 2022-12-14 | 2022-12-15 | 2022-12-09 | 2022-12-09 | Completed
| Other Print format: 1. Master Invoice 2. Notesheet Attachment 3. Journal Entry for Payment Workflow |  | 16 | Subhodeep | 2022-12-15 | 2022-12-19 |  |  | On Hold | 1 combined print format for Master Invoice and Notesheet attachment will be made (1*7=7) + 1 (Jounal Entry) = 8*2=16 NOT TO BE DONE
Print format new requirement | Date and Time for Approval of signature be fetched in print format for all Note-sheet types |  | 24 | Nehal, Subhodeep | 2022-12-16 | 2022-12-19 | 2022-12-13 | 2022-12-13 | Completed | Abhishek Completed
| Date of Approval' written across all print formats created should be replaced by 'Date' |  | 16 | Subhodeep | 2022-12-19 | 2022-12-20 | 2022-12-19 | 2022-12-20 | Completed
Third Party Approval | From the Workflow there should be a provision to send the notesheet for approval for sending to third person |  | 24 | Abhishek | 2022-12-07 | 2022-12-09 | 2022-12-07 | 2022-12-09 | Completed
Patient Refund | Update in Insurance Type, reason of refund |  | 16 | Abhishek |  |  | 2022-12-12 | 2022-12-13 | Completed
Reports & Dashboard | MIS Report |  | 32 | Abhishek | 2022-12-12 | 2022-12-15 | 2022-12-16 | 2022-12-19 | Completed
| Chart and Dash Board | 1.Dashboard will highlight the following details on a monthly basis. For e.g. a.No. Of Invoices Received b.No. Of Invoices In Process c.No. Of Invoices Pending d.No. Of Invoices Closed 2.Invoice details in the Dashboard shall be Department wise. For e.g. User belonging to a Bio Medical department shall be able to see his / her department details | 16 | Nehal | 2022-12-16 | 2022-12-19 | 2022-12-20 | 2022-12-21 | Completed
Email | Email to Vendor | Mail shall be triggered to the Vendor on following cases : a.Form is verified and saved from Note Creator b.Passed for payment for Individual Note-sheets c. Payment done after completion of Payment workflow. | 8 | Priytesh | 2022-12-20 | 2022-12-20 | 2022-12-12 | 2022-12-12 | Completed
| Email to Department / Note Creator | At each user level of approval to all concerened users containing all attachments attached in Note-creator | 24 | Abhishek | 2022-12-14 | 2022-12-16 | 2022-12-19 | 2022-12-21 | Completed | Scheduler email will be triggered based on User role and the user will receive a consolidated email of total number of Notesheets pending for approval from his login, Total Notesheets passed for payment and total Notesheets whose payment is done
| Mail rejection notification | Notification in form of email to be sent to users whenever an Invoice is rejected and transfered to the authority who have approved it | 16 | Abhishek | 2022-12-20 | 2022-12-21 | 2022-12-22 | 2022-12-23 | Completed
| Email to Users | All users in the workflow shall receive email if payment is not cleared within 80% of threshold date | 8 | Abhishek | 2022-12-20 | 2022-12-20 | 2022-12-23 | 2022-12-26 | Completed
| Email to third party | When a third party approval is asked a email to the third party employee must be triggered | 4 | Priytesh | 2022-12-21 | 2022-12-21 | 2022-12-13 | 2022-12-13 | Completed | 21-Dec Development Completes
Invoice requirement | A Invoice page must be developed for Invoice receive entry before a Notesheet is created for it |  | 24 | Nehal | 2022-12-12 | 2022-12-14 | 2022-12-12 | 2022-12-14 | Completed
| Date of Receipt field to be added | [7 empty] | Completed
Application UI | Designing of application UI |  |  | Subhodeep |  |  | 2022-12-21 | 2022-12-22 | Completed | Awaiting feedback from KIMS
| Test case Documentation | Master Screens - 8 screens | 12 | Sharmistha | 2022-11-08 | 2022-11-09 | 2022-11-09 | 2022-11-10 | Completed
|  | PO Based Invoices - Consumable (T-Kitchen) a. Header section b. Table section c. Signature section (workflow) | 24 | Sharmistha | 2022-11-09 | 2022-11-14 | 2022-11-10 | 2022-11-15 | Completed
|  | Update of PO Consumable Test Cases based on last discussion with KIMS | 1.5 | Sharmistha | 2022-11-30 | 2022-11-30 | 2022-12-19 | 2022-12-19 | Completed | This task added on 30th Nov 2022
|  | PO Based Invoices - Consignment a. Header section b. Table section c. Signature section (workflow) | 8 | Sharmistha | 2022-12-01 | 2022-12-07 | 2022-11-17 | 2022-11-18 | Completed | 01/12 - worked on 1st half
|  | PO Based Invoices - Pharmacy a. Header section b. Table section c. Signature section (workflow) | 8 | Sharmistha | 2022-12-07 | 2022-12-07 | 2022-12-07 | 2022-12-08 | Completed | 07/12 - started working on 2nd half of 7th Dec as first half had req discussion
|  | PO Based Invoices - Material Management a. Header section b. Table section c. Signature section (workflow) | 8 | Sharmistha | 2022-12-08 | 2022-12-08 | 2022-12-09 | 2022-12-13 | Completed | 09/12 - worked for 1h in the morning 13/12 - worked on 12th Dec for 1h
|  | Non PO Based Invoices - 2 forms (Contract and Non Contract) a. Header section b. Table section c. Signature section | 24 | Sharmistha | 2022-12-09 | 2022-12-13 | 2022-12-18 | 2022-12-18 | Completed
|  | Other Invoices - Patient Refund | 16 | Sharmistha | 2022-12-14 | 2022-12-15 | 2022-12-14 | 2022-12-15 | Completed
|  | Payment workflow | 16 | Sharmistha | 2022-12-16 | 2022-12-19 | 2022-12-17 | 2022-12-17 | Completed
|  | Email | 8 | Sharmistha | 2022-12-20 | 2022-12-20 | 2022-12-17 | 2022-12-17 | Completed
|  | Print Format - All 7 invoices PDF / print Print view of invoice and supporing documents at each level of the workflow | 24 | Sharmistha | 2022-12-21 | 2022-12-23 | 2022-12-16 | 2022-12-16 | Completed
|  | Dashboard for user role | 5 | Sharmistha | 2022-12-26 | 2022-12-26 | 2022-12-16 | 2022-12-16 | Completed
|  | Report | 3 | Sharmistha | 2022-12-26 | 2022-12-26 | 2022-12-22 | 2022-12-22 | Completed
|  | Invoice Form | 3 | Sharmistha | 2022-12-14 | 2022-12-14 | 2022-12-14 | 2022-12-14 | Completed | 14/12 - Task added on 14th dec. the req came up on 9th dec during demo
| System Testing (Writing of Test Cases, Test Execution) | 7 invoice workflows - approve, Cancel, Reject and transfer to all users in the workflow including 3rd party) - payment workflow - filter criteria, verification of invoice records based on vendor grouping - print formats - email - user role permission | 280 | Sharmistha, Abhishek, Nehal, Priytesh, Subhodeep. Shruthi | 2022-12-27 | 2023-01-03 | 2022-12-22 |  | In Progress | 29-Dec Project Completes ( to be rechecked)
| Test Report |  | 8 | Sharmistha | 2023-01-04 | 2023-01-04 |  |  | Not Started