## ScopeOfWork
Modules | Sub Modules | Details | Estimated hrs | Assumption | Comments
Users | Farmer
Department Users
| Experts |  |  | District wise (14 districts as per Google)
Super Admin
Registration | Existing user / Profile Details |  | 4
New User / Profile Details
Farmer's Page UI |  | UI will have menu options as specified in Farmer sheet | 24
Instruction Video |  | Instructions regarding handling the application should pop up when the application isopened for the first time after being downloaded. Either, a YouTube link to the video containing the instructions should be provided | 1
Land Details | Land details include location, area, |  | 16 | location might be district wise. so , google map integration
Crop Details | Name, age of crop and Upload Crop Image | The image will have stem, bud, leaf, fruit, flower | 8
Diagnosis of Crop Image |  | Plant damage have an accuracy above 90% then, diagnosis will be be performed by AI |  |  | Unable to estimate as AI to be integrated
Plant damage have an accuracy below 90% then, diagnosis will be be performed by Experts (KVK)
Experts feedback to be stored in Application (M-Velanmai)
1. Farmers have to focus the phone camera against the crop symptom. If the symptom matches with the images stored in the cloud server, then the technical advisory message to solve the damage symptom will pop up instantly. 2. About 95 % matches should only deliver an advice to the farmers if not, the farmer should be advised to take a photo and submit it to the experts for solution. 3.Advisories as replies to the farmers’ queries will be delivered in short form as Text or Voice SMS and if a farmer needs additional information, a link to the library has to be provided where the required information can be tracked.
Auto Reply to Farmer |  | Generation of auto reply to farmers’ repeated queries from the data base for ease of giving advisories by experts. | 24
Additional Features |  | 1. Push notifications to indicate various operations to be done by a farmer in a particular crop based on date of sowing. | 8
|  | 2. Addition of weather module: Predicting pest and disease occurrence based on weather modules and providing it in the form of Professional tips. | 8
|  | 3. Creation of Fertilizer calculator with the provision to get recommendations based on soil test results, pest and disease calendar for various crops | 8
|  | 4.Integration of DEMIC advisories | 2 | Point 4 - DEMIC advisories could be set of people per District
Reports |  | A detailed report on methodology used for development along with graph and tables indicating the accuracy regarding training, testing and validation, metric equations, confusion matrix for CNN/ AI models used to develop M-Velanmai app has to be submitted |  |  | Not clear
Interactive Interface | Farmer - Farmer | The advice for the queries/ photo sent by the farmer, should be delivered to the concerned farmer as personalized advisory as well as to be made available in the forum for the notice of other farmers | 8
| Farmer - Scientist | 1.Separate admin access for expert’s log in via mobile and desktop computer | 16
2.Each KVK to be assigned with one common app. ID to access and answer the queries
|  | 3.Super admin access for ICT infrastructure (backup/recovery) maintenance |  | Super admin will be part of Department
Feedback | Farmer's Feedback | 1.Recording of feedback from farmers with auto call mechanism. | 16
|  | 2.Rating of advisories by farmers to indicate their level of satisfaction | 8
Other Features |  | 1.Updation of application features with notification to users. 2.A responsive website to display the queries received from the farmers in the form of Photo, Text / Voice SMS.
Website |  | Farmer's query will be published in the form of photo or text/ voice sms |  |  | Not clear wrt content
Language Preference |  | 1.Advisories will be delivered in English or Tamil as preferred by the farmers. 2.Use of either Tamil or English language in the process of interaction | 24
R&D |  | Language preference auto call mechanism Push notifications based on date of sowing Addition of weather module Creation of Fertilizer calculator Feedback Rating | 65
Artificial Intelligence
240

## Farmer
Login
Land Details | Crop | FAQ | Add. Features | Weather | Forum | Feedback | History | Pop-Up
Fertilizer
DEMIC advisories

## Depart Users
Login | Assumptio
Reports PDF

## Experts
Login | Application | Website
Assignment of application ID unique to each KVK
New Queries
Old Queries
Pending Queries
Farmer's feedback rating