## Slide 1
Campus Management Application
At
World Skill Center
WEEKLY PROJECT STATUS REPORT
17-Feb-2023

## Slide 2: PROJECT SUMMARY
OVERALL PROJECT STATUS (R)ed, (A)mber, (G)reen | RISK
PROJECT NAME | Campus Management Application At World Skill Center(WSC) |  | 
SOUL POC | sharmistha.panda@soulunileaders.com | WSC POC | 
PROJECT START DATE | 03-02-2023 | PROJECT END DATE | 03-02-2024
Red | Likely delay in overall project schedule | Amber | Some Activities are delayed | Green | On track

## Slide 3: TASKS PLANNED THIS WEEK
TASKS |  | 
Description | Owner | Status
Shared the template for WSC team details | SOUL | Done
Updated the project plan and shared with WSC stakeholders | SOUL | Done
Start of requirement gathering sessions | SOUL and WSC | Not Started

## Slide 4: OVERALL PROJECT PROGRESS TIMELINE

## Slide 5: RISKS & ISSUES
ISSUES |  |  |  | 
Description | Issue Priority | Proposed Solution | Issue Owner | Status
WSC SPOC and SME team details are not available | High | WSC to share the team details with SOUL | WSC | Open
A delay in discussing and capturing requirements | High | WSC to propose the requirements gathering schedule | WSC | Open
RISKS |  |  |  | 
Description | Risk Impact | Mitigation | Risk Owner | Status

## Slide 6: UPCOMING WORK
WHAT’S NEXT |  | 
Description | Owner | Status
Requirements gathering sessions with WSC SME’s | WSC | Open

## Slide 7
THANK YOU