## Slide 1
Campus Management Application
At
World Skill Center
WEEKLY PROJECT STATUS REPORT
15-Sep-2023

## Slide 2: PROJECT SUMMARY
OVERALL PROJECT STATUS (R)ed, (A)mber, (G)reen | DELAY
PROJECT NAME | Campus Management Application At World Skill Center(WSC) |  | 
SOUL POC | sharmistha.panda@soulunileaders.com | WSC POC | bishnupriya.panda@worldskillcenter.org
PROJECT START DATE | 03-02-2023 | PROJECT END DATE | 03-02-2024
Red | Likely delay in overall project schedule | Amber | Some Activities are delayed | Green | On track

## Slide 3: CAMPUS MANAGEMENT SOFTWARE AT WORLD SKILL CENTER
Priority 1 Release Activities |  |  | 
Description | Owner | Status | Remarks
Campus Management Software At World Skill Center - Priority 1 Release - SLCM MODULE (features listed in slides 14 to 17) | SOUL - WSC | On-Going | SOUL team will set up the student applicant's guest user login - 11-Sep-2023 Update : DONE
 |  |  | With the above mentioned login, SOUL team will show the application to the WSC IT team - 13-Sep-2023 Update : DONE. Changes proposed by WSC IT team
 |  |  | The data template for Student Applicants will be shared by SOUL team with WSC - 16-Sep-2023
 |  |  | The data will be entered to the template by WSC - 18-Sep-23
 |  |  | WSC will enter the data into the system with the assistance of SOUL team - 21-Sep~22-Sep-23
 |  |  | UAT will be done by WSC
 |  |  | Production roll-out - 18-Sep-23 Update: date to be decided

## Slide 4: CAMPUS MANAGEMENT SOFTWARE AT WORLD SKILL CENTER
Priority 1 Release Activities |  |  | 
Description | Owner | Status | Remarks
Campus Management Software At World Skill Center - Priority 1 Release - HRMS MODULE (features listed in slides 18 to 19) | SOUL - WSC | OPEN | On August 28, 2023, SOUL team demonstrated the application to WSC stakeholders after completion of development activities. During the demonstration, SOUL team received feedback (changes) Production roll-out shall be scheduled after SLCM release (post September 18, 2023

## Slide 5: TASKS PLANNED/ACCOMPLISHED THIS WEEK
TASKS |  |  | 
Description | Owner | Status | Remarks
Design phase | SOUL | DELAY | The design documents of the following modules have been shared with module owners for their digital sign off: Students Management & Academic System Training Of Trainers Procurement & Inventory Management Human Resources Management System Training & Placement Infrastructure Management Finance and Accounting System The details of design phase shared in Slide 6 and 7
Application demonstration to WSC stakeholders | SOUL | OPEN | Details shared in slide 8

## Slide 6: DESIGN PHASE - DIGITAL SIGN OFF STATUS
Module | Owner(WSC) | Status | Remarks
Training and Placement | Mr. Rajan Pradhan | DELAY | 21-Aug-23: Documents sent to module owner for digital sign off
Procurement & Inventory Management | Mr. Chandan Kumar | DELAY | 21-Aug-23: Documents sent to module owner for digital sign off
Human Resources Management System | Ms. Shweta Choudhury | DELAY | 22-Aug-23: Documents sent to module owner for digital sign off
Infrastructure Management : Maintenance & Management | Mr. Brahmananda Sahoo | DONE | 22-Aug-23: Documents sent to module owner for digital sign off 24-Aug-23: WSC module owner has approved
Infrastructure Management : Project Plan and Monitoring | Mr. Sanjay Padhi | DELAY | 22-Aug-23: Documents sent to module owner for digital sign off
Finance and Accounting System | Mr. Bibhu Behura / Mr. Subodha Patra | DELAY | 22-Aug-23: Documents sent to module owner for digital sign off

## Slide 7: DESIGN PHASE - DIGITAL SIGN OFF
Module | Owner(WSC) | Status | Remarks
Students Management Modules, Academic System - Admission | Mr. Anil Das | DELAY | 05-Sep-23: Documents sent to module owner for digital sign off
Students Management Modules, Academic System - Academics | Ms. Suppiah Nagammal / Mr. Subhasis Das, Mr. Anil Das, Ms. Suguna Srinivasan | PARTIALLY DONE | 05-Sep-23: Documents sent to module owner for digital sign off 08-Sep-23: Received sign off (approval) from Academy module owner
Students Management Modules,Academic System - Examination | Mr. Suresh Kumar | DELAY | 05-Sep-23: Documents sent to module owner for digital sign off
Training Of Trainers (ToT) - Academy | Ms. Suppiah Nagammal | DELAY | 05-Sep-23: Documents sent to module owner for digital sign off
Training Of Trainers (ToT) - SOE | Mr. Subhasis Das | DELAY | 05-Sep-23: Documents sent to module owner for digital sign off
Students Management Modules,Academic System - Faculty workload, Hostel, Student clearance, Grievance,Feedback | Ms. Sushree / Mr. Anil Das | DELAY | 12-Sep-23: Documents sent to module owner for digital sign off
Update : The WSC module owners' digital approval is still pending. For the digital sign-off, the WSC IT team will coordinate

## Slide 8: CAMPUS MANAGEMENT SOFTWARE AT WORLD SKILL CENTER APPLICATION DEMONSTRATION
Description | Owner | Status | Remarks
SLCM (Admission, Academics, Examination) | SOUL | DONE | SOUL team demonstrated the application to WSC stakeholders on 16th and 17th August, 2023
HRMS | SOUL | DONE | SOUL team demonstrated the application to WSC stakeholders on 28 August, 2023
Hostel and Student Admission Fees | SOUL | DONE | SOUL team demonstrated the application to WSC stakeholders on 01 September, 2023
Procurement and Inventory management | SOUL | DELAY | 08-Sep-23:SOUL team demonstrated the application to WSC stakeholders on 08 September, 2023 Update: Subsequent meeting in the week of 11-Sep ~ 15-Sep could not be conducted due to unavailablity of stakeholders

## Slide 9: OVERALL PROJECT PROGRESS TIMELINE
Milestone 1 - Gap Analysis Document and SRS documents signed off on 12 June, 2023

## Slide 10: ISSUES
TASKS |  |  | 
Description | Owner | Status | Remarks
Integration - Payment Gateway (HDFC) | SOUL - WSC | DONE | 08-Sep-23: HDFC security audit is completed. HDFC team to provide the live kit Update : SOUL team received the live kit on 13-Sep-23. SOUL team has successfully completed the payment integration test with the live kit
Integration - Payment Gateway (Axis) | SOUL - WSC | BLOCKER | 08-Sep-23: SOUL team initiated the payment integration development but the test kit is not wroking on Firefox browser. The test kit should work on all browsers. Axis bank team has been already communicated about it. SOUL team is awaiting a response from them Update: Axis bank development team is checking the issue
Application demonstration to WSC stakeholders - Infrastructure Module | SOUL | DELAY | 08-Sep-23: The demonstration was scheduled for the week of September 4–8, 2023 however it was canceled due to unavailability of stakeholders Update: No meeting held

## Slide 11: ISSUES
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
A delay in discussing and capturing requirements | High | The revised project plan was discussed on 06-Apr, during weekly Project review meeting update : schedule has been reviwed with WSC stakeholders | WSC | OPEN | WSC stakeholders to acknowledge the delay | 
SOUL highlighted the addition to scope (change request) for the features that were discovered during the requirements study but were not specified in the request for proposal document | High | WSC stakeholders to acknowledge the change request | WSC | OPEN | The change requests will be acknowledged by WSC | Update: SOUL team sent an email to WSC to acknowledge the change reqests and the additional effort required for development. The change requests have been listed in Slide 8

## Slide 12: ISSUES
Description | Issue Priority | Proposed Solution | Issue Owner | Status | Action Item | Remarks
Availability of OCAC server | High | WSC stakeholder to ensure availability of the requested server version | WSC | OPEN | SOUL team has installed the application and database on the same server in the desktop version WSC to acknowledge the additional effort required (CR) to test the desktop version of the application | 

## Slide 13: CHANGE REQUESTS
Description | Module
Entrance Examination Process | Students Management
TrainingOfTrainers(TOT) | Students Management
Recruitment Process | Human Resources Management System
Employee Re-Engagement | Human Resources Management System
Testing effort for application installation in desktop version | OCAC Server
As discussed on 9th June 2023, the change requests Budget and Payroll have been removed from the the list

## Slide 14: UPCOMING WORK
WHAT’S NEXT |  |  | 
Description | Owner | Status | Remarks
Campus Management Software At World Skill Center - Priority 1 Release Activities (SLCM) - Student Enrollment | SOUL - WSC | On-Going | Activities mentioned in slide 3
Procurement and Inventory Management - Demonstration to WSC Stakeholders | SOUL | DELAY | Schedule for second session to be confirmed by WSC IT team

## Slide 15: Campus Management Software At World Skill Center Priority 1 Release
MODULE | SCOPE | SCREENS
Admission | Masters | Department
 |  | Course Type
 |  | Courses
 |  | Semester
 |  | Modules
 |  | Topic
 |  | Class Rooms
 | Admission Master | Academic Year
 |  | Academic Term
 |  | Academic Events
 |  | Academic Calendar Template
 |  | Documents
 |  | Documents Template
 |  | Eligibility Parameters
 | Student and Trainer | Student
 |  | Trainer
 |  | Student Categories
 |  | Student Btach
 | Tool | Course Enrollment Tool

## Slide 16: Campus Management Software At World Skill Center Priority 1 Release
MODULE | SCOPE | SCREENS
Academics | Groups & Schedules | Student Group
 |  | Class Schedule
 | Attendance and Leave Application | Student Attendance
 |  | Student Attendance Tool
 |  | Reason for Leave
 |  | Class Advisor and Manager Assignment
 |  | Student Leave Application
 | Mentor - Mentee | Mentor - Mentee
 |  | Communication
 | Tools | Class Scheduling Tool
 |  | Student Attendance Tool

## Slide 17: Campus Management Software At World Skill Center Priority 1 Release
MODULE | SCOPE | SCREENS
Examination | Master | Exam Type
 |  | Assessment Component
 |  | Grading Scale
 | Examination | Exam Declaration
 |  | Module Wise Exam Group
 |  | Exam Evaluation Plan
 |  | Exam Paper Setting
 |  | Student Backpaper Tracking
 | Evaluation | Component Evaluation
 |  | Component Re-Evalaution
 |  | Final Semester Result
 | Tools | Component Evaluation Tool
 |  | Component Re-Evalaution Tool
 |  | Final Semester Result Tool
 |  | Cumulative Marksheet Tool

## Slide 18: Campus Management Software At World Skill Center Priority 1 Release
ADDITIONAL FEATURES
Following are the additional features that will be part of priority 1 release : Student Enrollment Student Hostel Infrastructure (Maintenance & Management / Project Plan and Monitoring) Online Payment for HDFC (as long as HDFC gives SOUL team the live kit)

## Slide 19: Campus Management Software At World Skill Center Priority 1 Release
MODULE | SCOPE | SCREENS
HRMS | Masters | Employment Type
 |  | Branch (Location)
 |  | Department
 |  | Designation
 |  | Employee Grade
 |  | Employee Group
 |  | Holiday List
 |  | Employee Separation Template
 | Employee Lifecyle | Employee
 |  | Employee Profile Updation
 |  | Employee Resgination
 |  | Employee Separation
 |  | Employee Suggestion
 |  | Employee Transfer

## Slide 20: Campus Management Software At World Skill Center Priority 1 Release
MODULE | SCOPE | SCREENS
HRMS | Leave Management | Leave Type
 |  | Leave Policy Assignment
 |  | Leave Allocation
 |  | Leave Application
 |  | Leave Block List
 |  | Compensatory Leave Request
 |  | Leave Policy
 | Shift Management | Shift Type
 |  | Shift Assignment
 |  | Shift Request
 | Attendance Management | Attendance
 |  | Employee Attendance Tool
 |  | Attendance Request
 |  | Employee Checkin
 | Settings | HR Settings

## Slide 21
THANK YOU